## Slide 1
TSP Coach Training
The Launch Process - Meeting 7
Notes: <number>

## Slide 2: Lecture Objectives
At the end of this lecture, you will
  understand what risks are and why managing risks is important
  understand the TSP risk management process
  recognize common occurrences and problems
  understand the roles of the coach and team leader in meeting 7
Notes: <number>

## Slide 3: Lecture Overview
Overview of meeting 7
Meeting 7 exercise
Coaching considerations
Reference material
Notes: <number>

## Slide 4: The Launch Process Meetings
1. Establish
product and
business
goals
2. Assign roles
and define
team goals
4. Build overall
and
near-term
plans
5. Develop
the quality
plan
6. Build individual
and
consolidated
plans
7. Conduct
Risk assessment
8. Prepare
management
briefing and
launch report
Launch
postmortem
9. Hold
management
review
3. Produce
development
strategy
and process
A TSP team coach guides the team through a defined process to develop its plan and to negotiate that plan with management.
Notes: Talk about how long this meeting usually takes : less than an hour.
Set context.

## Slide 5: Purpose/Rationale for Meeting 7
The purpose of meeting 7 is to
  identify major project risks
  evaluate risks for likelihood and impact
  select team members to track high-priority risks
Notes: <number>

## Slide 6: Meeting 7 Exercise
Exercise purpose.
  understand how launch meeting 7 is conducted
  be able to identify and classify team risks
  be able to use the IRTL tab in the TSP tool
  recognize issues that might arise and understand how to deal with them
Directions (see meeting 7 exercise workbook).
  assemble into your launch team groups
  conduct launch meeting 7 using script LAU7
  class discussion of how process worked
After the exercise, we will conclude the module with a discussion of coaching considerations from the lecture slides.
Notes: <number>

## Slide 7: Coaching Considerations
Involve all team members in the risk identification brainstorming process, round-robin style works well.
Ask the team not to list typical risks of ordinary living. Instead, guide them on concentrating on risks that are particularly applicable to the project.
Suggest guidance for high/med/low impact.
Challenge the team to be pro-active about risks, what can they do to avoid or mitigate it, make them take responsibility.
Get the team to agree on a few high-priority, high-impact risks to present to management.
If issues, not addressed in plan are identified, tasks to address them should be added to the plan.
Make sure risks are recorded and assigned to individuals.
Notes: Example of getting carried away: team member gets run over by a truck is a risk, the team identifies dozens of risks, the team does not identify any risks.
Round robin works to involve otherwise passive team members

## Slide 8: Messages to Remember
In meeting 7, the team identifies and assesses risks to the team meeting its plan.
The risks are documented in the team’s plan and each high-priority near-term risk is assigned to a team member for tracking.
A plan that addresses risks is more credible with management.
Notes: <number>

## Slide 9: Reference Material
Rationale for risk management
The TSP risk management process
Notes: <number>

## Slide 10: What is a Risk?
A risk is something that may or may not happen to jeopardize a project.
If it is certain to happen, it is an issue not a risk. Issues should be addressed in plans.
Since risks may or may not occur, they are managed differently than issues.
Notes: Coaching hint: If the team does not come up with any risks, the coach may lead them in risk identification.
Ask the question: what could cause us not to meet the project goals?
What would happen if we failed to achieve this goal?

## Slide 11: Risk Management
The principal considerations for risk management are to
  identify risks
  determine the likelihood of a risk occurring
  determine the impact of the risk if it actually occurred
  devise timely mitigation actions
  track risks
Risk management is important because
  many risks can be avoided
  the cost of recovering from a realized risk is usually much greater than the cost of avoiding the risk
  the right people can be made aware of the risks
A plan that addresses risks is more credible.
Notes: <number>

## Slide 12: Guidelines for Risk Management
The five guidelines for risk management are
  learn from past projects
  everyone on the team must manage risks
  the team must be empowered to manage the risks
  risks must be reviewed periodically
  significant risks should have an assigned owner
Notes: <number>

## Slide 13: The TSP Risk Management Process
The TSP risk management process is defined in two parts.
  Risk identification is handled during meeting 7.
  Risk tracking is handled during the weekly team meeting.
The risk identification process will be described in this lecture. Risk tracking will be covered later in this course.
The TSP risk identification process is guided by TSP Launch Meeting 7 Script (LAU7), located in the meeting 7 tab of the launch notebook.
Notes: <number>

## Slide 14: Risk Identification
The meeting begins with the coach explaining to the team what risk management is and why it is important.
Refer to step 3 of LAU7.
Next, the team leader leads the team in identifying risks (consider using these risk taxonomies to help stimulate risk identification; Taxonomy-Based Risk Identification or A Taxonomy of Operational Risks.).
The brainstorming method is a good tool to use because it separates the activities of identifying new risks and evaluating them.
  The team brainstorms until they cannot identify any more risks.
  During brainstorming, the team leader lists each identified risk on the white board or flip chart.
Notes: Ask audience:
What would prevent a team from achieving a specific goal?
What are some of the risks they see in the SecSys study?

## Slide 15: Impact Evaluation
After the risks have been identified, the team considers the impact of each risk if it actually occurs.
  The impact on schedule is an effective way to evaluate risks.
  Impact on cost and functionality may also be considered.
Risks are categorized by impact: high, medium, or low.
  The team determines how to quantify a high, medium, or low impact risk.
  A high-impact risk is one that delays the project schedule significantly.
Notes: Organization may have their own risk management process.

## Slide 16: Likelihood Evaluation
As each risk is evaluated for impact, the team leader also leads the team in determining the likelihood of the risk occurring, using a scale of high, medium, and low.
The team leader
  records the probability of risk occurrence as high, medium, or low for each risk identified
  asks the team whether risks with a high probability of occurrence are not actually issues
  asks the team whether risks with a low probability of occurrence are not merely worries
Notes: <number>

## Slide 17
Sample - Risks
Notes: <number>

## Slide 18: Risk Assignment
Team members are assigned to track high-priority risks, e.g., H-H, M-H, H-M, or M-M. Where possible, assign risks to corresponding roles.
Low-priority risks generally can be ignored.
Even if all risks are not assigned for tracking, they should be recorded, and the team should periodically review them.
Risks are tracked weekly.
Notes: <number>

## Slide 19: Risk Mitigation
Refer to step 4 of LAU7.
For each high-priority near-term risk, briefly discuss possible mitigation actions.
  A mitigation action would lessen or alleviate the impact and/or likelihood of occurrence for a risk.
  Consider adding tasks to mitigate risks.
If the team cannot identify a mitigation action, raise the risk to management and get their advice.
Notes: <number>

## Slide 20: Sample – Risk Mitigation
Notes: <number>