## Slide 1
TSP Executive Strategy Seminar
Exercise 2: Using Data

## Slide 3: Exercise Objective
This exercise
demonstrates the value of PSP data
illustrates ways to use these data
shows the value of having complete and accurate data
We first describe the data gathered by a software developer and describe how these data can be used.
We then provide some developer data and ask you to
examine the data
use the data to answer some questions

## Slide 4: TSP Data Gathering
The TSP support tool provides an easy way for team members to record their time, size, defect, and task data.
These are the same data they learn to gather and use with the PSP.
Using this tool, they
record when they start and stop each task
log each defect when found and fixed
enter the size of each product when it is built
record the date when each task is completed

## Slide 5: Making PSP and TSP Plans
With historical data, developers
make size estimates
estimate total development time
spread this time over the project phases
estimate the total defects injected
spread the defect estimates over the project phases
This estimating process works because developers
produce at a fairly consistent LOC/hour rate
spend roughly the same amount of time in each phase
inject about the same number of defects/KLOC

## Slide 6: The TSP Forms
Three TSP forms summarize all of a team’s data.
The WEEK form shows the team’s schedule performance for every project week.
The SUMQ (quality summary) form summarizes the quality data for each system, product, and product component.
The SUMP (plan summary) form holds the time, size, and defect data for each system, product, and product component.
This exercise only uses the data on the SUMP form. Exercises 3 and 4 use the WEEK and SUMQ forms.

## Slide 7: The SUMP Form -1
Project data
Size data
Time data
Data used in the exercise

## Slide 8: The SUMP Form -2
Defects removed data
Summary information
Data used in the exercise
Defects injected data

## Slide 9: Exercise Data
Student 14 has completed writing 4 of the PSP course programs and is planning program 5A.
You are given a SUMP form with the data for Student 14’s first four programs.
This SUMP form shows the actual time, size, and defect data for programs 1 through 4 and the distribution of these data among the development phases.
You are also given Student 14’s size estimate for program 5A (112 new and changed LOC).
In the exercise, you use these data to produce part of the estimate for program 5A.

## Slide 10: Exercise Instructions
Estimate Student 14’s development time for program 5A.
  Total estimated time = (Estimated size)/(historical LOC/hour)
Estimate the total defects Student 14 will likely inject.
  Defects injected = (5A estimated size)*(Defects to date)/(Size to date)
Estimate how long Student 14 will spend in test.
  Time in test = (Total estimated time)*(% time in test)/100

## Slide 11: The Exercise
Read the exercise instructions.
Form into groups of two to four to answer the questions.
When done, we will discuss the questions as a group.
20 minutes

## Slide 12: Exercise Discussion
What did you estimate for program 5A development time?
How many defects did you estimate Student 14 will inject while writing program 5A?
How long will Student 14 likely spend in unit test?
How do your estimates compare with the actual results and what could have caused the differences?
What would be the likely consequences of inaccurate or incomplete data?