## Slide 1
TSP Executive Strategy Seminar
Exercise 3: Schedule Management

## Slide 3: Exercise Objective
The objective of this exercise is to illustrate how TSP data can be used to manage project schedules.
This exercise describes how to
  determine project status
  estimate when the project will finish
  identify the reasons for potential schedule problems

## Slide 4: Exercise Overview
This exercise uses data on one TSP team.
Lisa’s 5-member team has completed 13 weeks of its 36 week schedule.
The developers have completed the product’s high-level design and are about to start on detailed design.

## Slide 5: The Data
The exercise uses data from the TSP WEEK form.
The team reports these data every week.

## Slide 6: The WEEK Form
Weeks worked
Data used in
the exercise
Plan and actual hours worked
Plan and actual EV
Plan and actual hours for completed tasks

## Slide 7: Project Assessment Steps
The three principal steps in assessing project status are as follows.
  Determine the rate at which the team has completed its work so far.
  Assuming that the team continues at this rate, estimate when the project will finish.
  Determine the consequences of
    adding a developer to the team
    helping the team increase its weekly task hours
This exercise illustrates the use of TSP data to identify and address schedule problems.

## Slide 8: The Exercise
Read the exercise instructions.
Form into groups of two to four to answer the questions.
When done, we will discuss the questions as a group.
20 minutes

## Slide 9: Exercise Discussion -1
Schedule questions
  Where does the project stand?
  Why is it ahead or behind schedule?
Plan performance questions
  How much schedule would adding one developer save?
  How much schedule would a 5-hour increase in weekly team task hours save?

## Slide 10: Exercise Discussion -2
Other questions
How accurate is the plan?
What would it cost (or save) the business to
  add one developer
  increase team task hours by 5 hours per week
What management actions would increase (or decrease) the team’s weekly task hours?
What events might cause the weeks-to-go estimates to be in error?