## Slide 1
TSP Executive Strategy Seminar
Exercise 4: Quality Management

## Slide 3: Exercise Objective
The objective of this exercise is to show how to use TSP data to manage a software-intensive business.
This exercise shows how
  quality performance impacts project schedules
  managers can use TSP data to improve project results
  executives can use TSP data to make business decisions

## Slide 4: Exercise Overview
The instructors will
  describe a business situation
  present a project recommendation
  ask for your approval
You should ask for any information you need and then make your decision.
60 minutes

## Slide 5: Exercise Roles and Procedure
Instructor 1: Chris is project manager of a major software product and will chair the session.
Instructor 2: Pat is the WebInc quality assurance manager who has assessed this project and reported to the CEO.
Attendees: You are a management committee that the CEO
has asked to review this project and make a recommendation.

## Slide 6: Exercise Instructions -1
Chris will present the proposal and invite questions.
You can ask for any information you need to make a sound business decision.
Chris and Pat will answer to the best of their ability.

## Slide 7: Exercise Instructions -2
Chris and Pat will not volunteer information other than what they initially present.
If you do not ask for additional information, they will not furnish it.
When you have asked all of your questions, make your decision.
Do not state your decision out loud.

## Slide 8: Exercise Instructions -3
Write your name and decision on the form we will provide.
Be specific. Give the week number when you feel the project will be ready to ship.
Include on the form the main one or two reasons for selecting this date.
We will discuss your answers as well as other ways you could have used the data to make your decision.

## Slide 9: The Situation
WebWiz, a new WWW product, is scheduled to ship
in 20 weeks.
The situation
  WebInc is a new company that has not yet made a profit.
  The CEO has promised the investors that it will make a profit this year.
  If it does not, the investors will not provide further funding.
  If the product ships in 30 weeks, finance believes that WebInc can meet its profit goals.

## Slide 10: Project Proposal
Chris: Project Manager for WebWiz
Pat: Quality Assurance for WebInc
WebWiz
A WebInc Product

## Slide 11: Product Business Information
WebWiz, our new Web product, has been widely
praised by software experts.
We have scheduled a demonstration at a trade show in 24
weeks.
Marketing would like to launch a major ad campaign this week.
Our CEO will not agree to the campaign unless this committee assures him that the product will ship within 24 weeks.

## Slide 12: Product Information
WebWiz is designed for use on the Windows and Linux platforms.
WebWiz release 1 has three essential but independent components.
  The FILENET component provides system control. It has completed testing and is ready for shipment.
  The IOMGR provides the user interface. Lisa, the team leader, estimates it will be completed in 19.5 weeks.
  The APSNET component provides user application functions. Jeff, the team leader, estimates it will be done in 18.6 weeks.

## Slide 13: The Issue
Both team leaders believe that their teams will finish within the 24 weeks available.
Quality assurance has examined the project’s data and told the CEO that the 24-week date is very risky.

## Slide 14: Product Manager Recommendation
The product is on schedule and will finish in 20 weeks.
The team leaders are confident that their work will be completed in that time.
We should proceed with plans for the demonstration in 24 weeks.
In light of the Quality Assurance position, the CEO has asked that this committee recommend what to do.

## Slide 15: Q & A Period
We will now answer any questions regarding the WebWiz project.
Pat from QA has analyzed WebInc’s software work and will help me provide additional project details.

## Slide 16: Exercise Instructions Review
When you have the information you need, write your name and decision on the form provided.
  Do not state your decision aloud.
  Give the specific date when you feel the project will be ready to ship.
  Include on the form your one or two principal reasons for selecting this date.
  Also include your recommendation for what the CEO should do.
  Any questions?
5 minutes

## Slide 17: Exercise Conclusions
There are a wealth of potentially valuable data on
software projects.
These data can help you to make sound business
decisions.
You need these data to effectively manage a software-
intensive business.
If you do not ask for these data, you will not get them.
Following are some example data that a TSP team could provide.