Copyright 2018 Carnegie Mellon University.  All rights reserved.

This material is based upon work funded and supported by the Department of Defense under Contract No. FA8721-05-C-0003 with Carnegie Mellon University for the operation of the Software Engineering Institute, a federally funded research and development center.

Any opinions, findings and conclusions or recommendations expressed in this material are those of the author(s) and do not necessarily reflect the views of the United States Department of Defense.

NO WARRANTY. THIS MATERIAL IS FURNISHED ON AN “AS-IS” BASIS WITH NO WARRANTIES OF ANY KIND, EITHER EXPRESSED OR IMPLIED, INCLUDING, BUT NOT LIMITED TO, WARRANTY OF FITNESS FOR PURPOSE OR MERCHANTABILITY, ANY WARRANTY WITH RESPECT TO FREEDOM FROM PATENT, TRADEMARK, OR COPYRIGHT INFRINGEMENT, OR THIRD PARTY INTELLECTUAL PROPERTY RIGHTS.

[Distribution Statement A] This material has been approved for public release and unlimited distribution.  The United States Government has Unlimited Rights in this material as defined by DFARS 252.227-7013.

The text and illustrations in this material are licensed by Carnegie Mellon University under a Creative Commons Attribution 4.0 International License.

The Creative Commons license does not extend to logos, trade marks, or service marks of Carnegie Mellon University.

Workshop Handouts - Meetings 5, 5A, 5B, and 5C

| Contents |  |
| --- | --- |
| Page | Element |
| 2 | Meeting Report - Launch Meeting 5 (partially completed) |
| 3 | TSP Launch Meeting 5 - Script LAU5 |
| 4 | Meeting Report - Launch Meeting 5A (partially completed) |
| 5 | Meeting Report - Launch Meeting 5B (partially completed) |
| 6 | TSPm Launch Meeting 5B - Script LAU5B |
| 7 | Meeting Report - Launch Meeting 5C (partially completed) |
| 8 | TSPm Launch Meeting 5C - Script LAU5C |
| 9 | TSP Quality Summary - Form SUMQ (blank) |
| 11 | TSP Quality Summary Instructions - SUMQ |
| 12 | TSP Quality Guidelines |
| 14 | TSP Issue and Risk Tracking Log - Form ITL (blank) |
| 15 | TSP Process Improvement Proposal - Form PIP (blank) |

Note: for meeting 5, the TSP and TSPm launch and relaunch processes are the same.

Meeting Report - Launch Meeting 5

| Name |  |  |  |  |  |  |  |  | Date |  |  |
| --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- |
| Chairperson |  | TSP Coach |  |  |  | Location |  |  |  |  |  |
| Meeting Date |  |  |  |  |  | Time From: |  |  |  | To: |  |
| Subject/Purpose |  |  |  | TSP Launch Meeting 5: To produce the quality plan and schedule |  |  |  |  |  |  |  |
| Attendees |  |  |  |  |  |  |  |  |  |  |  |
| Name |  |  |  |  |  |  |  |  |  | Role |  |
| Agenda |  |  |  |  |  |  |  |  |  |  |  |
| Times (min.) |  |  |  |  | Topics |  |  |  |  | Discussion Leader |  |
| Plan | Start |  | Stop |  |  |  |  |  |  |  |  |
| 10 |  |  |  |  | Agenda and meeting process |  |  |  |  | TSP Coach |  |
| 15 |  |  |  |  | Review quality goals |  |  |  |  | Quality Manager |  |
| 10 |  |  |  |  | Estimate defects injected |  |  |  |  | Quality Manager |  |
| 10 |  |  |  |  | ### Estimate defects removed |  |  |  |  | Quality Manager |  |
| 10 |  |  |  |  | Produce the quality plan |  |  |  |  | Quality Manager |  |
| 5 |  |  |  |  | Meeting wrap-up and report |  |  |  |  | TSP Coach |  |
| Decisions, Actions, and Key Information |  |  |  |  |  |  |  |  |  |  |  |
| What |  |  |  |  |  |  |  | Who |  |  | When |
| Quality plan (form SUMQ) |  |  |  |  |  |  |  |  |  |  |  |

(Use additional form copies if needed.)

| TSP Launch Meeting 5 - Script LAU5 |  |
| --- | --- |
| Purpose | To guide the team in producing the quality plan |
| Entry Criteria | - All participants are present (TSP coach, team members, team leader). - Forms: ITL, MTG, PIP, SUMP, SUMQ, SUMS - Guidelines: Planning, Quality |
| General | Meeting 5 generally takes about 1 hour, depending on team size, project status, product complexity, and the team’s TSP experience. |

| Step | Activities | Description |
| --- | --- | --- |
| 1 | Meeting Roles | Select the meeting roles (specification ROLE). - The TSP coach leads the meeting (script MTG). - The timekeeper tracks time and keeps the meeting on schedule. - The recorder notes meeting decisions and actions and writes the meeting report (form MTG). |
| 2 | Meeting Overview | The TSP coach reviews the work to be done in this meeting and the products to be produced. |
| 3 | Quality Goals | The quality manager leads a review of the team's quality goals (form GOAL). - identifies quality data or uses Quality and Planning guidelines - establishes the quality guidelines for the quality plan |
| 4 | Estimate Defects Injected | Using the quality guidelines and historical data, the quality manager guides the team in estimating the defects to be injected by phase for each process identified in Meeting 3 (script LAU3). - The planned defects injected for phase P are estimated as the planned hours for phase P times the hourly defect injection rate for phase P. Defects injectedp = Time in phasep* Defect injection ratep - If phase injection rates are not available, the team makes a best estimate. |
| 5 | Estimate Defects Removed | - Using the quality guidelines and historical data, the quality manager guides the team in estimating the defects to be removed by phase for each process identified in Meeting 3 (script LAU3). - The number of defects removed in a phase is the phase defect-removal yield times defects present at the phase divided by 100. - Defects removedp = Defects present in phasep* Phase yieldp / 100 - Defects present in phase are the total defects injected by the end of the phase less the total removed before phase entry. - Defects present in phasep = Defects injected(1…p) - Defects removed(1..p-1) - If phase yields are not available, the team makes a best estimate. |
| 6 | Produce the Quality Plan | - The quality manager leads the team in calculating the remainder of the quality plan (form SUMQ), and in evaluating and adjusting the plan until the team’s quality goals and schedule are met. - evaluating the resulting defect densities and removal rates - making needed adjustments in phase times or yields if goals are not met - recalculating the quality parameters and checking again |
| 7 | Launch Meeting Documentation | The recorder completes form MTG. - lists the attendees and the time spent by agenda item - describes decisions made and by whom - documents pending actions: what, when, and by whom - verifies the meeting report with the meeting attendees and gives the completed form MTG to the planning manager |

| Exit Criteria | - Launch meeting 5 activities have been completed. - Overall quality plan has been documented (forms SUMP, SUMQ). - All issues have been recorded (form ITL). - All process improvement suggestions have been recorded (form PIP). - The meeting report has been completed (form MTG and attachments). - The planning manager has copies of all meeting products. |
| --- | --- |

Meeting Report – TSPm Launch Meeting 5A

| Name |  |  |  |  |  |  |  |  | Date |  |  |
| --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- |
| Chairperson |  | TSP Coach |  |  |  | Location |  |  |  |  |  |
| Meeting Date |  |  |  |  |  | Time From: |  |  |  | To: |  |
| Subject/Purpose |  |  |  | TSPm Launch Meeting 5A: The leadership team meets to review launch status |  |  |  |  |  |  |  |
| and resolve issues |  |  |  |  |  |  |  |  |  |  |  |
| Attendees |  |  |  |  |  |  |  |  |  |  |  |
| Name |  |  |  |  |  |  |  |  |  | Role |  |
| Agenda |  |  |  |  |  |  |  |  |  |  |  |
| ## Times (min.) |  |  |  |  | Topics |  |  |  |  | Discussion Leader |  |
| Plan | Start |  | Stop |  |  |  |  |  |  |  |  |
| 5 |  |  |  |  | Meeting roles and process |  |  |  |  | TSP Coach |  |
| 5 |  |  |  |  | ### Meeting agenda |  |  |  |  | Project Manager |  |
| 15 |  |  |  |  | Review launch status |  |  |  |  | Team Leaders |  |
| 20 |  |  |  |  | Review issues |  |  |  |  | Project Manager |  |
| 10 |  |  |  |  | Other items |  |  |  |  | Project Manager |  |
| 5 |  |  |  |  | Launch meeting documentation |  |  |  |  | Project Manager |  |
| Decisions, Actions, and Key Information |  |  |  |  |  |  |  |  |  |  |  |
| What |  |  |  |  |  |  |  | Who |  |  | When |

(Use additional form copies if needed.)

Meeting Report – TSPm Launch Meeting 5B

| Name |  |  |  |  |  |  |  |  | Date |  |  |
| --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- |
| Chairperson |  | TSP Coach |  |  |  | Location |  |  |  |  |  |
| Meeting Date |  |  |  |  |  | Time From: |  |  |  | To: |  |
| Subject/Purpose |  |  |  | TSPm Launch Meeting 5B: Each TSPm planning role manager team meets to |  |  |  |  |  |  |  |
| review and consolidate the team’s development plans |  |  |  |  |  |  |  |  |  |  |  |
| Attendees |  |  |  |  |  |  |  |  |  |  |  |
| Name |  |  |  |  |  |  |  |  |  | Role |  |
| Agenda |  |  |  |  |  |  |  |  |  |  |  |
| ## Times (min.) |  |  |  |  | Topics |  |  |  |  | Discussion Leader |  |
| Plan | Start |  | Stop |  |  |  |  |  |  |  |  |
| 5 |  |  |  |  | Meeting roles and process |  |  |  |  | TSP Coach |  |
| 5 |  |  |  |  | ### Meeting agenda |  |  |  |  | TSP Coach |  |
| 15 |  |  |  |  | Review and consolidate the team plans |  |  |  |  | Lead Role Manager |  |
| 20 |  |  |  |  | Identify internal team dependencies |  |  |  |  | Lead Role Manager |  |
| 10 |  |  |  |  | Identify external team dependencies |  |  |  |  | Lead Role Manager |  |
| 30 |  |  |  |  | Decide on the report to the leadership team |  |  |  |  | Lead Role Manager |  |
| 5 |  |  |  |  | Launch meeting documentation |  |  |  |  | Lead Role Manager |  |
| Decisions, Actions, and Key Information |  |  |  |  |  |  |  |  |  |  |  |
| What |  |  |  |  |  |  |  | Who |  |  | When |

(Use additional form copies if needed.)

| TSPm Launch Meeting 5B - Script LAU5B |  |
| --- | --- |
| Purpose | - The planning manager team meets to - conduct the initial planning manager team meeting - produce a consolidated team plan and dependency issue list |
| Entry Criteria | - The planning managers have been selected for each team. - The leadership team has named the leader for the planning manager team. - For distributed teams, remote planning managers participate via telephone or videoconference. - A TSP coach is available to guide the planning manager team meeting. - Specifications PLAN and ROLE - Forms: MTG, ITL |
| General | - Meeting 5B follows launch meeting 5, with the specific time depending on the availability of all team members and a TSP coach. - Meeting 5B takes from 1 to 2 hours. |

| Step | Activities | Description |
| --- | --- | --- |
| 1 | Meeting Role Assignments | - Select the meeting roles (specification ROLE). - The TSP coach leads the meeting (script MTG). - The timekeeper tracks time and keeps the meeting on schedule. - The recorder notes meeting decisions and actions and writes the meeting report (form MTG). |
| 2 | Meeting Overview | - The TSP coach reviews the purpose of the meeting and the results to be produced. |
| 3 | Consolidate the Team Plan | - The lead planning manager leads the team in - reviewing the plans for each sub-team - deciding which plans should be consolidated into higher level plans - assigning responsibility for producing these consolidations |
| 4 | Identifying Internal Team Dependencies | - The lead planning manager leads the team in - identifying the dependencies each sub-team has on other sub-teams - determining when each item is required and when it is to be available - assigning a person on each team to track that dependency - listing the dependencies, dates, and responsibilities on the ITL |
| 5 | Identifying External Team Dependencies | - The lead planning manager leads the team in - identifying the dependencies each sub-team has on external groups - determining when each item is required and when it is to be available - assigning a person on the sub-team to track that dependency - listing the dependencies, dates, and responsibilities on ITL forms |
| 6 | Reporting | - The lead planning manager leads the team in - deciding what items should be reported to the leadership team - preparing the report - deciding how and when to present the report |
| 7 | Launch Meeting Documentation | - The recorder gives the completed form MTG to the lead planning manager. - lists the attendees and the time spent by agenda item - describes decisions made and by whom - documents pending actions: what, when, and by whom - verifies the meeting report with the meeting attendees. |

| # Exit Criteria | - The consolidated plan prepared or assignments made to prepare it - Team dependencies identified and responsibilities defined - All issues and dependencies have been recorded (form ITL) - The meeting report has been completed (form MTG and attachments). |
| --- | --- |

Meeting Report – TSPm Launch Meeting 5C

| Name |  |  |  |  |  |  |  |  | Date |  |  |
| --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- |
| Chairperson |  | TSP Coach |  |  |  | Location |  |  |  |  |  |
| Meeting Date |  |  |  |  |  | Time From: |  |  |  | To: |  |
| Subject/Purpose |  |  |  | TSPm Launch Meeting 5C: Each TSPm quality role manager team meets to |  |  |  |  |  |  |  |
| review and consolidate the team’s quality plans. |  |  |  |  |  |  |  |  |  |  |  |
| Attendees |  |  |  |  |  |  |  |  |  |  |  |
| Name |  |  |  |  |  |  |  |  |  | Role |  |
| Agenda |  |  |  |  |  |  |  |  |  |  |  |
| ## Times (min.) |  |  |  |  | Topics |  |  |  |  | Discussion Leader |  |
| Plan | Start |  | Stop |  |  |  |  |  |  |  |  |
| 5 |  |  |  |  | Meeting roles and process |  |  |  |  | TSP Coach |  |
| 5 |  |  |  |  | ### Meeting agenda |  |  |  |  | TSP Coach |  |
| 15 |  |  |  |  | Review team goals and identify differences |  |  |  |  | Lead Role Manager |  |
| 20 |  |  |  |  | Define a common set of team quality goals |  |  |  |  | Lead Role Manager |  |
| 10 |  |  |  |  | Review and consolidate the team quality plans |  |  |  |  | Lead Role Manager |  |
| 30 |  |  |  |  | Decide on the report to the leadership team |  |  |  |  | Lead Role Manager |  |
| 5 |  |  |  |  | Launch meeting documentation |  |  |  |  | Lead Role Manager |  |
| Decisions, Actions, and Key Information |  |  |  |  |  |  |  |  |  |  |  |
| What |  |  |  |  |  |  |  | Who |  |  | When |

(Use additional form copies if needed.)

| TSPm Launch Meeting 5C - Script LAU5C |  |
| --- | --- |
| Purpose | - The quality manager team meets to - conduct the initial quality manager team meeting - identify quality issues and produce a consolidated quality plan |
| Entry Criteria | - The quality managers have been selected for each team. - The leadership team has named the leader for the quality manager team. - For distributed teams, remote quality managers participate via telephone or videoconference. - A TSP coach is available to guide the quality manager team meeting. - Specifications QUAL and ROLE - Forms: MTG, ITL |
| General | - Meeting 5C follows launch meeting 5, with the specific time depending on the availability of all team members and the TSP coach. - Meeting 5C takes from 1 to 2 hours. |

| Step | Activities | Description |
| --- | --- | --- |
| 1 | Meeting Role Assignments | - Select the meeting roles (specification ROLE). - The TSP coach leads the meeting (script MTG). - The timekeeper tracks time and keeps the meeting on schedule. - The recorder notes meeting decisions and actions and writes the meeting report (form MTG). |
| 2 | Meeting Overview | - The TSP coach reviews the purpose of the meeting and the results to be produced. |
| 3 | Review Team Quality Plans | - The lead quality manager leads the team in - reviewing the quality plans for each sub-team - identifying areas where the plans do not meet the team goals - deciding where changes are required and the changes to recommend - assigning responsibility for getting the changes made - recording the item in the ITL as an issue to be tracked |
| 4 | Consolidate the Team Quality Plan | - The lead quality manager leads the team in - deciding which plans should be consolidated into higher level quality plans - assigning responsibility for making these consolidations |
| 5 | Other Items | - The lead quality manager leads the team in - identifying any other issues that need attention across the teams - deciding how to handle these issues - assigning responsibilities for handling and tracking these issues - recording each issue in the ITL |
| 6 | Reporting | - The lead quality manager leads the team in - deciding what items should be reported to the leadership team - preparing the report - deciding how and when to present the report |
| 7 | Launch Meeting Documentation | - The recorder gives the completed form MTG to the lead quality manager. - lists the attendees and the time spent by agenda item - describes decisions made and by whom - documents pending actions: what, when, and by whom - verifies the meeting report with the meeting attendees. |

| # Exit Criteria | - Consolidated quality plan prepared or assignments made to prepare it. - Quality issues identified and responsibilities defined for resolving. - All quality issues have been recorded (form ITL). - The meeting report has been completed (form MTG and attachments). |
| --- | --- |

TSP Quality Summary - Form SUMQ

| Name |  | Date |  |
| --- | --- | --- | --- |
| Project |  | Launch/Phase |  |
| Part/Assembly |  | Assembly Level |  |

| Percent Defect Free | Plan |  | Actual |
| --- | --- | --- | --- |
| In compile |  |  |  |
| In unit test |  |  |  |
| In integration test |  |  |  |
| In system test |  |  |  |
| In acceptance test |  |  |  |
| In one year of use |  |  |  |
| In product life |  |  |  |
| Defect/Page |  |  |  |
| Requirements inspection |  |  |  |
| HLD review |  |  |  |
| HLD inspection |  |  |  |
| Defects/KLOC |  |  |  |
| DLD review |  |  |  |
| DLD inspection |  |  |  |
| Code review |  |  |  |
| Compile |  |  |  |
| Code inspection |  |  |  |
| Unit test |  |  |  |
| Build and integration |  |  |  |
| System test |  |  |  |
| Total development |  |  |  |
| Acceptance test |  |  |  |
| Product life |  |  |  |
| Total |  |  |  |
| Defect Ratios |  |  |  |
| Code review/Compile |  |  |  |
| DLD review/Unit test |  |  |  |
| Development Time Ratios (%) |  |  |  |
| Requirements inspection/Req. time |  |  |  |
| HLD inspection/HLD time |  |  |  |
| DLD/code |  |  |  |
| DLD review/design |  |  |  |
| Code review/code |  |  |  |
| A/FR |  |  |  |
| Personal Review Rates |  |  |  |
| DLD lines/hour |  |  |  |
| Code LOC/hour |  |  |  |
| Inspection Rates |  |  |  |
| Requirement pages/hour |  |  |  |
| HLD pages/hour |  |  |  |
| DLD lines/hour |  |  |  |
| Code LOC/hour |  |  |  |

(continued on next page)

TSP Quality Summary - Form SUMQ (continued)

| Part/Assembly |  | Date |  |
| --- | --- | --- | --- |

| Defect Injection Rates | Plan |  | Actual |
| --- | --- | --- | --- |
| Requirements |  |  |  |
| HLD |  |  |  |
| DLD |  |  |  |
| Coding |  |  |  |
| Compile |  |  |  |
| Unit test |  |  |  |
| Build and integration |  |  |  |
| System test |  |  |  |
| Defect Removal Rates | Plan |  | Actual |
| Requirements |  |  |  |
| System test planning |  |  |  |
| Requirements inspection |  |  |  |
| HLD |  |  |  |
| Integration test planning |  |  |  |
| HLD inspection |  |  |  |
| DLD review |  |  |  |
| Test development |  |  |  |
| DLD inspection |  |  |  |
| Code |  |  |  |
| Code review |  |  |  |
| Compile |  |  |  |
| Code inspection |  |  |  |
| Unit test |  |  |  |
| Build and integration |  |  |  |
| System test |  |  |  |
| Phase Yields | Plan |  | Actual |
| Requirements inspection |  |  |  |
| HLD inspection |  |  |  |
| DLD review |  |  |  |
| DLD inspection |  |  |  |
| Code review |  |  |  |
| Compile |  |  |  |
| Code inspection |  |  |  |
| Unit test |  |  |  |
| Build and integration |  |  |  |
| System test |  |  |  |
| Process Yields | Plan |  | Actual |
| % before compile |  |  |  |
| % before unit test |  |  |  |
| % before build and integration |  |  |  |
| % before system test |  |  |  |
| % before system delivery |  |  |  |

TSP Quality Summary Instructions – Form SUMQ

| Purpose | - This form holds plan and actual quality data for parts or assemblies. - An assembly could be a system with multiple products, a product with multiple components, or a component with multiple modules. - A part could be a module, component, or product. - Note: the lowest-level parts or modules typically have no system-level data (i.e., requirements, high-level design, or system test). |
| --- | --- |
| General | - Where possible, establish goals based on your own historical data. - Where data are not available, use the QUAL standard for guidance. - In planning, follow script LAU5 to make the quality plan. - This form is used only when a tool with equivalent functionality, features, or purpose is not available. |
| Header | - Enter your name, project name, part or assembly name, launch phase, and date. - Assembly level specifies the level of this part: module, component, product, sub-system, or system. |
| Percent Defect Free (PDF) | - Set the percent defect free (PDF) plan values in the project launch. - At phase completion, enter the actual PDF values. - PDF does not apply to modules or lowest-level parts. - For program assemblies, compute PDF from form SUMDR. |
| Defects/page and Defects/KLOC | - Set the defect/page and defect/KLOC plan values in the launch. - After development, calculate the actual values. For modules, calculate directly; for assemblies, calculate from the forms SUMS and SUMDR. |
| Defect Ratios | - From the defects/KLOC values, calculate the defect ratios. - When compile or unit test defects are 0, enter "inf." |
| %Development Time Ratios | - Calculate the planned and actual ratios from form SUMP. - During development, monitor these planned and actual ratios to ensure the work meets the team quality goals. |
| A/FR | - For A/FR, use detailed design and code review and inspection times divided by compile and unit test times. - Use the sum of personal review and team inspection times. |
| Review and Inspection Rates | - From forms SUMT and SUMS, calculate the indicated planned or actual review and inspection rates. - During development, monitor these planned and actual rates to ensure that the work meets the team quality goals. |
| Defect Injection and Removal Rates | - Based on the quality plan, establish standard team rates. - As you gather actual data, compute the actual defect injection and removal rates for each phase. - For modules, compute the values directly. - For larger program assemblies, compute the values from the forms SUMT, SUMDI, and SUMDR. |
| Yield | - In planning, use historical data to estimate the yield values needed for each defect-removal phase. - After each phase, calculate the estimated yield values. - Update these values as development progresses. - For modules, compute the yield values directly. - For larger program assemblies, compute the yield values from SUMDI and SUMDR. |

TSP Quality Guidelines

| General | - If your team does not have historical data, use these guidelines as standard planning factors. - Use these initial criteria until you have historical TSP data and can develop your own. - In all cases, use your judgement. If some guideline does not fit your case, use your best estimate instead. |  |  |
| --- | --- | --- | --- |
| Measure |  | Goal | Comments |
| Percent Defect Free (PDF) |  |  |  |
| Compile |  | > 10% |  |
| Unit Test |  | > 50% |  |
| Integration Test |  | > 70% |  |
| System Test |  | > 90% |  |
| Defects/KLOC: |  |  |  |
| Total defects injected |  | 75 - 150 | If not PSP-trained, use 100 to 200. |
| Compile |  | < 10 | All defects |
| Unit Test |  | < 5 | All major defects (in source LOC) |
| Integration Test |  | < 0.5 | All major defects (in source LOC) |
| System Test |  | < 0.2 | All major defects (in source LOC) |
| Defect Ratios |  |  |  |
| Detailed design review defects /unit test defects |  | > 2.0 | All major defects (in source LOC) |
| Code review defects/compile defects |  | > 2.0 | All major defects (in source LOC) |
| Development Time Ratios |  |  |  |
| Requirements inspection/requirements time |  | > 0.25 | Elicitation in requirements time |
| High-level design inspection/high-level design time |  | > 0.5 | Design work only, not studies |
| Detailed design/coding time |  | > 1.00 |  |
| Detailed design review/detailed design time |  | > 0.5 |  |
| Code review/code time |  | > 0.5 |  |
| Review and Inspection Rates |  |  |  |
| Requirements pages/hour |  | < 2 | Single-spaced text pages |
| High-level design pages/hour |  | < 5 | Formatted design logic |
| Detailed design text lines/hour |  | < 100 | Pseudocode ~ equal to 3 LOC |
| Code LOC/hour |  | < 200 | Logical LOC |
| Defect Injection and Removal Rates |  |  |  |
| Requirements defects injected/hour |  | 0.25 | Only major defects |
| Requirements inspection defects removed/hour |  | 0.5 | Only major defects |
| High-level design defects injected/hour |  | 0.25 | Only major defects |
| High-level design inspection defects removed/hour |  | 0.5 | Only major defects |
| Detailed design defects injected/hour |  | 0.75 | Only design defects |
| Detailed design review defects removed/hour |  | 1.5 | Only design defects |
| Detailed design inspection defects removed/hour |  | 0.5 | Only design defects |
| Code defects injected/hour |  | 2.0 | All defects |
| Code review defects removed/hour |  | 4.0 | All defects in source LOC |
| Compile defects injected/hour |  | 0.3 | Any defects |
| Code inspection defects removed/hour |  | 1.0 | All defects in source LOC |
| Unit test defects injected/hour |  | 0.067 | Any defects |

(continued on next page)

TSP Quality Guidelines (continued)

| Measure | Goal | Comments |
| --- | --- | --- |
| Phase Yields |  |  |
| Team requirements inspections | ~ 70% | Not counting editorial comments |
| Design reviews and inspections | ~ 70% | Using state analysis, trace tables |
| Code reviews and inspections | ~ 70% | Using personal checklists |
| Compiling | ~ 50% | 90+ % of syntax defects |
| Unit test at 5 or less defects/KLOC | ~ 90% | If high defects/KLOC use 50-75% |
| Integration and system test at < 1.0 defects/KLOC | ~ 80% | If high defects/KLOC use 30-65% |
| Before compile | >75% | Assuming sound design methods |
| Before unit test | > 85% | Assuming logic checks in reviews |
| Before integration test | > 97.5% | For small products, 1 defect max. |
| Before system test | > 99% | For small products, 1 defect max. |

TSP Issue and Risk Tracking Log - Form ITL

| Name |  | Date |  |
| --- | --- | --- | --- |
| Project |  | Launch/Phase |  |

| No. | Date |  | Personal/Team | Risk/Issue | Impact | Likelihood | Source | Owner |
| --- | --- | --- | --- | --- | --- | --- | --- | --- |
| Description |  |  |  |  |  |  |  | Follow-up Date |
|  |  |  |  |  |  |  |  | Resolved Date |
| No. | Date |  | Personal/Team | Risk/Issue | Impact | Likelihood | Source | Owner |
| Description |  |  |  |  |  |  |  | Follow-up Date |
|  |  |  |  |  |  |  |  | Resolved Date |
| No. | Date |  | Personal/Team | Risk/Issue | Impact | Likelihood | Source | Owner |
| Description |  |  |  |  |  |  |  | Follow-up Date |
|  |  |  |  |  |  |  |  | Resolved Date |
| No. | Date |  | Personal/Team | Risk/Issue | Impact | Likelihood | Source | Owner |
| Description |  |  |  |  |  |  |  | Follow-up Date |
|  |  |  |  |  |  |  |  | Resolved Date |
| No. | Date |  | Personal/Team | Risk/Issue | Impact | Likelihood | Source | Owner |
| Description |  |  |  |  |  |  |  | Follow-up Date |
|  |  |  |  |  |  |  |  | Resolved Date |
| No. | Date |  | Personal/Team | Risk/Issue | Impact | Likelihood | Source | Owner |
| Description |  |  |  |  |  |  |  | Follow-up Date |
|  |  |  |  |  |  |  |  | Resolved Date |
| No. | Date |  | Personal/Team | Risk/Issue | Impact | Likelihood | Source | Owner |
| Description |  |  |  |  |  |  |  | Follow-up Date |
|  |  |  |  |  |  |  |  | Resolved Date |

TSP Process Improvement Proposal - Form PIP

| Name |  |  | Date |  |  |
| --- | --- | --- | --- | --- | --- |
| E-mail |  | Organization |  |  |  |
| Project |  | Launch/Phase |  |  |  |

| PIP Number |  |  | Priority |  |  |  |  |
| --- | --- | --- | --- | --- | --- | --- | --- |
| PIP Title |  |  |  |  |  |  |  |
| Improvement Description |  |  |  |  |  |  |  |
| Briefly describe the improvement you suggest. |  |  |  |  |  |  |  |
| Process Elements Impacted |  |  |  |  |  |  |  |
| If you know them, list the process elements that must be added, changed, or deleted. |  |  |  |  |  |  |  |
| Improvement Benefits (check one) |  |  |  |  |  |  |  |
| Improved Quality _______ Reduced Cycle Time ________ Reduced Risk ________ |  |  |  |  |  |  |  |
| Describe the likely benefits of the suggested change. |  |  |  |  |  |  |  |
| When completed and reviewed, submit to the Process Manager and keep a copy. |  |  |  |  |  |  |  |
| Do not write below this line. |  |  |  |  |  |  |  |
| PIP Control No. |  |  |  | Accepted |  |  |  |
| Received |  |  |  | Returned |  |  |  |
| Evaluated |  |  |  | Deferred |  |  |  |
| Effort Involved |  |  |  | Date Done |  |  |  |
| Author Notified |  |  |  |  |  |  |  |
| Reasons |  |  |  |  |  |  |  |