Copyright 2018 Carnegie Mellon University.  All rights reserved.

This material is based upon work funded and supported by the Department of Defense under Contract No. FA8721-05-C-0003 with Carnegie Mellon University for the operation of the Software Engineering Institute, a federally funded research and development center.

Any opinions, findings and conclusions or recommendations expressed in this material are those of the author(s) and do not necessarily reflect the views of the United States Department of Defense.

NO WARRANTY. THIS MATERIAL IS FURNISHED ON AN “AS-IS” BASIS WITH NO WARRANTIES OF ANY KIND, EITHER EXPRESSED OR IMPLIED, INCLUDING, BUT NOT LIMITED TO, WARRANTY OF FITNESS FOR PURPOSE OR MERCHANTABILITY, ANY WARRANTY WITH RESPECT TO FREEDOM FROM PATENT, TRADEMARK, OR COPYRIGHT INFRINGEMENT, OR THIRD PARTY INTELLECTUAL PROPERTY RIGHTS.

[Distribution Statement A] This material has been approved for public release and unlimited distribution.  The United States Government has Unlimited Rights in this material as defined by DFARS 252.227-7013.

The text and illustrations in this material are licensed by Carnegie Mellon University under a Creative Commons Attribution 4.0 International License.

The Creative Commons license does not extend to logos, trade marks, or service marks of Carnegie Mellon University.

TSP+ Forms

All the TSP, TSPm, and TSP+ forms are given here in the alphabetical order of their abbreviations. Each form has an instruction that is on the immediate following page. The forms titled with TSP are core TSP forms which may have additional changes made for TSP+.  The forms titled TSP+ are add-on forms used to address other aspects of a mature software development organization.

| Form Abbreviation | Form and Instructions Name | Page Reference |
| --- | --- | --- |
| CCR | TSP+ Configuration Change Request | 3 |
| CHECKTMDR | TSP Checkpoint Team Member Data Review | 6 |
| CIBPS | TSP+ Project Configuration Item Baseline, Plan, and Status | 11 |
| CIR | TSP+ Configuration Identification Release | 13 |
| DAR | TSP+ Decision Analysis and Resolution | 15 |
| DEFECT | TSP Defect Reporting Form | 18 |
| GOAL | TSP Team Goals | 20 |
| INS | TSP Inspection Report | 22 |
| INV | TSP Process Inventory | 24 |
| ITL | TSP Issue/Risk Tracking Log | 26 |
| LOGCCR | TSP+ Configuration Change Request Log | 28 |
| LOGCI | TSP+ Configuration Item Log | 30 |
| LOGD | TSP Defect Recording Log | 32 |
| LOGPIP | TSP+ Process Improvement Proposal Log | 34 |
| LOGSPDR | TSP+ Standard Process Deviation Request Log | 36 |
| LOGT | TSP Time Recording Log | 38 |
| LOGTRNM | TSP+ Team Member Training Log | 40 |
| LOGTRNR | TSP+ Training Request Log | 42 |
| MTG | TSP Meeting Report Form | 44 |
| PIP | TSP Process Improvement Proposal | 46 |
| ROLE | TSP Team Roles | 48 |
| ROLEMX | TSP Role Assignment Matrix | 50 |
| RSIM | TSP+ Relevant Stakeholder Involvement Matrix | 52 |
| SCHED | TSP Schedule Planning Template | 64 |
| SPDE | TSP+ Standard Process Deviation Evaluation | 66 |
| SPDR | TSP+ Standard Process Deviation Request | 68 |
| SRAM | TSP+ Stakeholder Role Assignment Matrix | 70 |
| STRAT | TSP Strategic Planning Form | 72 |
| SUMDI | TSP Defects Injected Summary | 74 |
| SUMDR | TSP Defects Removed Summary | 76 |
| SUMP | TSP Plan Summary Form | 78 |
| SUMPD | TSP+ Standard Process Deviation Summary | 81 |
| SUMQ | TSP Quality Summary Form | 83 |
| SUMS | TSP Program Size Summary | 86 |
| SUMT | TSP Development Time Summary Form | 88 |
| SUMTASK | TSP Task Plan Summary | 90 |
| SUMTRNS | TSP+ Training Survey Summary | 92 |
| TASK | TSP Task Planning Template | 96 |
| TESTLOG | TSP Test Log | 98 |
| TRNM | TSP+ Training Matrix | 100 |
| TRNOJT | TSP+ On-the-Job Training | 102 |

(continued on next page)

TSP+ Forms (continued)

| Form Abbreviation | Form and Instructions Name | Page Reference |
| --- | --- | --- |
| TRNR | TSP+ Training Request | 104 |
| TRNSI | TSP+ Training Sign In Form | 106 |
| TRNSUR | TSP+ Training Survey | 108 |
| TRNWR | TSP+ Training Waiver Request | 111 |
| WEEK | TSP Weekly Status Report | 113 |

TSP+ Configuration Change Request Form - Form CCR

| Name |  |  | Date |  |
| --- | --- | --- | --- | --- |
| E-mail |  | Organization |  |  |
| Project |  | Launch/Phase |  |  |

| CI Number |  |  | Priority |  |  |  |
| --- | --- | --- | --- | --- | --- | --- |
| CCR Title |  |  |  |  |  |  |
| Change Information |  |  |  |  |  |  |
| Reason for Change |  |  |  |  |  |  |
| Change Impact |  |  |  |  |  |  |
| Change Description |  |  |  |  |  |  |
| (For source code, reference requirements and attach listing; for code changes, include defect number [if any] and listing of changed and unchanged program segment.) |  |  |  |  |  |  |
| When completed and reviewed, submit to the Support Manager or CMC and keep a copy. |  |  |  |  |  |  |
| Do not write below this line. |  |  |  |  |  |  |
| CCR Control # |  |  |  | Priority |  |  |
| Received |  |  |  | Approved |  |  |
| Evaluated |  |  |  | Returned |  |  |
| Product Owner |  |  |  | Disapproved |  |  |
| Effort Involved |  |  |  | Implemented |  |  |
| Comments/Information needed |  |  |  |  |  |  |
| Approvals |  |  |  |  |  |  |
| Product Owner |  |  |  |  | Date |  |
| Role Manager |  |  |  |  | Date |  |
| CCB |  |  |  |  | Date |  |

TSP+ Configuration Change Request Form Instructions - Form CCR

| Purpose | - To provide a way to record configuration change request - To maintain the integrity of work products currently under configuration control |
| --- | --- |
| General | Use the CCR form to - describe the required change(s) to an item under configuration control - record the rational for making the change(s) - assign responsibility for making change(s) - set priority for make change(s) For changes to the OSSP, and / or PSSP, the SPDR and LOGSPDR performs the role of, and substitutes, the configuration change request forms and associated process (forms CCR and LOGCCR). |
| Header | - Enter your name, date, e-mail and organization. - Provide the current project name and launch/phase the project is in. |
| CI Number | Provide the CI number for the configuration item being addressed by this change request. |
| Priority | - Indicate if CCR priority as urgent, important, or routine. - Explain the reason for this priority under “Change Impact.” |
| CCR Title | Create a title for the CCR. |
| Reason for Change | Describe why the change is required. |
| Change Impact | Where you can, reference other configuration items that will be impacted by this change and what is being done to address the impact. |
| Change Description | Describe the change being requested. Be as specific as possible. |
| When Completed | After you have completed the CCR, keep a copy and submit a copy to your team’s support manager or configuration management coordinator (CMC). |
| Support Manager or Configuration Management Coordinator (CMC) | - Review the CCR. - Evaluate the CCR for completeness. If incomplete return for more information - Enter CCR into LOGCCR and allocate unique CCR Control # - Enter date received - Identify Product Owner - Identify Role Manger. (For example: If the CCR impacts the code, then the implementation manager should evaluate CCR. etc.) - Obtain Product Owner and Role Manager’s approval of CCR. - Once approval of CCR is obtained from the Product Owner and the Role Manager, submit CCRs to the CCB for disposition. - Record CCB’s initial evaluation date. |
| Product Owner | - Review the CCR. - Evaluate the CCR for completeness. If incomplete return to support manager, or CMC, for more information. - Provide initial estimate of effort involved in implementing the change. - Record any relevant comments. - If you concur with this change, sign and date approval line. - Return CCR to Support Manager or CMC. |
| Role Manager | - Review the CCR for completeness in regards to your respective role. If incomplete return to support manager, or CMC, for more information. - Record any relevant comments. - If you concur with this change, sign and date approval line. - Return CCR to Support Manager or CMC. |

(continued on next page)

TSP+ Configuration Change Request Form Instructions - Form CCR (continued)

| Configuration Control Board (CCB) | - Review the CCR. - Evaluate the CCR and determine disposition (Approved, Returned, Disapproved, or Implemented). - Set priority as urgent, important, or routine. - Record any relevant comments. - If you concur with this change, sign and date approval line. - Track status of CCR to closure (Disapproved or Implemented). |
| --- | --- |

TSP Checkpoint Team Member Data Review Form – Form CHECKTMDR

| Team Member Name: |  |
| --- | --- |
| Team Name: |  |
| Role: |  |
| Date Checkpoint Review Conducted: |  |
| Coach Name: |  |

| Time Logging | Observations |
| --- | --- |
| Are times mostly recorded as the work is done? |  |
| Is interrupt time tracked appropriately? |  |
| Is comment field used to help guide and remind member of work? |  |
| Other observations and questions for team member |  |

| Defect Logging | Observations |
| --- | --- |
| Do all defects have required data? |  |
| Were defect injected before they were removed? |  |
| Does every defect have a fix time? |  |
| Do defects injected in compile and tests have fix numbers? |  |
| Are defects adequately described? |  |
| Are defect types consistent with descriptions? |  |
| Are defect types consistent with phase injected? |  |
| Are defect types assigned consistently? |  |
| Other observations and questions for team member |  |

| Defect Log and Time Log Consistency | Observations |
| --- | --- |
| Are defects being recorded for personal reviews and inspections? |  |
| Are defects being recorded for tests? |  |
| Are defects removed consistent with compile and test phase time and program size? |  |
| Is total compile defect fix times less than compile time? |  |
| Is total test defect fix times less than test time? |  |
| Are defect dates and phases consistent with the time log? |  |
| Other observations and questions for team member |  |

(continued on next page)

TSP Checkpoint Team Member Data Review Form – Form CHECKTMDR (continued)

| Tasks | Observations |
| --- | --- |
| Are all tasks < one week of effort in the next 2-4 weeks? |  |
| Are all tasks following a process as defined in the PSSP? |  |
| Is the number of open task hours < 5% of the plan? |  |
| Are all open tasks hours < one week of effort? |  |
| Other observations and questions for team member |  |

| Schedule | Observations |
| --- | --- |
| Is vacation or other significant things scheduled? |  |
| Is the next launch or re-launch scheduled? |  |
| Other observations and questions for team member |  |

| Quality | Observations |
| --- | --- |
| Are actual phase yields close to or exceeding plan yields? |  |
| Are actual defect injections lower than or close to planned inject rates? |  |
| Are review rates appropriate? |  |
| Do designs conform to team design standards? |  |
| Does code conform to team coding standards? |  |
| Is their evidence that checklists are being used in personal reviews? |  |
| Are review rates for inspections appropriate? |  |
| Are checklists being used in performing inspections? |  |
| Are Process Quality Indicator ratios close to expected? |  |
| Are the actual phase yields reasonable? |  |
| Are checklists up to date? |  |
| Are reviews and inspections being done properly? |  |
| Other observations and questions for team member |  |

(continued on next page)

TSP Checkpoint Team Member Data Review Form – Form CHECKTMDR (continued)

| Week | Observations |
| --- | --- |
| Is current plan date not > 1 week later than baseline date? |  |
| Is predicted date not > 2 weeks later than baseline date? |  |
| Is growth > 5% of plan? |  |
| Are schedule hours this cycle to date < 10% of plan? |  |
| Are to date hours for task completed > 10% of plan? |  |
| Are milestone dates being met? |  |
| Other observations and questions for team member |  |

| Summary Data | Observations |
| --- | --- |
| Are actual sizes being recorded? |  |
| Other observations and questions for team member |  |

| Project Overview | Observations |
| --- | --- |
| Baseline Plan End Date |  |
| Current Plan End Date |  |
| Predicted End Date |  |
| Earn Value Per Week (are most weeks ahead or behind baseline?) |  |
| Did the current plan change a lot from the baseline? |  |
| How many actual hours are ahead of / behind plan? |  |
| Defects removed by phase (are they tracking defects? How does actual defects removed by phase compare to plan?) |  |
| Other observations and questions for team member |  |

(continued on next page)

TSP Checkpoint Team Member Data Review Form – Form CHECKTMDR (continued)

| Role Data (Scripts and Forms) | Observations |
| --- | --- |
| Is the team member performing all the responsibilities outlined in the role specification? |  |
| Is the team member following all the scripts for which they are responsible? |  |
| Are all the forms for which the team member is responsible being completed and maintained correctly? |  |
| Other observations and questions for team member |  |

TSP Checkpoint Team Member Data Review Form Instructions – Form CHECKTMDR

| Purpose | To provide the TSP coach with a mechanism for systematically reviewing team member data and recording one-on-one interview discussions with team members |
| --- | --- |
| General | - The coach is responsible for ensuring that confidentiality is maintained. No individual statements by any individual team member are to be reported to anyone else. Only issues that are shared by multiple team members are to be reported. - In general, the analysis of team member data is very context sensitive. Thus, the review of team member data should generate many questions that only the team member themselves can answer. Only after the context of the data is understood can true conclusions be made about the data. - The questions provided in this form are designed to systematically walk the coach through the TSP data. It is not a complete list of questions. Other questions can and should be asked. - Note that this form is typically used as a template in a spreadsheet or database. |
| Header | - Enter team member’s name. - Enter name of the team the member’s data is associated with. - Enter the team member’s role assignment(s). - Enter date(s) checkpoint review was conducted. - Enter the name of the TSP Coach performing the checkpoint. |
| TSP Coach | - Review team member data and record answers to questions provided and observations made while analyzing the team member’s TSP data in the space provided. - When analysis is complete, meet with team member to discuss observations and answer questions discovered while analyzing the team member’s data. Questions about the team member’s data can best be answered by showing the team member the data in question directly in the TSP tool. - Record information provided by the team member during the interview process in the “Other observations and questions for team member” space provided. - After all data analysis and interviews are completed, consolidate finding in a Checkpoint Report (see TSP Checkpoint Report Guideline). - Answer any questions the team member might have about the data or processes being used. |

TSP+ Configuration Item Baseline, Plan, and Status Form - Form CIBPS

| Organization |  | Page Number |  |
| --- | --- | --- | --- |
| Project |  | Launch/Phase |  |

| Baseline CI Number | CI Title | Product Owner | Criteria for determining when to place new or modified item under configuration management | Expected Release Date | Actual Release Date | New CI Number |
| --- | --- | --- | --- | --- | --- | --- |

TSP+ Configuration Item Plan, Status, and Baseline Form Instructions - Form CIBPS

| Purpose | - To provide the team with a mechanism for establishing a configuration baseline, planning changes to existing configuration items and the creating of new configuration items, tracking the completing status of configuration item changes and creation |
| --- | --- |
| General | Use the CIBPS form to - establish the project’s baseline for a given Launch/Phase - establish criteria for determining when to place new or modified items under configuration management control - communicate configuration item status with team members and multiple levels of management Note that this form is typically used as a template in a spreadsheet or database. |
| Header | - Enter name of organization and page number. - Provide the current project name and launch/phase the project is in. |
| Baseline CI Number | - Enter the CI Number of the configuration item being used as the project’s baseline. - For new items to be placed under configuration during this project’s launch/phase, enter “New.” |
| CI Title | Enter the Configuration Item’s title. |
| Product Owner | Enter the name of the configuration item owner, as identified by the team for the given configuration item. |
| Criteria for Determining When to Place New or Modified Item Under Configuration Management | Record the established criteria for determining when to place the new or modified item under configuration management control |
| Expected Release Date | Enter the planned date for completing the identified modifications to an existing configuration or the completion of a new item to be placed under configuration management. |
| Actual Release Date | Record the configuration item’s released date as recorded on the LOGCI form. |
| New CI Number | Enter the configuration item’s control number, which contains the planned material, as it is recorded on the corresponding approved CIR from. |

TSP+ Configuration Identification Release Form - Form CIR

| Organization |  | Date |  |
| --- | --- | --- | --- |
| Project |  | Launch/Phase |  |

| CI Number |  |  |  |  |  |  |  |  |  |  |  |
| --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- |
| CI Title |  |  |  |  |  |  |  |  |  |  |  |
| Release Type |  |  | Initial |  | Revision |  | Version |  | Rescind the release |  |  |
| Requested Release or Rescinding Description: |  |  |  |  |  |  |  |  |  |  |  |
| If applicable, list CCR Control #s or SPDR Control #s implemented in this release. |  |  |  |  |  |  |  |  |  |  |  |
| When completed and reviewed, submit to the Support Manager or CMC and keep a copy. |  |  |  |  |  |  |  |  |  |  |  |
| Do not write below this line. |  |  |  |  |  |  |  |  |  |  |  |
| Approval / Disapproval Reasoning |  |  |  |  |  |  |  |  |  |  |  |
| Approvals |  |  |  |  |  |  |  |  |  |  |  |
| Product Owner |  |  |  |  |  |  |  |  |  | Date |  |
| Quality Manager |  |  |  |  |  |  |  |  |  | Date |  |
| Process Manager |  |  |  |  |  |  |  |  |  | Date |  |
| CCB |  |  |  |  |  |  |  |  |  | Date |  |

TSP+ Configuration Identification Release Form Instructions - Form CIR

| Purpose | To provide the team with a mechanism for final approval or rescinding of the release of any configuration item. |
| --- | --- |
| General | Use the CIR form to - obtain approval for the release of a configuration item - maintain historical lineage of a configuration item |
| Header | - Enter name of organization and date of CIR submittal. - Provide the current project name and launch/phase the project is in. |
| CI Number | Enter the CI Number assigned to the configuration item in LOGCI |
| CI Title | Enter the Configuration Item’s title. |
| Release Type | Select release type (Initial, Revision, Version, or Rescind the release) |
| Requested Release or Rescinding Description | - Provide description of why the configuration item is being released or rescinded. - If applicable list CCR Control #s or SPDR Control #s implemented in this release. |
| Approval/Disapproval Reasoning | Capture any relevant information regarding the approval or disapproval of the configuration item’s release or rescindment. |
| Product Owner | - Verify that configuration item has met the criteria for placement under configuration management as documented on the CIBPS form. - Record any relevant comments. - If you concur with the release of the configuration item, sign and date the approval line. |
| Quality Manager | - Review the CIR - verify that the configuration item is of high quality - verify that the configuration item was effectively reviewed and inspected according to the team’s plan. - Record any relevant comments. - If you concur with the release of the configuration item, sign and date the approval line. |
| Process Manager | - Review the CIR - verify that the configuration item was created using the team’s defined processes - verify that the configuration item complies with any applicable team specification(s). - Record any relevant comments. - If you concur with the release of the configuration item, sign and date the approval line. |
| CCB | - Review and evaluate the CIR and determine final disposition (Approved or Disapproved). - Record any relevant comments. - If you concur with the release of the configuration item, sign and date the approval line. |

TSP+ Decision Analysis and Resolution Form - Form DAR

| Decision Owner |  |  | Date |  |
| --- | --- | --- | --- | --- |
| E-mail |  | Organization |  |  |
| Project |  | Launch/Phase |  |  |

| Decision Title |  |  |  |  |  |  |
| --- | --- | --- | --- | --- | --- | --- |
| Decision Participants |  |  |  |  |  |  |
| Decision Stakeholders |  |  |  |  |  |  |
| Definition of Issue |  |  |  |  |  |  |
| Alternative Solutions |  |  |  |  |  |  |
| 1. |  |  |  |  | 3. |  |
| 2. |  |  |  |  | 4. |  |

| Evaluation Criteria | Factor | Method | Solution 1 |  | Solution 2 |  | Solution 3 |  | Solution 4 |  |
| --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- |
|  |  |  | Rank | Score | Rank | Score | Rank | Score | Rank | Score |
| Total Score |  |  | --- |  | --- |  | --- |  | --- |  |

| Final Solution |  |  |  |  |  |
| --- | --- | --- | --- | --- | --- |
| Solution Justification |  |  |  |  |  |
| Approvals |  |  |  |  |  |
| Decision Owner |  |  | Date |  |  |
| Process Manager |  |  | Date |  |  |

TSP+ Decision Analysis and Resolution Form Instructions - Form DAR

| Purpose | To provide a mechanism for documenting the formal evaluation and selection of a solution to a defined issue. |
| --- | --- |
| General | - Care should be taken to limit the use of the DAR process (script DAR) to key decisions, so as to not impede progress. - Note that this form is typically used as a template in a spreadsheet or database. |
| Header | - Enter the decision owner’s name, date, e-mail and organization. - Provide the current project name and launch/phase the project is in. |
| Decision Title | Create title for decision that needs to be made. |
| Decision Participants | List the names of all participants that will assist in evaluating the alternative solutions. |
| Decision Stakeholders | List the names of all stakeholders, which is anyone affected by the decision but who will not participate in the decision making process. |
| Definition of Issue | Provide a clear definition of the issue requiring a decision as to which solution is preferable. |
| Alternative Solutions | In the space provide list between 2 to 4 of the identified alternative solutions to the defined issue that have been selected for further evaluation. |
| Evaluation Criteria | - In the space provided list between 2 to 7 evaluation criteria to be used to evaluation the alternative solutions. - Typical evaluation criteria used to evaluate alternative solutions include, but are not limited to: cost, schedule, risk, performance, reliability, reusability, efficiency, maintainability, scalability, and portability. |
| Factor | - The factor is used to more accurately reflect the driving factors of the project or team. For each evaluation criteria, select a factor between 1 and 5. (The larger the factor, the more important that criteria is to the project or team. Some evaluation criteria may be considered equally important, in which case, the same factor is assigned to both criteria.) - Enter the factor for each corresponding evaluation criteria in the space provided. |
| Method | - Typical methods used to evaluate alternative solutions include, but are not limited to: cost study/model, simulation, prototypes, benchmarks, trade studies, extrapolation based on experience and open discussion, user comments, testing, data comparison, feature comparison, and analysis of solutions to similar problems. - Enter the selected method for each corresponding evaluation criteria in the space provided. |
| Rank | - For each alternative solution assign a unique ranking of 1 to 4 for each evaluation criteria, with 1 as the worst-ranked solution and 4 being the best-ranked solution. - Enter the ranking in the spaces provided. |
| Score | - Calculate the score for each solution by multiplying the factor and rank of each evaluation criteria and recoding the product in the space provided. - In the spaces provided enter the sum of the evaluation criteria scores for of each solution. |
| Final Solution | - Enter the solution with the highest total score. - In the event of a tie between multiple solutions, the solution with the best ranking for the most important evaluation criteria should be selected. |

(continued on next page)

TSP+ Decision Analysis and Resolution Form Instructions - Form DAR (continued)

| Solution Justification | Provide justification of selected solution based on the data collected in relation to the evaluation criteria and associated methods selected. |
| --- | --- |
| Decision Owner | - Follow all the steps defined in script DAR. - Once a solution has been selected and all corresponding data has been assembled, review decision with all relevant stakeholder for concurrence. - Once concurrence is obtained, sign and date form and provide DAR data package to process manager for review. |
| Process Manager | - Review all the DAR material provided for completeness. If incomplete return for more information. The data package should include all information needed to reproduce the results and derive at the same conclusion. - If data package is complete, sign and date form and place entire data package under formal configuration management. |

TSP Defect Report - Form DEFECT

| Problem Report |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- |
| Originator |  |  |  |  |  |  |  |  |  |  |  | Date |  |  |  |  |
| Product |  |  |  |  |  |  |  |  |  |  |  | Phase |  |  |  |  |
| Problem Record |  |  | Number |  |  |  | Severity |  |  |  |  |  |  | Category |  |  |
| Problem Description |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| Briefly describe the problem encountered and its impact. |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| Include or attach sufficient data to recreate the problem. Where you know a fix, describe it. |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| Total time spent on problem (hours) |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| Fix Report |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| Team Member |  |  |  |  |  |  |  |  |  |  | Date |  |  |  |  |  |
| Product |  |  |  |  |  |  |  |  |  |  | Component |  |  |  |  |  |
| Defect Number |  |  |  |  |  |  | Defect Type |  |  |  |  |  |  |  |  |  |
| Phase Injected |  |  |  |  |  |  | Phase Removed |  |  |  |  |  |  |  |  |  |
| Fix Size (LOC) |  |  |  |  |  |  | Team Member Fix Time |  |  |  |  |  |  |  |  |  |
| Fix Defect Number |  |  |  |  |  |  | Fix Category |  |  |  |  |  |  |  |  |  |
| Fix Description |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| Describe the changes made as completely as possible, including affected programs, dependencies, etc. |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| When fix completed and reviewed, submit this form to the change control board. |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| Do not write below this line. |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| Fix Control # |  |  |  |  |  |  |  | Date Verified |  |  |  |  |  |  |  |  |
| Date Distributed |  |  |  |  |  |  |  | Date Installed |  |  |  |  |  |  |  |  |
| Notification |  |  |  |  |  |  |  | Date Closed |  |  |  |  |  |  |  |  |
| Prerequisites |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |

TSP Defect Report Instructions - Form DEFECT

| Purpose | - Record program problem and fix data on this form. - Use the form for all defects reported during integration testing, system testing, acceptance testing, and customer installation and use. |
| --- | --- |
| General | This form is only used when a tool with equivalent functionality, features, or purpose is not available. |
| Problem Report | In completing the problem report, the problem originator enters - his/her name and the date - the name and/or number of the product component and/or module where the problem was encountered - the phase where the problem was found (system test, use, etc.) |
| Problem Record | - Number: enter a serial identification number for each problem. - Severity: the problem originator enters the severity. - C (critical): System operation is not possible. - S (serious): System operation is possible but limited. - U (usable): The problem can be bypassed - M (minor): The problem is not operationally significant. - Category: the team member making the fix enters the category. - V (defect): a valid software defect - D (duplicate): a previously reported defect - I (invalid): any other problem report - Invalid categories - user error: the user made an error in using the system. - non-software problem, e.g. hardware or other software - a product suggestion |
| Problem Description | - Describe the problem in as much detail as possible. - Provide system or application data for problem recreation. - If you know a fix or bypass, describe it. - Record the total time spent on the problem. |
| Fix Report | - In completing the fix report, the development team member enters - his/her name and the date - the product name and the component or module fixed - the defect number, type, phase injected, and phase removed - the total time diagnosing and fixing the problem and fix size - If it is a fix defect, the team member records the prior fix number. - The team member enters the fix category. - major: any change that will affect the program source - minor: any change that will not affect the program source |
| Fix Description | - Describe the defect and fix in sufficient detail to permit later analysis to determine problem cause and problem prevention. - Note any dependencies on fixes, features, or configuration. |
| Fix Control | Use the bottom section of the form for tracking and managing the fix process. |

TSP Team Goals - Form GOAL

| Name |  | Date |  |  |  |  |  |
| --- | --- | --- | --- | --- | --- | --- | --- |
| Project |  | Launch/Phase |  |  |  |  |  |
|  |  |  |  | Measures |  |  | Tracking |
| Goal |  |  |  | Goal |  | Actual | Responsibility |

TSP Team Goals Instructions - Form GOAL

| Purpose | Use this form to record the team's goals. |
| --- | --- |
| General | This form is used only when a tool with equivalent functionality, features, or purpose is not available. |
| Goal-setting Process | In establishing goals, follow these guidelines. - Start with management's and marketing’s or customer’s stated goals. - Identify implied goals. - Define the team goals required to meet stated and implied goals. |
| Implied Goals | Some goals seem too obvious to state. Examples include: - Produce a product that works reliably and consistently. - Provide a product that is safe, does not damage people or property, and is protected against anticipated failures. - Respond to customer requests with sufficient reports and information to keep them satisfied with the team's work. |
| Team Goals | In establishing goals, examine each stated and implied goal and ask what would have to happen for this result to be assured. - What must the team do to assure that this goal is met? - Define team goals that require that these actions be taken. |
| Example Team Goals | - Provide a highly usable and convenient system. - Deliver the product on time and at planned costs. - Produce a defect-free product. - Reduce development cycle time. - Keep management and the customer fully informed of project status. |
| Measures: Goal | Try to define one or more measurements for every goal. - Sometimes, the goal will be readily measurable. - Often, indirect or opinion measures will be needed. - For every goal, specify how to determine if it was met. |
| Example Measures | Possible measures for the above example goals include, - Establish user performance targets and run usability tests to measure the performance and reaction of typical users. - Measure cost and schedule performance against the plan. - Set percent defect free (PDF) targets and track through development, test, acceptance, and use. - Measure how often specific managers must ask about project status rather than being informed in advance. |
| Measures: Actual | At project completion or whenever the data are available, measure and enter actual performance against each goal. |
| Responsibility | - Name the team member or role manager responsible for tracking and reporting on each goal. - In the weekly meeting, report status against all goals as soon as performance measures are available. |

TSP Inspection Report - Form INS

| Name |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  | Date |  |  |  |  |  |  |  |  |  |  |
| --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- |
| Project |  |  |  |  |  |  |  |  |  |  | Team |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| Product |  |  |  |  |  |  |  |  |  |  | Phase |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| Moderator |  |  |  |  |  |  |  |  |  |  | Producer |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| Inspection Summary |  |  |  |  |  | Product Size |  |  |  |  |  |  |  |  | Size Measure |  |  |  |  |  |  |  |  |  |  |  |  |
| Total Defects for A |  |  |  |  |  | Total Defects for B |  |  |  |  |  |  |  |  |  |  |  |  | C (# common) |  |  |  |  |  |  |  |  |
| Total Defects (AB/C) |  |  |  |  |  | Number Found (A+B-C) |  |  |  |  |  |  |  |  |  |  |  |  | Number Left |  |  |  |  |  |  |  |  |
| Meeting Time |  |  |  |  |  | Total Inspection Hours |  |  |  |  |  |  |  |  |  |  |  |  | Overall Rate |  |  |  |  |  |  |  |  |
| Reviewer Data |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| Name |  |  |  |  |  |  |  | Defects |  |  |  |  | Preparation Data |  |  |  |  |  |  |  |  |  |  |  |  | Est. |  |
|  |  |  |  |  |  |  |  | Major |  |  | Minor |  | Size |  |  |  |  | Time |  |  |  | Rate |  |  |  | Yield |  |
| Totals |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| Defect Data |  |  |  |  |  |  | Defects |  |  |  | Reviewers (finding major defects) |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| No. | Defect Description |  |  |  |  |  | Maj |  | Min |  |  |  |  |  |  |  |  |  |  |  |  |  | A |  |  |  | B |
| Page Totals |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| Page Unique Defects |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |

TSP Inspection Report Instructions - Form INS

| Purpose | - Use this form to gather and analyze inspection data. - These data must be gathered during the inspection as they cannot generally be obtained later. |
| --- | --- |
| General | - Record the preparation data at the beginning of the inspection meeting. - Complete the inspection data at the end of the inspection meeting. - It is helpful to have line and page numbers on the printed product text. |
| Major/Minor Defects | - Major defects: where the fix will change the design or code - Example: a requirements defect necessitating code changes - Example: a coding change requiring an added semicolon - Minor defects: all other defects - Example: a comment, documentation, or code format change |
| Header | - Enter your name, the project name, team name, and the date. - Enter the names of the moderator and producer. - Also enter the product and the process phase it is in or completing. |
| Reviewer Data: Preparation | - For each reviewer, enter the reviewer’s name and preparation time. - the major and minor defects the reviewer found in preparation - the LOC, lines, or pages each reviewer inspected (to save time, reviewers may concentrate on program sections) - the preparation rate in LOC, pseudocode lines, or pages per hour - Also calculate and enter the total preparation time, total major and minor defects found, and overall preparation rate. |
| Reviewer Data: Yield | At the end of the inspection, calculate the team and reviewer yields. |
| Product Size | - For requirements or high-level design inspections, enter the text pages. - For detailed design inspections, enter the LOC or pseudocode lines. - For source code inspections, enter the source LOC. |
| Defect Data: Reviewers | In the first row below the “Reviewers” heading, enter the name or initials of each reviewer who participated in the inspection. |
| Defect Data: No. | - Enter a number for each defect found in the inspection. - It is most convenient to use the document line and page number. |
| Defect Data: Defect Description | - Describe defects and check whether major (Maj) or minor (Min). - For major defects, check the column for each reviewer who found that defect during inspection preparation. |
| Summary: Estimate Remaining Defects | - After all defects are entered, count the major defects each reviewer found that no other reviewer found (the reviewer's unique defects). - Identify the reviewer who found the most unique defects. - Check the defects that reviewer found in column A. - In column B, check all the defects found by the other reviewers. - Count the common defects (C for common) between columns A and B. - The estimated number of defects in the product is AB/C. - Round fractional results to the nearest integer. - The number of defects found in the inspection is A+B-C. - The number remaining is: total less the number found: (AB/C)-A-B+C. - This defect estimate is only reliable when all the numbers A and B are greater than 4 and A-C, and B-C are both greater than 1. - Even with these criteria, total defect error is likely to be 10% or more. - Generally, the larger these numbers, the more reliable the estimate. - If A=B=C, you have likely found all the defects. - If several reviewers found the same largest number of unique defects, repeat these calculations, using each of these reviewers as A, and use the largest resulting number as the total defect estimate. - Enter total meeting time, inspection hours, and inspection rate. |

TSP Process Inventory - Form INV

| Name |  | Date |  |
| --- | --- | --- | --- |
| Project |  | Launch/Phase |  |

(If you need additional space, use another inventory sheet.)

(List the elements in categories such as forms, scripts, standards, text pages, etc.)

|  |  | Work Units |  |  |  | When |  | Est. |  |  |
| --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- |
| Process Elements |  | Mod. |  | New |  | Needed |  | Hours |  | Team Member |
| Totals |  |  |  |  |  |  |  |  |  |  |

TSP Process Inventory Instructions - Form INV

| Purpose | Use this form for - listing needed scripts, forms, standards, or other work products - specifying when those items are needed - recording the estimated size of the item and the time for developing or obtaining it - assigning a team member to obtain or develop each item |
| --- | --- |
| General | - In making the inventory, group the processes or other items in categories. - Since it generally takes a different amount of time to develop elements in each category, the data from this form will help you make more accurate estimates in the future. - When making detailed plans, team members should include these items in their personal task plans. - This form is used only when a tool with equivalent functionality, features, or purpose is not available. |
| Header | Enter your name, project name, launch phase, and date. |
| Process Elements | List the process elements you plan to develop or modify. |
| Size | Determine and record the number of elements or pages to be - modified - newly developed |
| When Needed | Enter when each element will be needed, either by a date or by a process phase. |
| Estimated Hours | List the estimated hours of work required to develop, modify, or obtain each item. |
| Team member | Enter the name of the team member who will either develop the element or otherwise obtain it for the team. |
| Total | Total the estimated size and time data by element category. |

TSP Issue and Risk Tracking Log - Form ITL

| Name |  | Date |  |
| --- | --- | --- | --- |
| Project |  | Launch/Phase |  |

| No. | Date |  | Personal/Team | Risk/Issue | Impact | Likelihood | Source | Owner |
| --- | --- | --- | --- | --- | --- | --- | --- | --- |
| Description |  |  |  |  |  |  |  | Follow-up Date |
|  |  |  |  |  |  |  |  | Resolved Date |
| No. | Date |  | Personal/Team | Risk/Issue | Impact | Likelihood | Source | Owner |
| Description |  |  |  |  |  |  |  | Follow-up Date |
|  |  |  |  |  |  |  |  | Resolved Date |
| No. | Date |  | Personal/Team | Risk/Issue | Impact | Likelihood | Source | Owner |
| Description |  |  |  |  |  |  |  | Follow-up Date |
|  |  |  |  |  |  |  |  | Resolved Date |
| No. | Date |  | Personal/Team | Risk/Issue | Impact | Likelihood | Source | Owner |
| Description |  |  |  |  |  |  |  | Follow-up Date |
|  |  |  |  |  |  |  |  | Resolved Date |
| No. | Date |  | Personal/Team | Risk/Issue | Impact | Likelihood | Source | Owner |
| Description |  |  |  |  |  |  |  | Follow-up Date |
|  |  |  |  |  |  |  |  | Resolved Date |
| No. | Date |  | Personal/Team | Risk/Issue | Impact | Likelihood | Source | Owner |
| Description |  |  |  |  |  |  |  | Follow-up Date |
|  |  |  |  |  |  |  |  | Resolved Date |
| No. | Date |  | Personal/Team | Risk/Issue | Impact | Likelihood | Source | Owner |
| Description |  |  |  |  |  |  |  | Follow-up Date |
|  |  |  |  |  |  |  |  | Resolved Date |

TSP Issue and Risk Tracking Log Instructions - Form ITL

| Purpose | Use this log to record and track project risks and issues. - Risks or issues may affect the team or may be personal. - Risks are uncertainties; they may or may not happen. - Issues are certainties; without action, they will happen. |
| --- | --- |
| General | - For both risks and issues record - a description of the risk or issue - who is responsible for tracking each risk or issue (owner) - data on each risk or issue, including when it is resolved - For risks, conduct a risk evaluation. - Evaluate the risk in terms of likelihood and impact. - Determine the source of the risks, which can fall within three categories; Engineering, Development Environment, and Program Constraints. For information about these categories, their associated sources and characteristics, refer to the Taxonomy-Based Risk Identification Technical Report, CMU/SEI-93-TR-6 (www.sei.cmu.edu). - A priority of HM would be a risk with a high likelihood of occurring and a medium impact on the project. |
| Issue/Risk Tracking | - Keep a master copy of the completed risk and issue logs in the project notebook. - In each weekly meeting, each team member reviews the status of the risks and issues he or she is responsible for. - In the weekly meetings, set review priorities based on issue/risk priority, flag date, and chronological age. - For each new phase, review the flagged items for the phase. - Note that this form is typically used as a template in a spreadsheet or database. |
| No. | Assign a control number to each risk and issue. |
| Date | Enter the date on which the risk or issue was entered in the ITL system. |
| Personal/Team | Enter an P for a personal risk or issue and a T for a team risk or issue. |
| Risk/Issue | Enter an R for a risk or an I for an issue. |
| Impact | For risks, enter the impact to the project if the risk occurs. - H (High): high impact to the project - M (Medium): medium impact to the project - L (Low): low impact to the project |
| Likelihood | For risks, enter the likelihood that the risk will occur. - H (High): high likelihood of occurring - M (Medium): medium likelihood of occurring - L (Low): low likelihood of occurring |
| Source | Based on the risk category, select one of the following sources of the described risk. - Engineering: Requirements, Design, Code and Unit Test, Integration and Test, or Engineering Specialties - Development Environment: Development Process, Development System, Management Process, Management Methods, or Work Environment - Program Constraints: Resources, Contract, or Program Interfaces |
| Owner | Name the team member who is tracking the risk or issue. |
| Description | - Describe the risk or issue as clearly as possible. For example - a change to be made or interface to be checked - a requirements question to answer - a possible delay in obtaining a support tool - Describe the risk or issue completely enough to permit you or someone else to later take the needed action. |
| Follow-up Date | Note the date when the risk or issue should be reviewed. |
| Resolved | Record the date on which the risk or issue was resolved. |

TSP+ Configuration Change Request Log - Form LOGCCR

| Organization |  | Page Number |  |
| --- | --- | --- | --- |
| Project |  | Launch/Phase |  |

| CCR Control No. | CCR Title | CCB Priority | Product Owner | CI Number Against | Status | CI Number Released |
| --- | --- | --- | --- | --- | --- | --- |

TSP+ Configuration Change Request Log Instructions - Form LOGCCR

| Purpose | - To provide the support manager or configuration management coordinator (CMC) with a mechanism for recording and tracking all configuration change request forms (Form CCR) - To maintain the integrity of work products currently under configuration control |
| --- | --- |
| General | - Use the LOGCCR form to - assign unique CCR identification numbers to all CCR forms received - maintain status of CCR - maintain change control history of configuration items - Note that this form is typically used as a template in a spreadsheet or database. - For changes to the OSSP, and / or PSSP, the SPDR and LOGSPDR performs the role of, and substitutes, the configuration change request forms and associated process (forms CCR and LOGCCR). |
| Header | - Enter name of organization and page number. - Provide the current project name and launch/phase the project is in. |
| CCR Control No. | - Enter the configuration change request number. - For each CCR, use a sequential number starting with 1 (or 001, etc.). |
| CCR Title | - Enter the CCR Title as written on the CCR form. |
| CCB Priority | - Enter the priority assigned by the CCB (Urgent, Important, or Routine). |
| Product Owner | - Enter the product owner assigned to the particular CCR. |
| CI Number Against | - Enter the Configuration Item number the CCR was written against, as specified on the CCR form. |
| Status | - Enter the CCR’s status (Received, Evaluated, Approved, Returned, Disapproved, or Implemented). - This field should be updated whenever the CCR’s status is changed. |
| CI Number Released | - Enter the CI number of the first CI release which contains the CCR’s approved implementation. - This field should be populated after Configuration Identification Release Form (Form CIR) has been approved for the configuration item containing the CCR’s approved change. |

TSP+ Configuration Item Log - Form LOGCI

| Organization |  | Page Number |  |
| --- | --- | --- | --- |
| Project |  | Launch/Phase |  |

| CI No. | CI Title | Release Type | Product Owner | Date Released | Location of CI | Physical Configuration Audit |
| --- | --- | --- | --- | --- | --- | --- |

TSP+ Configuration Item Log Instructions - Form LOGCI

| Purpose | - To provide the Support Manager or Configuration Management Coordinator (CMC) a mechanism for recording and tracking all configuration items which have been released (Form CIR) - To maintain the integrity of work products currently under configuration control |
| --- | --- |
| General | - Use the LOGCI form to - assign unique Configuration Item identification numbers to all configuration items identified using the Configuration Identification Release Form (Form CIR) - maintain status and location of all configuration items - maintain configuration history of all configuration items - Note that this form is typically used as a template in a spreadsheet or database. |
| Header | - Enter name of organization and page number. - Provide the current project name and launch/phase the project is in. |
| CI No. | - Enter the configuration item number for the configuration item identified of the CIR form. - For each CI, use the following format CI-V.R, starting with 001-0.0. A CI number is assigned to a particular configuration item when the “Initial” CIR is approved. CI numbers are assigned sequentially, starting with 001. For example, 005-0.0. - V and R represent the configurations item’s version and revision, respectfully. V and R are assigned sequentially, starting with 0.0. The V is incremented whenever a “Version” CIR is approved for an existing configuration item. For example, 005-1.0. - The R is incremented whenever a “Revision” CIR is approved for an existing configuration item. For example, 005-1.1. - In the event a “Rescind the release” CIR is approved. The CI number is simply the CI Number of the configuration item being rescinded. |
| CI Title | Enter the CI Title as written on the CIR form. |
| Release Type | Enter the release type selected on the CIR form (Initial, Revision, Version, or Rescind) |
| Product Owner | Enter the name of the configuration item owner, as identified on the CIBPS form, for the given configuration item being released. |
| Date Released | Enter the date in which all approvals are received on the CIR form. |
| Location of CI | - Enter the location in which the configuration item is stored. - In order to establish and maintain the integrity of the configuration item, appropriate levels of control must also be established and maintained. The levels of control should be considered when determining the storage location of the configuration item. |
| Physical Configuration Audit | This field is reserved for the quality manager. The quality manager will populate this field when conducting a configuration management audit (see script CMAUDIT) |

| TSP Defect Recording Log - Form LOGD Defect Types |  |
| --- | --- |
| 10 Documentation | 60 Checking |
| 20 Syntax | 70 Data |
| 30 Build, Package | 80 Function |
| 40 Assignment | 90 System |
| 50 Interface | 100 Environment |

| Name |  |  | Date |  |
| --- | --- | --- | --- | --- |
| Project |  |  |  |  |
| Part/Assembly |  |  |  |  |

|  | Date |  | Number |  |  | Type |  | Assembly |  | Inject |  | Remove |  | Fix Time |  | Fix Defect |
| --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- |
| Description |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
|  | Date |  | Number |  |  | Type |  | Assembly |  | Inject |  | Remove |  | Fix Time |  | Fix Defect |
| Description |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
|  | Date |  | Number |  |  | Type |  | Assembly |  | Inject |  | Remove |  | Fix Time |  | Fix Defect |
| Description |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
|  | Date |  | Number |  |  | Type |  | Assembly |  | Inject |  | Remove |  | Fix Time |  | Fix Defect |
| Description |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
|  | Date |  | Number |  |  | Type |  | Assembly |  | Inject |  | Remove |  | Fix Time |  | Fix Defect |
| Description |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
|  | Date |  | Number |  |  | Type |  | Assembly |  | Inject |  | Remove |  | Fix Time |  | Fix Defect |
| Description |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
|  | Date |  | Number |  |  | Type |  | Assembly |  | Inject |  | Remove |  | Fix Time |  | Fix Defect |
| Description |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
|  | Date |  | Number |  |  | Type |  | Assembly |  | Inject |  | Remove |  | Fix Time |  | Fix Defect |
| Description |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |

TSP Defect Recording Log Instructions – Form LOGD

| Purpose | - Use this form to hold data on the defects you find and correct. - Keep separate logs for each program, component, or module. - These data are used to complete form SUMP. - For integration, system test, and user-reported defects, also use form DEFECT. |
| --- | --- |
| General | - Record each defect separately and completely. - If you need additional space, use another copy of the form. - This form is only used when a tool with equivalent functionality, features, or purpose is not available. |
| Header | - Enter your name, project name, part or assembly name, and date. - For larger programs, keep a separate LOGD form for each component or module. |
| Date | Enter the date you found the defect. |
| Number | - Enter the defect number. - For each program or module, use a sequential number starting with 1 (or 001, etc.). |
| Type | - Enter the defect type from the defect type list summarized in the top left corner of the LOGD form. - Use your best judgment in selecting which type applies. |
| Assembly | Enter the assembly name |
| Inject | - Enter the phase when this defect was injected. - Use your best judgment. |
| Remove | - Enter the phase during which you fixed the defect. - This will generally be the phase when you found the defect. |
| Fix Time | - Enter the time you took to find and fix the defect. - This time can be determined by stopwatch or by judgment. |
| Fix Defect | - If you or someone else injected this defect while fixing another defect, record the number of the improperly fixed defect. - If you cannot identify the defect number, enter an X. |
| Description | Write a succinct description of the defect that is clear enough to later remind you about the error and help you to remember why you made it. |

TSP+ Process Improvement Proposal Log - Form LOGPIP

| Organization |  | Page Number |  |
| --- | --- | --- | --- |
| Project |  | Launch/Phase |  |

| PIP Control No. | PIP Title | Estimated Effort Involved | Status | CI Number Released | Actual Effort Involved | Date Done |
| --- | --- | --- | --- | --- | --- | --- |

TSP+ Process Improvement Proposal Log Instructions - Form LOGPIP

| Purpose | To provide the Process Manager or PIP Coordinator a mechanism for recording and tracking all process improvement proposal forms (Form PIP) |
| --- | --- |
| General | - Use the LOGPIP form to - assign unique PIP identification numbers to all PIP forms received - maintain status of PIP - Note that this form is typically used as a template in a spreadsheet or database. |
| Header | - Enter name of organization and page number. - Provide the current project name and launch/phase the project is in. |
| PIP Control # | - Enter the process improvement proposal number. - For each PIP, use a sequential number starting with 1 (or 001, etc.) |
| PIP Title | Enter the PIP Title as written on the PIP form. |
| Estimated Effort Involved | Enter the estimate of the effort involved in implementing the PIP, in terms of task hours. |
| Status | - Enter the PIP’s status (Received, Evaluated, Accepted, Returned, Deferred, or Done) - This field should be updated whenever the PIP’s status is changed. |
| CI Number Released | - Enter the CI number of the first CI release which contains the PIP’s implementation. - This field should be populated after Configuration Identification Release, Form – Form CIR, has been approved for the configuration item containing the PIP’s changes. |
| Actual Effort Involved | After PIP has been implemented and configured, enter the actual effort involved in implementing the PIP, in terms of task hours. |
| Date Done | Enter date the PIP’s implementation was completed and configured. |

TSP+ Standard Process Deviation Request Log - Form LOGSPDR

| Organization |  | Page Number |  |
| --- | --- | --- | --- |

| SPDR Control No. | SPDR Title | Project | Launch/Phase | Effected Process Asset(s) | Status | PIP Number Created |
| --- | --- | --- | --- | --- | --- | --- |

TSP+ Standard Process Deviation Request Log Instructions - Form LOGSPDR

| Purpose | - To provide the Process Group (PG) a mechanism for recording and tracking all standard process deviation request forms (Form SPDR) - To establish and maintain the integrity of the organizational and project’s set of standard processes |
| --- | --- |
| General | - Use the LOGSPDR form to - assign unique SPDR identification numbers to all SPDR forms received - maintain status of SPDR - maintain history of the standard processes being used. - For changes to the OSSP, and / or PSSP, the SPDR and LOGSPDR performs the role of, and substitutes, the configuration change request forms and associated process (forms CCR and LOGCCR). - Note that this form is typically used as a template in a spreadsheet or database. |
| Header | Enter name of organization and page number. |
| SPDR Control # | - Enter the standard process deviation request’s control number. - For each SPDR, use a sequential number starting with 1 (or 001, etc.). |
| SPDR Title | Enter the SPDR Title as written on the SPDR form. |
| Project | Enter the project affected by the SPDR. |
| Launch/Phase | Enter the launch or phase the project is in, as stated on the SPDR. |
| Effected Process Asset(s) | List all scripts, specifications, guidelines, instructions and checklist affected by the deviation request. |
| Status | - Enter the SPDR’s status (Received, Approved, Returned, Disapproved, or Evaluated). - This field should be updated whenever the SPDR’s status is changed. |
| PIP Number Created | Enter the PIP control # of any PIP generated from a team’s evaluation of the given SPDR. |

TSP Time Recording Log - Form LOGT

| Name |  | Date |  |
| --- | --- | --- | --- |
| Project |  |  |  |

| Assembly | Phase | Task | Start Date and Time | Stop Date and Time | Int. Time | Delta Time | Comments |
| --- | --- | --- | --- | --- | --- | --- | --- |

TSP Time Recording Log Instructions – Form LOGT

| Purpose | - Use this form to record the time spent on each project task. - Either keep one log and note the task and product element for each entry, or keep separate logs for each major task. |
| --- | --- |
| General | - This form is used only when a tool with equivalent functionality, features, or purpose is not available. - Record all the time you spend on the project. - Record the time in minutes. - Be as accurate as possible. - If you need additional space, use another copy of the form. - If you forget to record the starting, stopping, or interruption time for a task, promptly enter your best estimate. |
| Header | - Enter your name and the date. - Enter the project name. |
| Assembly | Enter the assembly name. |
| Phase | Enter the name or other designation of the phase or step you worked on, e.g. Requirements, Design, Test. |
| Task | Enter the task name. |
| Start Date and Time | Enter the date and time when you start working on a task. |
| Stop Date and Time | Enter the date and time when you stop working on that task. |
| Interruption Time | - Record any interruption time that was not spent on the task - If you have several interruptions, enter their total time. - You may enter the reason for the interrupt in comments. |
| Delta Time | Enter the clock time you actually spent working on the task, less the interruption time. |
| Comments | Enter any other pertinent comments that might later remind you of any unusual circumstances regarding this activity. |

TSP+ Team Member Training Log – Form LOGTRNM

| Name |  | Page |  |  |  |
| --- | --- | --- | --- | --- | --- |
| E-mail |  | Organization |  |  |  |
| Role(s) |  |  |  |  |  |

| Skills, Courses, OJT Experience | (R)equired / (D)esired | Date Completed |
| --- | --- | --- |

TSP+ Team Member Training Log Instructions – Form LOGTRNM

| Purpose | To track the status of an individual’s training |
| --- | --- |
| General | - A separate team member training log should be established and maintained for each individual in the organization. - Note that this form is typically used as a template in a spreadsheet or database. |
| Header | - Enter the team member’s name, email and designated roles. - Enter the organization’s name and form page number |
| Skills, Courses, OJT Experience | Copy the Skills, Courses, and OJT Experienced listed in the training matrix (form TRNM). |
| Required / Desired | Based on the team member’s allocated role(s), mark each skill as required or desired by placing an R or D, respectively, in the field provided. |
| Date Completed | Enter the date in which each skill, course, or OJT experience has been obtained or waiver approved. The date completed can be obtained from the following forms: TRNOJT, TRNSI, TRNWR. |
| Training Manager | - Periodically review all individual’s team member training log to ensure that they are complete and accurate. - When individual role assignments change or updates are made to the training matrix (form TRNM): - Update all individual team member training logs (form LOGTRNM) to reflect changes made to the TRNM. - Review individual team member training logs (form LOGTRNM) to determine if any additional training is required. Notify individuals of any unsatisfied training requirement. - Notify team leader of team member’s unsatisfied training requirements. |

TSP+ Training Request Log - Form LOGTRNR

| Organization |  | Page Number |  |
| --- | --- | --- | --- |

| TRNR Number | Proposed Training Activity (Course Title) | Project | Launch/Phase | Date Approved | Target Date | Status | Date Complete |
| --- | --- | --- | --- | --- | --- | --- | --- |

TSP+ Training Request Log Instructions - Form LOGTRNR

| Purpose | To provide the training manager with a mechanism for recording and tracking all training requests (form TRNR) |
| --- | --- |
| General | - Use the LOGTRNR form to - assign unique training request control numbers to all training requests received (form TRNR) - maintain status of all training requests. - Note that this form is typically used as a template in a spreadsheet or database. |
| Header | Enter name of organization and form page number. |
| TRNR Number | - Enter the training request control number. - For each TRNR, use a sequential number starting with 1 (or 001, etc.). |
| Proposed Training Activity (Course Title) | Enter the Proposed Training Activity as written on the TRNR form. |
| Project | Enter the project(s) effected by the training request. |
| Launch/Phase | Enter the launch or phase the project is in, as stated on the TRNR form. |
| Date Approved | Enter the date in which all approvals are received on the TRNR form. |
| Target Date | Enter the date in which the training is required or scheduled. |
| Status | - Enter the training request status (Approved, Denied, Received, Scheduled, or Completed). - This field should be updated whenever the TRNR’s status is changed. |
| Date Completed | - Enter the date in which the training was Denied or Completed. - Upon completion of approved training requests, update all individuals who completed the training, using the Team Member Training Logs (form LOGTRNM). |

TSP Meeting Report - Form MTG

| Name |  |  |  |  | Date |  |  |  |
| --- | --- | --- | --- | --- | --- | --- | --- | --- |
| Chairperson |  | Location |  |  |  |  |  |  |
| Meeting Date |  | Start Time |  |  |  | End Time |  |  |

| Subject/Purpose |  |  |  |  |  |  |  |  |
| --- | --- | --- | --- | --- | --- | --- | --- | --- |
| Attendees |  |  |  |  |  |  |  |  |
| Name |  |  |  |  |  |  | Role |  |
| Agenda |  |  |  |  |  |  |  |  |
| Times (min.) |  |  |  |  |  |  |  |  |
| Plan | Start |  | Stop |  | Topics |  | Discussion Leader |  |
| Decisions, Actions, and Key Information |  |  |  |  |  |  |  |  |
| What |  |  |  |  |  | Who |  | When |

TSP Meeting Report Instructions – Form MTG

| Purpose | To record meeting arrangements and results |
| --- | --- |
| General | - Complete the header, purpose, and agenda portions of this form in advance of the meeting. - At the beginning of the meeting, determine who will handle the timekeeper and recorder roles. - For more space, attach another form or separate sheets. - This form is used only when a tool with equivalent functionality, features, or purpose is not available. |
| Header | - Enter your name and the date you filled out the form. - Enter the name of the chairperson. - Enter the planned meeting time and location. |
| Subject/Purpose | - Name the type of meeting: weekly team, status, review, etc. - Succinctly describe the meeting’s purpose. - If you cannot briefly describe what the meeting is to accomplish, reconsider holding the meeting. |
| Attendees | - List the planned meeting attendees. - You must know in advance who will chair the meeting. |
| Meeting Roles | - The chairperson leads the discussion and ensures that the meeting process and agenda are followed. - The chairperson also ensures that the meeting roles are assigned at the beginning of the meeting. - The timekeeper records the actual meeting times and helps the chairperson keep the meeting on schedule. - The recorder ensures that all conclusions, decisions, and planned actions are understood, and documented. - The recorder completes the meeting report form and gives it to the chairperson. - The chairperson prepares and distributes the meeting report. - In most cases, a completed copy of the MTG form is an adequate report. |
| Agenda | - List the agenda topics with times and discussion leaders. - All discussion leaders must know their agenda topics in advance. - If you need additional space, use another form or attach a separate sheet with the agenda. |
| Decisions, Actions, and Key Information | - For all decisions, actions, and key information, clearly and completely list - what is to be or was done - who made the decision or will take the action - what information was provided by whom - when the actions are to be taken - Where additional data are needed, attach separate sheets |

TSP Process Improvement Proposal - Form PIP

| Name |  |  | Date |  |  |
| --- | --- | --- | --- | --- | --- |
| E-mail |  | Organization |  |  |  |
| Project |  | Launch/Phase |  |  |  |

| PIP Number |  |  | Priority |  |  |  |  |
| --- | --- | --- | --- | --- | --- | --- | --- |
| PIP Title |  |  |  |  |  |  |  |
| Improvement Description |  |  |  |  |  |  |  |
| Briefly describe the improvement you suggest. |  |  |  |  |  |  |  |
| Process Elements Impacted |  |  |  |  |  |  |  |
| If you know them, list the process elements that must be added, changed, or deleted. |  |  |  |  |  |  |  |
| Improvement Benefits (check one) |  |  |  |  |  |  |  |
| Improved Quality _______ Reduced Cycle Time ________ Reduced Risk ________ |  |  |  |  |  |  |  |
| Describe the likely benefits of the suggested change. |  |  |  |  |  |  |  |
| When completed and reviewed, submit to the Process Manager and keep a copy. |  |  |  |  |  |  |  |
| Do not write below this line. |  |  |  |  |  |  |  |
| PIP Control No. |  |  |  | Accepted |  |  |  |
| Received |  |  |  | Returned |  |  |  |
| Evaluated |  |  |  | Deferred |  |  |  |
| Effort Involved |  |  |  | Date Done |  |  |  |
| Author Notified |  |  |  |  |  |  |  |
| Reasons |  |  |  |  |  |  |  |

TSP Process Improvement Proposal Instructions - Form PIP

| Purpose | - To provide a way to record process problems and improvement ideas - To provide an orderly record of your process improvement ideas for use in process improvement |
| --- | --- |
| General | - This form is used only when a tool with equivalent functionality, features, or purpose is not available. - Use the PIP form to - record process improvement ideas as they occur to you - establish priorities for your improvement plans - describe lessons learned and unusual conditions - Keep PIP forms on hand while using the TSP. - Record process problems, even without proposed solutions. - Submit the PIPs for use in process improvement. |
| Header | - Enter your name and date. - Provide your e-mail address and organization in case there are any questions. |
| PIP Number | Use for your own identification purposes. |
| Priority | - Indicate if PIP priority is urgent, important, or routine. - Explain the reason for this priority under “Improvement Benefits.” |
| PIP Title | Create a title for the PIP. |
| Improvement Description | Describe your proposed improvement as explicitly as possible. |
| Process Elements Impacted | Where you can, reference the specific process elements impacted and the changes suggested. |
| Improvement Benefits | Describe the benefits you expect from this change. Be as specific as possible. - the difficulties overcome - the impact on the product, the process, and you |
| When Completed | - Keep a copy for your records. - Submit a copy to your team’s process manager or PIP coordinator. |
| Process Manager or PIP Coordinator | - Review all PIPs. - Evaluate the PIP. - Estimate implementation effort. - Enter PIP into LOGPIP and allocate unique PIP Control No. - Enter date received. - Decide whether to accept the PIP, return it for more information, or defer it. - Notify the author of the disposition and, if returned, the information needed. - Submit approved PIPs to the process group for action. |

TSP Team Role Assignments - Form ROLE

| Name |  | Date |  |
| --- | --- | --- | --- |
| Project |  | Launch/Phase |  |

| Team Member Roles |  | Requirements | Design | Implementation | Integration and Test |
| --- | --- | --- | --- | --- | --- |
| Official Team Leader | P |  |  |  |  |
|  | A |  |  |  |  |
| Customer Interface | P |  |  |  |  |
| Manager | A |  |  |  |  |
| Design Manager | P |  |  |  |  |
|  | A |  |  |  |  |
| Implementation | P |  |  |  |  |
| Manager | A |  |  |  |  |
| Planning Manager | P |  |  |  |  |
|  | A |  |  |  |  |
| Process Manager | P |  |  |  |  |
|  | A |  |  |  |  |
| Quality Manager | P |  |  |  |  |
|  | A |  |  |  |  |
| Support Manager | P |  |  |  |  |
|  | A |  |  |  |  |
| Test Manager | P |  |  |  |  |
|  | A |  |  |  |  |
|  | P |  |  |  |  |
|  | A |  |  |  |  |
|  | P |  |  |  |  |
|  | A |  |  |  |  |
|  | P |  |  |  |  |
|  | A |  |  |  |  |
|  | P |  |  |  |  |
|  | A |  |  |  |  |
|  | P |  |  |  |  |
|  | A |  |  |  |  |
|  | P |  |  |  |  |
|  | A |  |  |  |  |
|  | P |  |  |  |  |
|  | A |  |  |  |  |
|  | P |  |  |  |  |
|  | A |  |  |  |  |
|  | P | Principal responsibility for the role |  |  |  |
|  | A | Alternate responsibility for the role |  |  |  |

TSP Team Role Assignments Instructions - Form ROLE

| Purpose | This form holds data on the team role assignments. |
| --- | --- |
| General | - Make team role assignments during launch and relaunch. - Enter the names of those assigned the principal and alternate responsibilities for each role. - Every team member should have at least one principal or alternate team role. - Update the form during relaunch or when roles change. - Use form ROLEMX if necessary to help make role selections. - See ROLE specification for the role responsibilities. - This form is used only when a tool with equivalent functionality, features, or purpose is not available. |
| Header | Enter your name, project name, launch phase, and date. |
| Team Member Roles | List any other role assignments at the bottom of the form. |
| Team Leader | The team leader - serves as the project and team manager - obtains project staffing, makes job assignments, approves plans, reports status, and arranges for needed support - leads the launch and relaunch meetings - supports and guides the team members in doing their jobs - usually has no other team role. |
| Customer Interface Manager | The customer interface manager - manages requirements issues and changes - ensures that all requirements assumptions are verified - leads usability, installation, documentation, and training plans |
| Design Manager | The design manager - leads the design work and controls design changes - sets the design standards and specifications |
| Implementation Manager | The implementation manager - leads the implementation work - sets the implementation, size, and performance standards |
| Planning Manager | The planning manager - guides estimating, planning, tracking, and risk management - establishes the standard planning framework used for developing the team and personal plans - consolidates the team members' plans into the overall team plan |
| Process Manager | The process manager - leads the process and procedure definition work - manages the PIP process - owns and maintains the team processes |
| Quality Manager | The quality manager - develops and tracks the quality plan and analyzes quality data - moderates team inspections or obtains a moderator - alerts the team and management to likely quality problems |
| Support Manager | The support manager - establishes the development system - operates the configuration management, change management, and issue tracking systems |
| Test Manager | The test manager - ensures that testing issues are considered in every phase - leads test planning, measuring, tracking, and management |
| Team Member | All team members do design, implementation, and testing work and support other team members as needed. |

TSP Role Assignment Matrix - Form ROLEMX

| Name |  | Date |  |
| --- | --- | --- | --- |
| Project |  | Launch/Phase |  |

| Team Member Roles Team Members | Customer Interface Manager | Design Manager | Implementation Manager | Planning Manager | Process Manager | Quality Manager | Support Manager | Test Manager |  |  |  |  |  |  |  |  |
| --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- |

TSP Role Assignment Matrix Instructions - Form ROLEMX

| Purpose | This form is used by the team to select team role assignments. |
| --- | --- |
| General | - Make team role assignments during launch and relaunch. - Record the names of those assigned the principal and alternate responsibilities for each role in form ROLE. - Every team member should have at least one principal or alternate team role. - See ROLE specification for the role responsibilities. - This form is used only when a tool with equivalent functionality, features, or purpose is not available. |
| Header | Enter your name, project name, launch phase, and date. |
| Team Member Roles | - The standard TSP role assignments are listed across the top of the form. - List any other role assignments in the blank spaces at the right of the form. |
| Team Leader | - The project leader or team manager is typically designated by management before the project starts. - The team leader usually has no other team role. |
| Team Members | List the team members in the left-hand column of the form. |
| Initial Role Selection | - Have each team member identify the two roles he or she would prefer to have. - Label these roles with 1 or 2 for the first or second choice. - For small teams, make a larger number of initial selections. |
| Initial Role Entry | For each team member, mark a 1 or 2 by the two roles selected by that team member (or 3, etc. for smaller teams). |
| Unique Role Identification | - Where a team member is the only one to select a role, that team member gets that assignment. - Where a team member has two or more unique roles, he or she may choose which one to take. |
| Choice Elimination | - When a team member's role has been selected, cross off all other choices for that team member. Also cross off all selected roles. - Next, note which team members now have unique roles selected and make appropriate assignments. - Continue this process until either all roles have been selected or no unique choices remains. |
| Duplicate Role Choices | - Where two or more team members select the same roles, they decide with the team's assistance which will have the role. - Where they cannot agree, the team leader, with the team's assistance, makes the final selection. |
| Unselected Roles | Similarly, where no roles have been selected, volunteers are requested from those team members with no or the fewest roles. |
| Alternate Roles | - After the roles have been selected, select an alternate for each role. - The role alternate backs up the role manager when needed. - Be guided by the team members' preferences in assigning the alternate roles. |

| TSP+ Relevant Stakeholder Involvement Matrix Form – Form RSIM |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- |
| Organization |  |  |  |  |  | Page Number |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| Roles |  | Management |  |  | Team Lead | Customer Interface Manager | Design Manager | Implementation Manager | Planning Manager | Process Manager | Support Manager | Quality Manager | Test Manager | TSP Team | Team Member | PG Team |  | PG Planning Manager | PG Support Manager | PG Process Manager | PG Implementation Manager | PG Quality Manager | PG Coaching Manager / Lead TSP Coach | PG Process Asset and Data Repository Manager | PG Training Manager | TSP Coach | PSP Instructor | Configuration Control Board | Product Owner | Course Instructor | Role Manager Team |  |
| Scripts, Forms | Type |  | Leadership Team | Customer / Marketing |  |  |  |  |  |  |  |  |  |  |  |  | PG Team Lead |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| ANA | S | I |  | C |  | R |  |  |  |  |  |  |  | R |  |  |  |  |  |  |  |  |  |  |  | C |  | A |  |  |  |  |
| CCR | F | I |  | I |  |  |  |  |  |  | R |  |  | I | R |  |  |  |  |  |  |  |  |  |  |  |  | A | A |  |  |  |
| CHECKPOINT | S | I | I | I | C |  |  |  |  |  |  |  |  | I | C |  | I |  |  |  |  |  | A |  |  | R |  |  |  |  |  |  |
| CHECKTMDR | F |  |  |  |  |  |  |  |  |  |  |  |  |  | C |  |  |  |  |  |  |  |  |  |  | R |  |  |  |  |  |  |
| CIBPS | F | I |  | I |  |  |  |  |  |  | R |  |  | C |  |  | C |  |  |  |  |  |  |  |  |  |  | C |  |  |  |  |
| CIR | F | I |  | I |  |  |  |  |  | A | R | A |  | I | R | I |  |  |  |  |  |  |  |  |  |  |  | A | A |  |  |  |
| CMAUDIT | S | I |  |  | C |  |  |  |  |  | C | R |  | I |  |  |  |  |  |  |  |  |  |  |  | I |  |  |  |  |  |  |
| CYCLE | S | A | R | I |  |  |  |  |  |  |  |  |  | R |  |  | C |  |  |  |  |  |  |  |  | C |  |  |  |  |  |  |
| DEFECT | F |  |  |  |  |  |  |  |  |  |  | C | C | I | R |  |  |  |  |  |  |  |  |  |  | I |  | A |  |  |  |  |
| DEV | S | A | R | I |  |  |  |  |  |  |  |  |  | R |  |  | C |  |  |  |  |  |  |  |  | C |  |  |  |  |  |  |
| GOAL | F | A |  | A |  |  |  |  |  |  |  |  |  | R |  |  | A |  |  |  |  |  |  |  |  | C |  |  |  |  |  |  |
| HLD | S | C |  | C |  |  | R |  |  |  |  |  |  | R |  |  | I |  |  |  |  |  |  |  |  | C |  | A |  |  |  |  |
| IMP | S | I |  | I |  |  | R | R | R |  |  | R | R | C |  |  | I |  |  |  |  |  |  |  |  | C |  | A |  |  |  |  |
| IMP6 | S | I |  | I |  |  |  |  | R |  |  |  | R | I |  |  | I |  |  |  |  |  |  |  |  | C |  |  |  |  |  |  |
| INS | S |  |  |  |  |  |  |  |  |  |  | R |  | R |  |  |  |  |  |  |  | I |  |  |  | C |  |  | R |  |  |  |
| INS | F |  |  |  |  |  |  |  |  |  |  | R |  | R |  |  |  |  |  |  |  | I |  |  |  | C |  |  | R |  |  |  |
| INV | F |  |  |  |  |  |  |  |  |  |  |  |  | R |  |  |  |  |  |  |  |  |  |  |  | C |  |  |  |  |  |  |
| ITL | F | I |  | I |  |  |  |  |  |  |  |  |  | R | R |  |  |  |  |  |  |  |  |  |  | C |  |  |  |  |  |  |
| LAU | S | A |  | A |  |  |  |  |  |  |  |  |  | R |  | I | A |  |  |  |  |  |  |  |  | R |  |  |  |  |  |  |
| LAU1 | S | R | R | R |  |  |  |  |  |  |  |  |  | C |  |  | R |  |  |  |  |  | R |  |  | R |  |  |  |  |  |  |
| LAU1A | S |  | R |  |  |  |  |  |  |  |  |  |  | R |  |  |  |  |  |  |  |  | R |  |  | R |  |  |  |  |  |  |
| LAU2 | S |  |  |  | R |  |  |  |  |  |  |  |  | R |  |  |  |  |  |  |  |  | C |  |  | R |  |  |  |  |  |  |
| LAU3 | S |  |  |  | R |  | R |  |  | R | R |  |  | R |  |  |  |  |  |  |  |  | C |  |  | R |  |  |  |  |  |  |
| LAU3A | S |  | R |  |  |  |  |  |  |  |  |  |  | C |  |  |  |  |  |  |  |  | R |  |  | R |  |  |  |  | I |  |
| LAU4 | S |  |  |  | R |  | R |  | R |  |  |  |  | R |  |  |  |  |  |  |  |  | C |  |  | R |  |  |  |  |  |  |
| LAU5 | S |  |  |  |  |  |  |  |  |  |  | R |  | R |  |  |  |  |  |  |  |  | C |  |  | R |  |  |  |  |  |  |
| LAU5B | S |  | I |  |  |  |  |  | R |  |  |  |  | I |  |  |  |  |  |  |  |  | C |  |  | R |  |  |  |  | R |  |
| LAU5C | S |  | I |  |  |  |  |  |  |  |  | R |  | I |  |  |  |  |  |  |  |  | C |  |  | R |  |  |  |  | R |  |
| LAU6 | S |  |  |  |  |  |  |  | R |  |  |  |  | R | R |  |  |  |  |  |  |  | C |  |  | R |  |  |  |  |  |  |
| LAU6B | S |  | I |  |  |  |  |  | R |  |  |  |  | I |  |  |  |  |  |  |  |  | C |  |  | R |  |  |  |  | R |  |
| LAU7 | S |  |  |  | R |  |  |  |  |  |  |  |  | R |  |  |  |  |  |  |  |  | C |  |  | R |  |  |  |  |  |  |
| LAU7A | S |  | R |  |  |  |  |  |  |  |  |  |  | I |  |  |  |  |  |  |  |  | R |  |  | R |  |  |  |  |  |  |
| LAU8 | S |  | C |  | R |  |  |  |  |  |  |  |  | R |  |  |  |  |  |  |  |  | C |  |  | R |  |  |  |  |  |  |
| LAU9 | S | A | R | A | R |  |  |  |  |  |  |  |  | R |  |  | A |  |  |  |  |  | R |  |  | R |  |  |  |  |  |  |
| LAUm | S | A | R | A |  |  |  |  |  |  |  |  |  | R |  | I | A |  |  |  |  |  | R |  |  | R |  |  |  |  | R |  |
| LAUPM | S | I | I |  | R |  |  |  |  |  |  |  |  | R |  | I |  |  |  |  |  |  | R |  |  | R |  |  |  |  |  |  |
| LOGCCR | F | I |  |  |  |  |  |  |  |  | R |  |  | I |  | I |  |  |  |  |  |  |  |  |  | I |  |  |  |  |  |  |
| LOGCI | F |  |  |  |  |  |  |  |  |  | R | I |  | I |  |  |  |  |  |  |  |  |  |  |  | I |  | I |  |  |  |  |
| LOGD | F |  |  |  |  |  |  |  |  |  |  | C |  |  | R |  |  |  |  |  |  |  |  |  |  | C |  |  |  |  |  |  |
| LOGPIP | F | I | I |  |  |  |  |  |  | C |  |  |  | I |  |  | C |  |  | R |  |  |  |  |  |  |  |  |  |  |  |  |
| LOGSPDR | F | I |  |  | I |  |  |  |  | I |  |  |  |  | I | I | I |  |  | R |  |  |  |  |  | I |  |  |  |  |  |  |
| LOGT | F |  |  |  |  |  |  |  | C |  |  |  |  |  | R |  |  |  |  |  |  |  |  |  |  | C |  |  |  |  |  |  |
| LOGTRNM | F |  |  |  | I |  |  |  |  |  |  |  |  |  | I |  |  |  |  |  |  |  |  |  | R |  |  |  |  |  |  |  |
| LOGTRNR | F | I |  |  | I |  |  |  |  |  |  |  |  |  |  |  | I |  |  |  |  |  |  |  | R |  |  |  |  |  |  |  |
| LTL | S | A | R |  |  |  |  |  |  |  |  |  |  |  |  |  | C |  |  |  |  |  | R |  |  |  |  |  |  |  |  |  |
| LTL1 | S | A | R |  |  |  |  |  |  |  |  |  |  |  |  |  | C |  |  |  |  |  | R |  |  |  |  |  |  |  |  |  |
| LTL2 | S |  | R |  |  |  |  |  |  |  |  |  |  |  |  |  | C |  |  |  |  |  | R |  |  |  |  |  |  |  |  |  |
| LTL3 | S |  | R |  |  |  |  |  |  |  |  |  |  |  |  |  | C |  |  |  |  |  | R |  |  |  |  |  |  |  |  |  |
| LTL4 | S |  | R |  |  |  |  |  |  |  |  |  |  |  |  |  | C |  |  |  |  |  | R |  |  |  |  |  |  |  |  |  |
| LTL5 | S |  | R |  |  |  |  |  |  |  |  |  |  |  |  |  | C |  |  |  |  |  | R |  |  |  |  |  |  |  |  |  |
| LTLPM | S |  | R |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  | R |  |  |  |  |  |  |  |  |  |
| MAINT | S | A | R | R |  |  |  |  |  |  |  |  |  | R |  |  | A |  |  |  |  |  |  |  |  | R |  |  |  |  |  |  |
| PIP | F |  |  |  |  |  |  |  |  | R |  |  |  | C | R |  |  |  |  |  |  |  |  |  |  | C |  |  |  |  |  |  |
| PM | S | I | I |  | R | R | C | C | R | R | R | R | C | R |  | I |  |  |  |  |  |  |  | I |  | R |  | C | C |  | C |  |
| PMTD | S | I | I |  | R |  |  |  |  | R |  |  |  | R |  |  |  |  |  |  |  |  |  | I |  | R |  | C | C |  | C |  |
| POPS | S | A |  | C | C |  |  |  |  |  |  |  |  | C |  | I | R |  |  |  |  |  | R |  |  | C |  |  |  |  |  |  |
| POPS7 | S | A |  | C | C |  |  |  |  |  |  |  |  |  |  | R | R |  |  |  |  |  |  |  |  | R |  |  |  |  |  |  |
| PREP | S |  | R |  |  |  | R |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  | R |  |  |  |  |  |  |  | R |  |
| PREPT | S | I |  | I | R |  |  |  |  |  |  |  |  | R |  |  | I |  |  |  |  |  |  |  |  | R |  |  |  |  |  |  |
| PREPW | S | I | R |  |  |  | C |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  | R |  | C |  |  |  |  |  | C |  |
| PSSPE | S |  |  |  |  |  |  |  |  | R |  |  |  | C |  | C |  |  |  |  |  |  |  |  |  | C |  |  |  |  |  |  |
| REL1 | S |  |  |  | R |  |  |  |  |  |  |  |  | C |  |  |  |  |  |  |  |  |  |  |  | R |  |  |  |  |  |  |
| REL1A | S |  | R |  |  |  |  |  |  |  |  |  |  | C |  |  |  |  |  |  |  |  | R |  |  | R |  |  |  |  | R |  |
| REQ | S | I |  | C | R | R |  |  |  |  |  |  |  | R |  |  | I |  |  |  |  |  |  |  |  | C |  | A |  |  |  |  |
| ROLE | F |  |  |  |  |  |  |  |  |  |  |  |  | R |  |  |  |  |  |  |  |  |  |  |  | C |  |  |  |  |  |  |
| ROLEMX | F |  |  |  |  |  |  |  |  |  |  |  |  | R |  |  |  |  |  |  |  |  |  |  |  | C |  |  |  |  |  |  |
| RSIM | F | A | R |  | R |  |  |  |  |  |  |  |  | C |  | C | A |  |  |  |  |  |  |  |  | C |  | A |  |  |  |  |
| RTL | S |  | A |  |  |  |  |  |  |  |  |  |  |  |  |  | C |  |  |  |  |  | R |  |  | R |  |  |  |  | R |  |
| RTL1 | S |  | R |  |  |  |  |  |  |  |  |  |  |  |  |  | C |  |  |  |  |  | R |  |  | R |  |  |  |  | R |  |
| RTL2 | S |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  | R |  |  | R |  |  |  |  | R |  |
| RTL3 | S |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  | R |  |  | R |  |  |  |  | R |  |
| RTL4 | S |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  | R |  |  | R |  |  |  |  | R |  |
| RTL5 | S |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  | R |  |  | R |  |  |  |  | R |  |
| RTL6 | S |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  | R |  |  | R |  |  |  |  | R |  |
| RTL7 | S |  | A |  |  |  |  |  |  |  |  |  |  |  |  |  | C |  |  |  |  |  | R |  |  | R |  |  |  |  | R |  |
| RTLPM | S |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  | R |  |  | R |  |  |  |  | R |  |
| SCHED | F |  |  |  |  |  |  |  | C |  |  |  |  | R | R |  |  |  |  |  |  |  |  |  |  | C |  |  |  |  |  |  |
| SPDE | F | A |  |  |  |  |  |  |  | R |  |  |  | C | R | A |  |  |  | R |  |  |  |  |  | C |  |  |  |  |  |  |
| SPDR | F | A |  |  |  |  |  |  |  | R |  |  |  | C | R | A |  |  |  | R |  |  |  |  |  | C |  |  |  |  |  |  |
| SRAM | F | A | R | I | R |  |  |  |  |  |  |  |  | C |  | C | A |  |  |  |  |  |  |  |  | C |  | A |  |  |  |  |
| STATUS | S | I | R | I | R |  |  |  |  |  |  |  |  | R |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| STRAT | F |  |  |  |  |  |  |  |  |  |  |  |  | R |  |  |  |  |  |  |  |  |  |  |  | C |  |  |  |  |  |  |
| SUMDI | F |  |  |  |  |  |  |  |  |  |  | R |  | R | R |  |  |  |  |  |  |  |  |  |  | C |  |  |  |  |  |  |
| SUMDR | F |  |  |  |  |  |  |  |  |  |  | R |  | R | R |  |  |  |  |  |  |  |  |  |  | C |  |  |  |  |  |  |
| SUMP | F |  |  |  |  |  |  |  | R |  |  |  |  | R | R |  |  |  |  |  |  |  |  |  |  | C |  |  |  |  |  |  |
| SUMPD | F | I |  |  |  |  |  |  |  | R |  |  |  | I |  | I |  |  |  | R |  |  |  |  |  | I |  |  |  |  |  |  |
| SUMQ | F |  |  |  |  |  |  |  |  |  |  | R |  | R | R |  |  |  |  |  |  |  |  |  |  | C |  |  |  |  |  |  |
| SUMS | F |  |  |  |  |  |  |  | R |  |  |  |  | R | R |  |  |  |  |  |  |  |  |  |  | C |  |  |  |  |  |  |
| SUMT | F |  |  |  |  |  |  |  | R |  |  |  |  | R | R |  |  |  |  |  |  |  |  |  |  | C |  |  |  |  |  |  |
| SUMTASK | F |  |  |  |  |  |  |  | R |  |  |  |  | R | R |  |  |  |  |  |  |  |  |  |  | C |  |  |  |  |  |  |
| SUMTRNS | F | I |  |  | I |  |  |  |  |  |  |  |  | I |  |  | I |  |  |  |  |  |  |  | R | C |  |  |  | I |  |  |
| TASK | F |  |  |  | R |  |  |  | C |  |  |  |  | R | R |  |  |  |  |  |  |  |  |  |  | C |  |  |  |  |  |  |
| TEST | S |  |  |  |  |  |  | R | R |  |  | R | R | R |  |  |  |  |  |  |  |  |  |  |  | C |  |  |  |  |  |  |
| TEST1 | S |  |  |  |  |  |  | R | R |  |  | R | R | R |  |  |  |  |  |  |  |  |  |  |  | C |  |  |  |  |  |  |
| TEST2 | S |  |  |  |  |  |  | R | R |  |  | R | R | R |  |  |  |  |  |  |  |  |  |  |  | C |  |  |  |  |  |  |
| TEST3 | S |  |  |  |  |  |  | R | R |  |  | R | R | R |  |  |  |  |  |  |  |  |  |  |  | C |  |  |  |  |  |  |
| TESTD | S |  | R |  | R |  |  |  |  |  |  |  |  | R |  |  |  |  |  |  |  |  |  |  |  | C |  |  |  |  | R |  |
| TESTLOG | F |  |  |  |  |  |  |  |  |  |  |  | C | I | R |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| TOPS | S | R |  | R | R |  |  |  |  |  |  |  |  | R |  | R | R |  |  |  |  |  |  |  |  | R |  |  |  |  | R |  |
| TOPS4 | S | R |  | R | R |  |  |  |  |  |  |  |  | R |  | R | R |  |  |  |  |  |  |  |  | R |  |  |  |  | R |  |
| TRNM | F | A |  |  | A | C | C | C | C | C | C | C | C |  | I |  | A | C | C | C | C | C | C | C | R | C | C |  |  |  |  |  |
| TRNOJT | F | A |  |  | A |  |  |  |  |  |  |  |  |  | R |  |  |  |  |  |  |  |  |  | R |  |  |  |  |  |  |  |
| TRNR | F | A |  |  | A |  |  |  |  |  |  |  |  |  | R |  |  |  |  |  |  |  |  |  | R |  |  |  |  |  |  |  |
| TRNSI | F |  |  |  |  |  |  |  |  |  |  |  |  |  | R |  |  |  |  |  |  |  |  |  | R |  |  |  |  | R |  |  |
| TRNSUR | F |  |  |  |  |  |  |  |  |  |  |  |  |  | R |  |  |  |  |  |  |  |  |  | R |  |  |  |  |  |  |  |
| TRNWR | F | A |  |  | A |  |  |  |  |  |  |  |  |  | R |  |  |  |  |  |  |  |  |  | R |  |  |  |  |  |  |  |
| WEEK | S |  |  |  | R | R | R | R | R | R | R | R | R |  | R |  |  |  |  |  |  |  |  |  |  | C |  |  |  |  |  |  |
| WEEK | F |  |  |  |  |  |  |  | R |  |  |  |  | R |  |  |  |  |  |  |  |  |  |  |  | C |  |  |  |  |  |  |
| WEEKL | S |  | R |  | R |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  | C |  |  |  |  |  |  |  |  |  |
| WEEKLR | S |  | R |  | R |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  | C |  |  |  |  |  |  |  | R |  |

TSP+ Relevant Stakeholder Involvement Matrix Form Instructions – Form RSIM

| Purpose | To document and communicate stakeholder roles and responsibilities within an organization and project |
| --- | --- |
| General | - A relevant stakeholder is a group or individual that is called out in a plan to perform certain types of activities or receive certain kinds of information and is affected by or in some way accountable for the outcome of an undertaking. - The matrix must be assessed periodically to ensure that it meets the immediate needs of the organization and its projects. - Note the relevant stakeholder involvement matrix has been pre-populated with a minimal set of roles, scripts and forms as an example. - Each organization and project must evaluate the example and tailor the matrix for completeness. - For example the management role has been used in the broadest sense of the term. This role may be broken down into more specific management roles within an organization. - The types of involvement (Responsible, Accountable, Consulted, and Informed) may also be expanded or modified to adequately describe the involvement of specified stakeholders. - A description of most roles can be found in the role specification (specification ROLE). - Refer to the Stakeholder Role Assignment Matrix (form SRAM) for individual assignments - Many cells in the table are left blank, indicating there is no involvement by the stakeholder for that activity, decision, or deliverable. - Note that this form is typically used as a template in a spreadsheet or database. - The team leader will (1) periodically review the RSIM with teams, projects, the process group, and management for completeness and approval, (2) make changes as required, (3) Ensure that RSIM is placed under appropriate levels of control, and (4) distribute the latest version of RSIM to all relevant stakeholders. |
| Header | Enter the organization’s name and page number. |
| Roles | List all organizational and project specific roles. |
| Scripts, Forms | - List all organizational and project specific scripts and forms defined in the OSSP and PSSP. - For each script and form listed determine how the relevant stakeholders and specify their type of involvement by entering an “R”, “A”, “C”, or “I” in the corresponding row and column. The involvement types are defined as follows. - Responsible – role responsible for performing the activity or producing the deliverable - Accountable – role accountable for approving the activity or deliverable - Consulted – role that needs to be given an opportunity to provide input on the activity or deliverable before it is completed - Informed – role that needs to be informed of the activity or deliverable after it is completed |
| Type | Identify as either a script or form by entering an “S” or “F”, respectively. |

TSP Schedule Planning Template - Form SCHED

| Name |  | Date |  |
| --- | --- | --- | --- |
| Project |  | Launch/Phase |  |

|  |  | Plan |  |  | Actual |  |  |  |
| --- | --- | --- | --- | --- | --- | --- | --- | --- |
| Week No. | Date | Task Direct Hours | Cumulative Hours | Cumulative Planned Value | Task Hours | Cumulative Hours | Week Earned Value | Cumulative Earned Value |

TSP Schedule Planning Template Instructions - Form SCHED

| Purpose | - To record the estimated and actual hours expended by calendar period - To relate the task planned value to the calendar schedule - To calculate adjusted planned and earned values when tasks change |
| --- | --- |
| General | - Expand this template or use multiple pages as needed. - Complete in conjunction with the task planning template. - This form is used only when a tool with equivalent functionality, features, or purpose is not available. |
| Header | Enter your name, project name, launch phase, and date. |
| Week No. | - From the project start, enter a week number, typically starting with 1. - For very small projects, it may be more convenient to use days instead of weeks. |
| Date | - Enter the calendar date for each week. - Pick a standard day in the week, for example, Monday. |
| Plan: Task Direct Hours | - Enter the planned number of task project hours you expect to spend each week. - Consider non-work time such as vacations, holidays, etc. - Consider other committed activities such as e-mail, courses, meetings, and other projects. |
| Plan: Cumulative Hours | Enter the cumulative planned hours through each week. |
| Plan: Cumulative Planned Value | - For each week - take the plan cumulative hours from the SCHED template - on the TASK template, find the task with nearest equal or lower plan cumulative hours and note its plan cumulative value - enter this cumulative value in the SCHED template for that week - if the cumulative value for the prior week still applies, enter it again |
| Actual | - During development, enter the actual direct hours, cumulative hours, and cumulative earned value for each week. - Determine status against plan by comparing the cumulative planned value and the actual cumulative earned value. |

TSP+ Standard Process Deviation Evaluation Form - Form SPDE

| Name |  |  | Date |  |  |
| --- | --- | --- | --- | --- | --- |
| Organization |  | Project |  |  |  |
| Launch/Phase |  | SPDR Number |  |  |  |

| SPDR Title |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- |
| Team Recommendation |  |  |  |  | Successful |  | Unsuccessful |  |  |  |  |  |  | Indeterminate Results |  |  |  |  |  |
| Has a PIP been created for Successful SPDR? |  |  |  |  |  |  |  | Yes |  |  |  |  | No |  |  |  |  |  |  |
| If no, why? |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| Evaluation |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| Based on the Effectiveness Evaluation Criteria, document results of deviation. Include metrics and |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| reference artifacts as appropriate. Provide justification of team’s recommendation. If use of the deviation is |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| terminated prior to project completion, provide rational for premature termination. |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| When completed and reviewed, submit to the Process Manager and keep a copy. |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| Do not write below this line. |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| SPDR Control No. |  |  |  |  |  |  |  |  | Received |  |  |  |  |  |  |  |  |  |  |
| Returned |  |  |  |  |  |  |  |  | Accepted |  |  |  |  |  |  |  |  |  |  |
| Comments/Information Needed |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| Approvals |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| Process Manager |  |  |  |  |  |  |  |  |  |  |  |  |  |  | Date |  |  |  |  |
| Process Group |  |  |  |  |  |  |  |  |  |  |  |  |  |  | Date |  |  |  |  |
| Management |  |  |  |  |  |  |  |  |  |  |  |  |  |  | Date |  |  |  |  |

TSP+ Standard Process Deviation Evaluation Form Instructions - Form SPDE

| Purpose | To provide a mechanism for a team to capture the effectiveness of an approved process deviation (Form SPDR) |
| --- | --- |
| General | - All approved SPDRs must be evaluated against the stated effectiveness evaluation criteria, upon completion of a project or applicable cycle. - The evaluation of the SPDR should be conducted prior to or during a project postmortem in order to incorporate lessons learned into the next project cycle or into future projects within the organization. |
| Header | - Enter your name, date, and organization. - Provide the current project name and launch/phase the project is in. |
| SPDR Number | Use for your own identification purposes. It should be same as the number used on the approved SPDR. |
| SPDR Title | Enter the SPDR title as written on the approved SPDR form. |
| Team Recommendation | Select team recommendation based on evaluation (Successful, Unsuccessful, or Indeterminate Results) |
| Has PIP been created for Successful SPDR? | Select yes if PIP has been or will be generated, or no if the team does not plan to generate a PIP. If the answer is no, provide reason for not generating a PIP. |
| Evaluation | Based on the effectiveness evaluation criteria on form SPDR, document results of deviation. Include metrics and reference artifacts as appropriate. Provide justification of team’s recommendation. If use of the deviation is terminated prior to project completion, provide rationale for premature termination. |
| When Completed | After you have completed the SPDE, keep a copy and submit a copy to your team’s process manager. |
| Process Manager | - Review the SPDE. - Evaluate the SPDE for completeness. If incomplete return for more information. - Compare SPDE to SPDR to ensure all aspects of the effectiveness evaluation criteria of the SPDR has been addressed by the SPDE. If criteria has not been fully addressed return to originator to complete evaluation. - Enter the SPDE’s associated SPDR’s control number. - Record any relevant comments. - Sign and date approval line. - Forward SPDE to process group for approval. |
| Process Group (PG) | - Review the SPDE. - Evaluate the SPDE for completeness. If incomplete return to process manager for more information. - Compare SPDE to SPDR to ensure all aspects of the effectiveness evaluation criteria of the SPDR have been addressed by the SPDE. If criteria have not been fully addressed, return to process manager. - For “Successful” team recommendations, compare SPDR and SPDE to associated PIP to ensure constancy and that sufficient information has been collected to implement the PIP. If not, return SPDE with request for additional information. - Enter date received. - Record any relevant comments. - Sign and date approval line. - Obtain management approval. - Enter date accepted. - Update SPDR status in LOGSPDR to “Evaluated.” - If applicable, enter “PIP number created” in LOGSPDR. |

TSP+ Standard Process Deviation Request Form - Form SPDR

| Name |  |  |  | Date |  |
| --- | --- | --- | --- | --- | --- |
| Organization |  |  | Project |  |  |
| Launch/Phase |  |  | SPDR Number |  |  |

| SPDR Title |  |  |  |  |  |  |  |  |  |
| --- | --- | --- | --- | --- | --- | --- | --- | --- | --- |
| Deviation Request Information |  |  |  |  |  |  |  |  |  |
| List Script(s), Form(s), Specification(s), Guideline(s), Instruction(s) and Checklist(s) effected by deviation |  |  |  |  |  |  |  |  |  |
| Request. (Be as specific as possible; include step numbers, section references, etc.) |  |  |  |  |  |  |  |  |  |
| Provide rationale for deviation, including expected benefits. |  |  |  |  |  |  |  |  |  |
| Effectiveness Evaluation Criteria |  |  |  |  |  |  |  |  |  |
| (Describe what metrics and/or criteria will be used to evaluate effectiveness and/or determine if a PIP will be submitted to modify the standard process.) |  |  |  |  |  |  |  |  |  |
| When completed and reviewed, submit to the Process Manager and keep a copy. |  |  |  |  |  |  |  |  |  |
| Do not write below this line. |  |  |  |  |  |  |  |  |  |
| SPDR Control No. |  |  |  | Received |  |  |  |  |  |
| Approved |  |  |  |  | Returned |  |  |  |  |
| Disapproved |  |  |  |  | Evaluated |  |  |  |  |
| Comments/Information Needed |  |  |  |  |  |  |  |  |  |
| Approvals |  |  |  |  |  |  |  |  |  |
| Process Manager |  |  |  |  |  |  | Date |  |  |
| Process Group |  |  |  |  |  |  | Date |  |  |
| Management |  |  |  |  |  |  | Date |  |  |

TSP+ Standard Process Deviation Request Form Instructions - Form SPDR

| Purpose | To provide a mechanism for a team to make deviation request(s) for a specific project or cycle |
| --- | --- |
| General | - Any deviation from the Organizational Set of Standard Processes (OSSP) or the Project’s Set of Standard Processes (PSSP) must be documented, reviewed and approved using the SPDR form. - For changes to the OSSP, and/or PSSP, the SPDR and LOGSPDR performs the role of, and substitutes for, the configuration change request forms and associated process (forms CCR and LOGCCR). |
| Header | - Enter your name, date, and organization. - Provide the current project name and launch/phase the project is in. |
| SPDR Number | Use for your own identification purposes. |
| SPDR Title | Create title for SPDR. |
| Deviation Request Information | - List all parts of the OSSP or PSSP impacted by this deviation request. - Provide rational for deviation, including expected benefits. - Describe what metrics and/or criteria will be used to evaluate the effectiveness and/or determine if a PIP will be submitted to modify the OSSP. |
| When Completed | After you have completed the SPDR, keep a copy and submit a copy to your team’s process manager. |
| Process Manager | - Review the SPDR. - Evaluate the SPDR for completeness. If incomplete return for more information. - Compare the SPDR to other SPDRs to ensure no conflicts have occurred. If conflicts are detected, review conflicted SPDRs with originators for resolution. If originators cannot agree on resolution, take SPDRs to team for final resolution. - Compare SPDR to the team’s goals to ensure that SPDR does not inadvertently prevent the team from accomplishing its objectives. If conflicts are detected, review conflict with SPDR’s originator for resolution. If resolution cannot be found, take SPDR to team for final resolution. - Record any relevant comments. - Sign and date approval line. - Forward SPDR to process group for approval. |
| Process Group (PG) | - Review the SPDR. - Evaluate the SPDR for completeness. If incomplete, return to process manager for more information. - Enter SPDR into LOGSPDR and allocate unique SPDR Control No. - Enter date received. - Compare the SPDR to the organization’s business goals and objectives. If conflicts are detected, review conflict with SPDR’s originator and process manager for resolution. If resolution cannot be found, take SPDR to team lead and management for final resolution. - Record any relevant comments. - Sign and date approval line. - Obtain management approval. - Enter date approved. - Inform process manager of approval. - Track status of SPDR to closure (Disapproved or Evaluated). |

| TSP+ Stakeholder Role Assignment Matrix Form – Form SRAM |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- |
| Organization |  |  |  |  |  | Page Number |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| Roles | Management |  |  | Team Lead | Customer Interface Manager | Design Manager | Implementation Manager | Planning Manager | Process Manager | Support Manager | Quality Manager | Test Manager | TSP Team | Team Member | PG Team |  | PG Planning Manager | PG Support Manager | PG Process Manager | PG Implementation Manager | PG Quality Manager | PG Coaching Manager / Lead TSP Coach | PG Process Asset and Data Repository Manager | PG Training Manager | TSP Coach | PSP Instructor | Configuration Control Board | Product Owner | Course Instructor | Role Manager Team |  |
| Name |  | Leadership Team | Customer / Marketing |  |  |  |  |  |  |  |  |  |  |  |  | PG Team Lead |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |

TSP+ Stakeholder Role Assignment Matrix Form Instructions – Form SRAM

| Purpose | To provide a mechanism for assigning roles identified in the relevant stakeholder involvement matrix (form RSIM) to individuals |
| --- | --- |
| General | - The matrix must be assessed periodically to ensure that it meets the immediate needs of the organization and its projects. - A description of most roles can be found in the role specification (specification ROLE). - Type of role involvement is identified in the relevant stakeholder involvement matrix (form RSIM). - Note that this form is typically used as a template in a spreadsheet or database. - The team leader will (1) periodically review the SRAM with teams, projects, the process group and management for completeness and approval, (2) make changes as required, (3) ensure that SRAM is placed under appropriate levels of control, and (4) distribute the latest version of the SRAM to all individuals listed in the matrix. |
| Header | Enter the project’s name and page number. |
| Roles | List all organizational and project specific roles as listed in the Relevant Stakeholder Involvement Matrix (form RSIM). |
| Name | - List all relevant stakeholders assigned to the project. - For each individual listed determine which roles the individual is performing by entering a “P” or “B” in the corresponding row and column for Primary or Backup respectively. - In the event that an individual does not map to any role, reevaluate the Relevant Stakeholder Involvement Matrix (form RSIM) for completeness or consider removing the individual from the project’s stakeholder role assignment matrix (SRAM). - Note: not all roles will be assigned a backup. |

TSP Strategy Recording - Form STRAT

| Name |  | Date |  |
| --- | --- | --- | --- |
| Project |  | Launch/Phase |  |

|  |  | Cycle LOC |  |  | Cycle Hours |  |  |
| --- | --- | --- | --- | --- | --- | --- | --- |
| Ref. | Component, Element, or Feature | 1 | 2 | 3 | 1 | 2 | 3 |
| Totals |  |  |  |  |  |  |  |

TSP Strategy Recording Instructions - STRAT

| Purpose | - Use this form to record strategic decisions. - Use it during strategy development to allocate product functions to development cycles. - Also use it during high-level design to allocate SRS functions to components. |
| --- | --- |
| General | - This form provides a way to record strategic decisions. Use it or any other format that contains the same data. - If you need space for more functions or cycles, use additional form copies. - This form is used only when a tool with equivalent functionality, features, or purpose is not available. |
| Header | Enter your name, project name, launch phase, and date. |
| Reference | Use this column to list the need statement, SRS paragraph, sentence number, or other reference for the functions. |
| Component, Element, or Feature | In this column, list the principal product components, elements, or features to be included in the product in each development cycle. |
| Cycle LOC | - Use these columns for the estimated LOC or other size measure for each function. - Enter the size estimated for each function under the number of the development cycle that will include that function. - If you plan to implement a function partially in two or more cycles, enter the estimated new and changed size for each cycle. |
| Cycle Hours | - Use these columns for the estimated time required to develop each function. - Enter the time estimated for each function under the number of the cycle where you plan to include that function. - If you plan to implement a function partially in two or more cycles, enter the estimated development time for each cycle. |

| TSP Defects Injected Summary - Form SUMDI Plan |  |
| --- | --- |
| Bottom-up Plan |  |
| Actual |  |

| Name |  | Date |  |
| --- | --- | --- | --- |
| Project |  | Launch/Phase |  |
| Assembly |  | Part Level |  |

| Phase Parts |  | Requirements |  | Requirements Inspection |  | High-level Design |  | HLD Inspection |  | Detailed Design |  | Detailed Design Review |  | Detailed Design Inspection |  | Code |  | Code Review |  | Compile |  | Code Inspection |  | Unit Test |  | Build and Integration |  | System Test |
| --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- |
| Total |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |

TSP Defects Injected Summary Instructions - Form SUMDI

| Purpose | - This form summarizes the data for estimated and actual defects injected. - At the lowest level, it holds summaries of all the module data in a product or product component. - At higher levels, it holds summaries of all the component data in a product, all the product data in a sub-system, or all the sub-system data in an overall system. |
| --- | --- |
| General | - Use this form to record the defect-injected data from a number of modules, components, products, or sub-systems. - The totals from this form are used to complete the defects-injected entries in the next higher-level plan summary. - This form is used only when a tool with equivalent functionality, features, or purpose is not available. - In such cases, the number of rows is variable, depending on the number of modules, components, products, or sub-systems. |
| Plan/Bottom-up Plan/Actual | Check whether the form is for plan, bottom-up plan, or actual data. - Plan: use when recording estimates in top-level planning. - Bottom-up plan: use when rolling up estimates from lower-level parts plans to assembly-level plans. - Actual: use for entering or rolling up actual data. |
| Header | - Enter your name, project name, part or assembly name, launch phase, and date. - Assembly level specifies the level of this part: module, component, product, sub-system, or system. |
| Phase | The phases of the development process are listed across the top of the form. |
| Parts | List the name or number of each module, component, product, or subsystem in the left column. |
| Columns | Under each phase heading, enter, for each part, the number of defects injected in that phase. |
| Total | At the bottom of the form, enter the totals of the defects injected in all the parts in that phase. |

| TSP Defects Removed Summary - Form SUMDR Plan |  |
| --- | --- |
| Bottom-up Plan |  |
| Actual |  |

| Name |  | Date |  |
| --- | --- | --- | --- |
| Project |  | Launch/Phase |  |
| Assembly |  | Part Level |  |

| Phase Parts |  | Requirements |  | Requirements Inspection |  | High-level Design |  | HLD Inspection |  | Detailed Design |  | Detailed Design Review |  | Detailed Design Inspection |  | Code |  | Code Review |  | Compile |  | Code Inspection |  | Unit Test |  | Build and Integration |  | System Test |
| --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- |
| Total |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |

TSP Defects Removed Summary Instructions - Form SUMDR

| Purpose | - This form summarizes the data for estimated and actual defects removed. - At the lowest level, it holds summaries of all the module data in a product or product component. - At higher levels, it holds summaries of all the component data in a product, all the product data in a sub-system, or all the sub-system data in an overall system. |
| --- | --- |
| General | - Use this form to record the defect-removed data from a number of modules, components, products, or sub-systems. - The totals from this form are used to complete the defects-removed entries in the next higher-level plan summary. - This form is used only when a tool with equivalent functionality, features, or purpose is not available. - In such cases, the number of rows is variable, depending on the number of modules, components, products, or sub-systems. |
| Plan/Bottom-up Plan/Actual | Check whether the form is for plan, bottom-up plan, or actual data. - Plan: use when recording estimates in top-level planning. - Bottom-up plan: use when rolling up estimates from lower-level parts plans to assembly-level plans. - Actual: use for entering or rolling up actual data. |
| Header | - Enter your name, project name, part or assembly name, launch phase, and date. - Assembly level specifies the level of this part: module, component, product, sub-system, or system. |
| Phase | The phases of the development process are listed across the top of the form. |
| Parts | List the name or number of each module, component, product, or subsystem in the left column. |
| Columns | Under each phase heading, enter, for each part, the number of defects removed in that phase. |
| Total | At the bottom of the form, enter the totals of the defects removed in all the parts in that phase. |

TSP Plan Summary - Form SUMP

| Name |  | Date |  |
| --- | --- | --- | --- |
| Project |  | Launch/Phase |  |
| Part/Assembly |  | Assembly Level |  |

| Summary | Plan |  |  |  | Actual |  |  |
| --- | --- | --- | --- | --- | --- | --- | --- |
| CPI(Cost-Performance Index) |  |  |  |  |  |  |  |
| LOC/Hour |  |  |  |  |  |  |  |
| % Reuse (% of Total LOC - T) |  |  |  |  |  |  |  |
| % New Reuse (% of N&C LOC - N) |  |  |  |  |  |  |  |
| Product Size | Plan |  |  |  | Actual |  |  |
| Requirements pages (SRS) |  |  |  |  |  |  |  |
| High-level design pages (SDS) |  |  |  |  |  |  |  |
| Detailed design lines |  |  |  |  |  |  |  |
| Base LOC (B) (measured) |  |  |  |  |  |  |  |
| Deleted LOC (D) |  |  |  |  |  |  |  |
|  | (Estimated) |  |  |  | (Counted) |  |  |
| Modified LOC (M) |  |  |  |  |  |  |  |
|  | (Estimated) |  |  |  | (Counted) |  |  |
| Added LOC (A) |  |  |  |  |  |  |  |
|  | (N-M) |  |  |  | (T-B+D-R) |  |  |
| Reused LOC (R) |  |  |  |  |  |  |  |
|  | (Estimated) |  |  |  | (Counted) |  |  |
| Total New & Changed LOC (N) |  |  |  |  |  |  |  |
|  | (Estimated) |  |  |  | (A+M) |  |  |
| Total LOC (T) |  |  |  |  |  |  |  |
|  | (N+B-M-D+R) |  |  |  | (Measured) |  |  |
| Total New Reuse LOC |  |  |  |  |  |  |  |
| Estimated Object LOC (E) |  |  |  |  |  |  |  |
| Size UPI (70%) |  |  |  |  |  |  |  |
| Size LPI (70%) |  |  |  |  |  |  |  |
| Time in Phase (hours) | Plan |  | Actual |  |  |  | Actual % |
| Launch and planning |  |  |  |  |  |  |  |
| Requirements |  |  |  |  |  |  |  |
| System test plan |  |  |  |  |  |  |  |
| Requirements inspection |  |  |  |  |  |  |  |
| Relaunch and planning |  |  |  |  |  |  |  |
| High-level design |  |  |  |  |  |  |  |
| Integration test plan |  |  |  |  |  |  |  |
| High-level design inspection |  |  |  |  |  |  |  |
| Relaunch and planning |  |  |  |  |  |  |  |
| Detailed design |  |  |  |  |  |  |  |
| Detailed design review |  |  |  |  |  |  |  |
| Test development |  |  |  |  |  |  |  |
| Detailed design inspection |  |  |  |  |  |  |  |
| Code |  |  |  |  |  |  |  |
| Code review |  |  |  |  |  |  |  |
| Compile |  |  |  |  |  |  |  |
| Code inspection |  |  |  |  |  |  |  |
| Unit test |  |  |  |  |  |  |  |

(continued on next page)

TSP Plan Summary - Form SUMP (continued)

| Part/Assembly |  | Date |  |
| --- | --- | --- | --- |

| Time in Phase (hours) (Continued) | Plan |  | Actual |  | Actual % |
| --- | --- | --- | --- | --- | --- |
| Relaunch and planning |  |  |  |  |  |
| Build and integration |  |  |  |  |  |
| System test |  |  |  |  |  |
| Postmortem |  |  |  |  |  |
| Total |  |  |  |  |  |
| Time UPI (70%) |  |  |  |  |  |
| Time LPI (70%) |  |  |  |  |  |
| Defects Injected | Plan |  | Actual |  | Actual % |
| Requirements |  |  |  |  |  |
| Requirements inspection |  |  |  |  |  |
| High-level design |  |  |  |  |  |
| High-level design inspection |  |  |  |  |  |
| Detailed design |  |  |  |  |  |
| Detailed design review |  |  |  |  |  |
| Detailed design inspection |  |  |  |  |  |
| Code |  |  |  |  |  |
| Code review |  |  |  |  |  |
| Compile |  |  |  |  |  |
| Code inspection |  |  |  |  |  |
| Unit Test |  |  |  |  |  |
| Build and integration |  |  |  |  |  |
| System test |  |  |  |  |  |
| Total Development |  |  |  |  |  |
| Defects Removed | Plan |  | Actual |  | Actual % |
| Requirements |  |  |  |  |  |
| System test planning |  |  |  |  |  |
| Requirements inspection |  |  |  |  |  |
| High-level design |  |  |  |  |  |
| Integration test planning |  |  |  |  |  |
| High-level design inspection |  |  |  |  |  |
| Detailed design |  |  |  |  |  |
| Detailed design review |  |  |  |  |  |
| Test development |  |  |  |  |  |
| Detailed design inspection |  |  |  |  |  |
| Code |  |  |  |  |  |
| Code review |  |  |  |  |  |
| Compile |  |  |  |  |  |
| Code inspection |  |  |  |  |  |
| Unit Test |  |  |  |  |  |
| Build and integration |  |  |  |  |  |
| System test |  |  |  |  |  |
| Total Development |  |  |  |  |  |
| Acceptance test |  |  |  |  |  |
| Product life |  |  |  |  |  |

TSP Plan Summary Instructions – Form SUMP

| Purpose | - This form holds plan and actual data for parts or assemblies. - An assembly could be a system with multiple products, a product with multiple components, or a component with multiple modules. - A part could be a module, component, or product. - Note: the lowest-level parts or modules typically have no system-level data (i.e. requirements, high-level design, or system test). |
| --- | --- |
| General | - Where possible, make estimates based on your own historical data. - Where data are not available, use the PLAN standard for guidance. - This form is used only when a tool with equivalent functionality, features, or purpose is not available. |
| Header | - Enter your name, project name, part or assembly name, launch phase, and date. - Assembly level specifies the level of this part: module, component, product, sub-system, or system. |
| Summary | - For CPI, use the sums of planned and actual development times for all products developed in this system to date. - Enter the new and changed LOC per hour planned, the actual for this product, and the rate for all products at this level to date. - CPI = (To Date Planned Time)/(To Date Actual Time). - Reuse percent is reuse LOC as a percent of total LOC. - New Reuse percent is new reuse LOC as a percent of new and changed LOC. |
| Product Size | - For text and designs, enter only the new and changed size data. - For program parts or assemblies, enter all the indicated LOC data. |
| Time in Phase | - Enter estimated and actual time by phase. - For higher-level assemblies, enter the sums of the plan and actual times for the parts (from SUMT). - For the lowest-level parts, these values come from the TASK template. - Actual Percent: Enter the percent of the actual development time by phase. |
| Defects Injected | - Enter estimated and actual defects injected by phase from form SUMDI. - For assemblies, enter the total of the plan and actual defects injected for its parts. For modules, enter the defect data directly. - Make the defect estimates while producing the quality plan. - Actual Percent: Enter the percent of the actual defects injected by phase. |
| Defects Removed | - Enter estimated and actual defects removed by phase from form SUMDR. - For assemblies, enter the total of the plan and actual defects removed for its parts. For modules, enter the defect data directly. - Make the defect estimates while producing the quality plan. - Actual Percent: Enter the percent of the actual defects removed by phase. |

TSP+ Standard Process Deviation Summary - Form SUMPD

| Organization |  | Date |  |
| --- | --- | --- | --- |
| Project |  | Launch/Phase |  |

| No. | Standard Process Impacted | Proposed Change | Rationale |
| --- | --- | --- | --- |

TSP+ Standard Process Deviation Summary Instructions - Form SUMPD

| Purpose | This form summarizes the proposed deviations to the project’s standard set of processes (PSSP). |
| --- | --- |
| General | - Use this form to record recommended changes or deviations to the PSSP, based on project requirements during both launch/relaunch preparations and launch/relaunch meeting 3 (LAU3). - Note that this form is typically used as a template in a spreadsheet or database. |
| Header | - Enter name of organization and date of SUMPD creation. - Provide the current project name and launch/phase the project is in. |
| Reference # | Use for your own identification purposes. |
| Standard Process Impacted | List Script(s), Form(s), Specification(s), Guideline(s), Instruction(s) and Checklist(s) effected by the proposed change. |
| Proposed Change | Briefly describe the proposed change to the PSSP. |
| Rationale | Provide a brief rationale for making changes to the PSSP. |

TSP Quality Summary - Form SUMQ

| Name |  | Date |  |
| --- | --- | --- | --- |
| Project |  | Launch/Phase |  |
| Part/Assembly |  | Assembly Level |  |

| Percent Defect Free | Plan |  | Actual |
| --- | --- | --- | --- |
| In compile |  |  |  |
| In unit test |  |  |  |
| In integration test |  |  |  |
| In system test |  |  |  |
| In acceptance test |  |  |  |
| In one year of use |  |  |  |
| In product life |  |  |  |
| Defect/Page |  |  |  |
| Requirements inspection |  |  |  |
| HLD review |  |  |  |
| HLD inspection |  |  |  |
| Defects/KLOC |  |  |  |
| DLD review |  |  |  |
| DLD inspection |  |  |  |
| Code review |  |  |  |
| Compile |  |  |  |
| Code inspection |  |  |  |
| Unit test |  |  |  |
| Build and integration |  |  |  |
| System test |  |  |  |
| Total development |  |  |  |
| Acceptance test |  |  |  |
| Product life |  |  |  |
| Total |  |  |  |
| Defect Ratios |  |  |  |
| Code review/Compile |  |  |  |
| DLD review/Unit test |  |  |  |
| Development Time Ratios (%) |  |  |  |
| Requirements inspection/Req. time |  |  |  |
| HLD inspection/HLD time |  |  |  |
| DLD/code |  |  |  |
| DLD review/design |  |  |  |
| Code review/code |  |  |  |
| A/FR |  |  |  |
| Personal Review Rates |  |  |  |
| DLD lines/hour |  |  |  |
| Code LOC/hour |  |  |  |
| Inspection Rates |  |  |  |
| Requirement pages/hour |  |  |  |
| HLD pages/hour |  |  |  |
| DLD lines/hour |  |  |  |
| Code LOC/hour |  |  |  |

(continued on next page)

TSP Quality Summary - Form SUMQ (continued)

| Part/Assembly |  | Date |  |
| --- | --- | --- | --- |

| Defect Injection Rates | Plan |  | Actual |
| --- | --- | --- | --- |
| Requirements |  |  |  |
| HLD |  |  |  |
| DLD |  |  |  |
| Coding |  |  |  |
| Compile |  |  |  |
| Unit test |  |  |  |
| Build and integration |  |  |  |
| System test |  |  |  |
| Defect Removal Rates | Plan |  | Actual |
| Requirements |  |  |  |
| System test planning |  |  |  |
| Requirements inspection |  |  |  |
| HLD |  |  |  |
| Integration test planning |  |  |  |
| HLD inspection |  |  |  |
| DLD review |  |  |  |
| Test development |  |  |  |
| DLD inspection |  |  |  |
| Code |  |  |  |
| Code review |  |  |  |
| Compile |  |  |  |
| Code inspection |  |  |  |
| Unit test |  |  |  |
| Build and integration |  |  |  |
| System test |  |  |  |
| Phase Yields | Plan |  | Actual |
| Requirements inspection |  |  |  |
| HLD inspection |  |  |  |
| DLD review |  |  |  |
| DLD inspection |  |  |  |
| Code review |  |  |  |
| Compile |  |  |  |
| Code inspection |  |  |  |
| Unit test |  |  |  |
| Build and integration |  |  |  |
| System test |  |  |  |
| Process Yields | Plan |  | Actual |
| % before compile |  |  |  |
| % before unit test |  |  |  |
| % before build and integration |  |  |  |
| % before system test |  |  |  |
| % before system delivery |  |  |  |

TSP Quality Summary Instructions – Form SUMQ

| Purpose | - This form holds plan and actual quality data for parts or assemblies. - An assembly could be a system with multiple products, a product with multiple components, or a component with multiple modules. - A part could be a module, component, or product. - Note: the lowest-level parts or modules typically have no system-level data (i.e., requirements, high-level design, or system test). |
| --- | --- |
| General | - Where possible, establish goals based on your own historical data. - Where data are not available, use the QUAL standard for guidance. - In planning, follow script LAU5 to make the quality plan. - This form is used only when a tool with equivalent functionality, features, or purpose is not available. |
| Header | - Enter your name, project name, part or assembly name, launch phase, and date. - Assembly level specifies the level of this part: module, component, product, sub-system, or system. |
| Percent Defect Free (PDF) | - Set the percent defect free (PDF) plan values in the project launch. - At phase completion, enter the actual PDF values. - PDF does not apply to modules or lowest-level parts. - For program assemblies, compute PDF from form SUMDR. |
| Defects/page and Defects/KLOC | - Set the defect/page and defect/KLOC plan values in the launch. - After development, calculate the actual values. For modules, calculate directly; for assemblies, calculate from the forms SUMS and SUMDR. |
| Defect Ratios | - From the defects/KLOC values, calculate the defect ratios. - When compile or unit test defects are 0, enter "inf." |
| %Development Time Ratios | - Calculate the planned and actual ratios from form SUMP. - During development, monitor these planned and actual ratios to ensure the work meets the team quality goals. |
| A/FR | - For A/FR, use detailed design and code review and inspection times divided by compile and unit test times. - Use the sum of personal review and team inspection times. |
| Review and Inspection Rates | - From forms SUMT and SUMS, calculate the indicated planned or actual review and inspection rates. - During development, monitor these planned and actual rates to ensure that the work meets the team quality goals. |
| Defect Injection and Removal Rates | - Based on the quality plan, establish standard team rates. - As you gather actual data, compute the actual defect injection and removal rates for each phase. - For modules, compute the values directly. - For larger program assemblies, compute the values from the forms SUMT, SUMDI, and SUMDR. |
| Yield | - In planning, use historical data to estimate the yield values needed for each defect-removal phase. - After each phase, calculate the estimated yield values. - Update these values as development progresses. - For modules, compute the yield values directly. - For larger program assemblies, compute the yield values from SUMDI and SUMDR. |

| TSP Product Size Summary - Form SUMS Plan |  |
| --- | --- |
| Bottom-up Plan |  |
| Actual |  |

| Name |  | Date |  |
| --- | --- | --- | --- |
| Project |  | Launch/Phase |  |
| Assembly |  | Part Level |  |

|  |  |  |  | Size Category |
| --- | --- | --- | --- | --- |

| Product or Part Names |  | Size Measure |  | Base |  | Deleted |  | Modified |  | Added |  | Reused |  | New and Changed |  | Total |  | Total New Reuse |
| --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- |
| Totals |  | Text Pages |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
|  |  | HLD Pages |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
|  |  | DLD Lines |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
|  |  | LOC |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |

TSP Product Size Summary Instructions - Form SUMS

| Purpose | - This form summarizes the data for program size. - At the lowest level, it holds summaries of all the module data in a product or product component. - At higher levels, it holds summaries of all the component data in a product, all the product data in a sub-system, or all the sub-system data in an overall system. |
| --- | --- |
| General | - Use this form to record the size data for a number of modules, components, products, or sub-systems. - The totals from this form are used to complete the size entries in the next higher-level plan summary. - This form is used only when a tool with equivalent functionality, features, or purpose is not available. - In such cases, the number of rows is variable, depending on the number of modules, components, products, or sub-systems. |
| Plan/Bottom-up Plan/Actual | Check whether the form is for plan, bottom-up plan, or actual data. - Plan: use when recording estimates in top-level planning. - Bottom-up plan: use when rolling up estimates from lower-level parts plans to assembly-level plans. - Actual: use for entering or rolling up actual data. |
| Header | - Enter your name, the date, project, and launch phase. - Name the assembly that contains these parts. - For part level, enter whether module, component, product, or sub-system data are summarized in the form. |
| Product or Part Names | List the name or number of each module, component, or other product in the left column. |
| Size Measure | - Enter the size measure for the product in each row. - Example measures are text pages, HLD pages, DLD pseudocode lines, and LOC. |
| Size Category | - For planned size, under each size category, for each part - Enter the estimated Base, Deleted, Modified, Added, Reused, and Total New Reuse size. - Calculate New and Changed size (Added + Modified) categories. - Calculate the Total size (Base - Deleted + Added + Reused). - For actual size, under each size category, for each part - Measure and enter the estimated Base, Deleted, Modified, Added, Reused, and Total New Reuse size. - Calculate New and Changed size (Added + Modified) categories. - Calculate the Total size (Base - Deleted + Added + Reused). |
| Total | - At the bottom of the form, enter the totals of each size measure. - Be careful not to double count the base size measure when several parts have been developed from the same base. - Also, when products are developed in cycles, check that the base or reused code are not double counted. |

| TSP Development Time Summary - Form SUMT Plan |  |
| --- | --- |
| Bottom-up Plan |  |
| Actual |  |

| Name |  |  | Date |  |  |  |  |  |
| --- | --- | --- | --- | --- | --- | --- | --- | --- |
| Project |  |  | Launch/Phase |  |  |  |  |  |
| Assembly |  |  |  | Part Level |  |  |  |  |

| Phase Parts |  | Launch and Planning |  | Requirements |  | System Test Planning |  | Requirements Inspection |  | Relaunch |  | High-level Design |  | Integration Test Planning |  | HLD Inspection |  | Relaunch |  | Detailed Design |  | Detailed Design Review |  | Test Development |  | Detailed Design Inspection |  | Code |  | Code Review |  | Compile |  | Code Inspection |  | Unit Test |  | Relaunch |  | Build and Integration |  | System Test |  | Postmortem |
| --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- |
| Total |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |

TSP Development Time Summary Instructions - Form SUMT

| Purpose | - This form summarizes the data for estimated and actual development time. - At the lowest level, it holds summaries of all the module data in a product or product component. - At higher levels, it holds summaries of all the component data in a product, all the product data in a sub-system, or all the sub-system data in an overall system. |
| --- | --- |
| General | - Use this form to record the development time data for a number of modules, components, products, or sub-systems. - The totals from this form are used to complete the phase time entries in the next higher-level plan summary. - This form is used only when a tool with equivalent functionality, features, or purpose is not available. - In such cases, the number of rows is variable, depending on the number of modules, components, products, or sub-systems. |
| Header | - Enter your name, project name, part or assembly name, launch phase, and date. - Assembly level specifies the level of this part: module, component, product, sub-system, or system. |
| Plan/Bottom-up Plan/Actual | Check whether the form is for plan, bottom-up plan, or actual data. - Plan: use when recording estimates in top-level planning. - Bottom-up plan: use when rolling up estimates from lower-level parts plans to assembly-level plans. - Actual: use for entering or rolling up actual data. |
| Phase | The phases of the development process are listed across the top of the form. |
| Parts | List the name or number of each module, component, product, or subsystem part in the left column. |
| Columns | Under each phase heading, enter, for each part, the plan or actual time for that development phase. |
| Total | At the bottom of the form, enter the total development time for all parts in that phase. |

TSP Task Plan Summary - Form SUMTASK

| Name |  | Date |  |
| --- | --- | --- | --- |
| Project |  | Launch/Phase |  |
| Part/Assembly |  | Assembly Level |  |

| Products of the task |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- |
| Task users/customers |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| Overall requirements/message |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| Specifications/constraints |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| Product Elements |  | Size Unit |  |  |  |  | Plan Units |  |  |  |  | Plan Rate |  |  |  |  | Plan Time |  |  |  |  |  |  | Act. Units |  |  |  | Act. Time |  |  |  |  |  |  |  |  | Act. Rate |  |  |
| Total |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| Time in Phase |  |  |  | Plan |  |  |  |  |  |  |  |  |  | Actual |  |  |  |  |  |  |  |  | % |  |  |  |  |  |  |  |  | Base Times |  |  |  |  |  |  |  |
| Planning |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| Research |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| Outline/High-level design |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| Peer review and correct |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| Draft/Detailed-level design |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| Design review |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| Peer review and correct |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| Implement/Rewrite |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| Review |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| Peer review and correct |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| Test/Trial use |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| Postmortem |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| Total time (minutes) |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| Total time (hours) |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |

TSP Task Plan Summary Instructions - Form SUMTASK

| Purpose | - To facilitate planning and tracking task activities - Use this form for tasks that take more than about 10 hours. - This form is for those general tasks which are large enough to warrant detailed project plan summaries. |
| --- | --- |
| General | This form is used only when a tool with equivalent functionality, features, or purpose is not available. |
| Header | - Enter your name, project name, part or assembly name, launch phase, and date. - Assembly level specifies the level of this part: module, component, product, sub-system, or system. |
| Product of the Task | Describe the product to be produced by this task: i.e., test scripts, requirements documents, database designs, etc. |
| Task Users/Customers | - Note who will use or be the customer for this product. - For example, if it is a process, the team will use, list "team." |
| Overall Requirements/ Message | - Briefly list the product requirements. - If the product is a document, give a brief outline of the principal topics or document sections. - For a process, list its principal steps and elements. |
| Specifications/ Constraints | - Summarize any special task or product constraints. - For example: prerequisites, page limits, number of slides, etc. |
| Product Elements | - List the various product elements to be produced. - Give the size unit for each element type. - Estimate the development rate in minutes per unit. - Estimate the new and changed units per element type and the time. - Record the actual units, time, and rate when done. |
| Time in Phase | - Record the plan and actual times for the task phases. - Where some phases are not appropriate or differ from those in the form, make appropriate changes. |
| % and Base | When your personal plan contains tasks of more than 10 hours, use % and Base Times columns to divide tasks into smaller steps. |
| Percent (%) | The percent of time you typically plan for each task phase. |
| Base Times | - Using the phase % values, allocate the original total estimated task time among the phases. - Since the base times add up to the original estimate, using these values will preserve the original earned value plan. |
| Example | Suppose, during the launch, you planned a task to take 30 hours, and had not then divided it into smaller time steps. - You now estimate the task to take 50 hours. - Your current phase estimates in hours are planning: 2, research: 10, design: 5, implementation: 12, review: 6, peer review: 8, trial: 6, and postmortem: 1. - These percents are respectively 4, 20, 10, 24, 12, 16, 12, 2. - In “Base Times”, enter 1.2 for planning (4*30/100), 3 for research (10*30/100), etc. - To preserve your earned value plan, enter new rows for these tasks and times and set the original 30 hour estimate to 0. |

TSP+ Training Survey Summary Form – Form SUMTRNS

| Course Title |  |  |  |  |  |  |  |  |  |
| --- | --- | --- | --- | --- | --- | --- | --- | --- | --- |
| Instructor(s) |  |  |  |  |  |  |  |  |  |
| Date(s) |  |  |  |  |  |  |  |  |  |
| No. of Attendees |  |  |  |  | No. of Responses |  | Response Rate |  |  |

| Content / Instruction How would you rate: | Excellent (4) | Good (3) | Fair (2) | Poor (1) | N/A | Total | Total Possible | Rating |
| --- | --- | --- | --- | --- | --- | --- | --- | --- |
| the contents of the course |  |  |  |  |  |  |  |  |
| the organization of the course materials |  |  |  |  |  |  |  |  |
| the quality of the instruction |  |  |  |  |  |  |  |  |
| your current understanding of the material covered |  |  |  |  |  |  |  |  |
| how well the course matched its stated goals and objectives |  |  |  |  |  |  |  |  |
| the quality of the exercised (if applicable) |  |  |  |  |  |  |  |  |
| Subtotal |  |  |  |  |  |  |  |  |

| Relevance How much of the subject matter was: | >80% (4) | >50 % (3) | <50% (2) | <20% (1) | N/A | Total | Total Possible | Rating |
| --- | --- | --- | --- | --- | --- | --- | --- | --- |
| important/relevant to your job |  |  |  |  |  |  |  |  |
| Subtotal |  |  |  |  |  |  |  |  |

| Length / Questions How would you rate: | Too Much (1) | (2) | About Right (3) | (2) | Too Little (1) | N/A | Total | Total Possible | Rating |
| --- | --- | --- | --- | --- | --- | --- | --- | --- | --- |
| length of time for the course |  |  |  |  |  |  |  |  |  |
| amount of material covered |  |  |  |  |  |  |  |  |  |
| depth of material covered |  |  |  |  |  |  |  |  |  |
| individual/”hands on” learning |  |  |  |  |  |  |  |  |  |
| group exercises |  |  |  |  |  |  |  |  |  |
| direct interaction with instructors |  |  |  |  |  |  |  |  |  |
| asking questions |  |  |  |  |  |  |  |  |  |
| breaks/intermissions |  |  |  |  |  |  |  |  |  |
| testing your understanding of the content |  |  |  |  |  |  |  |  |  |
| Subtotal |  |  |  |  |  |  |  |  |  |

(continued on next page)

TSP+ Training Survey Summary Form – Form SUMTRNS (continued)

| Instructional Material Was the instructional material: | Often (5) | (4) | Sometimes (3) | (2) | Rarely (1) | N/A | Total | Total Possible | Rating |
| --- | --- | --- | --- | --- | --- | --- | --- | --- | --- |
| easy to understand |  |  |  |  |  |  |  |  |  |
| complete |  |  |  |  |  |  |  |  |  |
| well-designed |  |  |  |  |  |  |  |  |  |
| relevant to the course |  |  |  |  |  |  |  |  |  |
| Subtotal |  |  |  |  |  |  |  |  |  |

Best aspects of the course

Worst aspects of the course

How can the course be improved to better satisfy student needs?

Additional comments

TSP+ Training Survey Summary Form Instructions – Form SUMTRNS

| Purpose | To provide a consistent way of measuring the effectiveness of training provided. |
| --- | --- |
| General | The training manager must distribute and collect training surveys (form TRNSUR) as input into generating training summary information. Note that this form is typically used as a template in a spreadsheet or database. |
| Header | - Enter name of the course being taught. - Enter instructor(s) name(s). - Enter date course was conducted. - Enter the number of training attendees by counting the number of attendees listed on the course’s training sign in form (form TRNSI) - Enter the number of responses by counting the number of completed training survey forms (form TRNSUR) for the given course. - Calculate the survey response rate as a percentage. (Response Rate = 100 * (# of responses) /( # of attendees)) |
| Content / Instruction | - Count the number of Excellent, Good, Fair, Poor, and N/A responses for each of the questions and enter the number in the appropriate column and row. - Calculate the total for each question. (Total = (# of Excellent) * 4 + (# of Good) * 3 + (# of Fair) * 2 + (# of Poor) * 1) - Calculate the Total Possible for each question. (Total Possible = ((# of Excellent) + (# of Good) + (# of Fair) + (# of Poor)) * 4) - Calculate the Subtotal for each column. - Calculate the Content / Instruction rating as a percentage. (Rating = 100 * (Subtotal of Total) / (Subtotal of Total Possible)) |
| Relevance | - Count the number of >80%, >50%, <50%, <20%, and N/A responses for each of the questions and enter the number in the appropriate column and row. - Calculate the total for each question. (Total = (# of >80%) * 4 + (# of >50%) * 3 + (# of <50%) * 2 + (# of <20%) * 1) - Calculate the Total Possible for each question. (Total Possible = ((# of >80%) + (# of >50%) + (# of <50%) + (# of <20%)) * 4) - Calculate the Subtotal for each column. - Calculate the Relevance rating as a percentage. (Rating = 100 * (Subtotal of Total) / (Subtotal of Total Possible)) |
| Length / Questions | - Count the number of each response, on the Too Much to Too Little scale and N/A, for each of the questions and enter the number in the appropriate column and row. - Calculate the total for each question. (Total = (# of Too Much) *1 + (# of “(2)”) * 2 + (# of About Right) * 3 + (# of “(2)”) * 2 + (# of Too Little) * 1) - Calculate the Total Possible for each question. (Total Possible = ((# of Too Much) + (# of “(2)”) + (# of About Right) +(# of “(2)”) + (# of Too Little)) * 3) - Calculate the Subtotal for each column. - Calculate the Length / Questions rating as a percentage. (Rating = 100 * (Subtotal of Total) / (Subtotal of Total Possible)) |

(continued on next page)

TSP+ Training Survey Summary Form Instructions – Form SUMTRNS (continued)

| Instructional Material | - Count the number of each response, on the Often to Rarely scale and N/A, for each of the questions and enter the number in the appropriate column and row. - Calculate the total for each question. (Total = (# of Often) *5 + (# of “(4)”) * 4 + (# of Sometimes) * 3 + (# of “(2)”) * 2 + (# of Too Rarely) * 1) - Calculate the Total Possible for each question. (Total Possible = ((# of Often) + (# of “(4)”) + (# of Sometimes) +(# of “(2)”) + (# of Rarely)) * 5) - Calculate the Subtotal for each column. - Calculate the Instructional Material rating as a percentage. (Rating = 100 * (Subtotal of Total) / (Subtotal of Total Possible)) |
| --- | --- |
| Attendee Comments | - Copy any comments written on the surveys (form TRNSUR) into the appropriate section of the training summary (form SUMTRNS) |
| Training Manager | - Provide instructors with a copy of the completed survey results (form SUMTRNS). - Store a copy of the SUMTRNS, all completed TRNSURs, associated TRNSI(s) - Periodically review SUMTRNS results with Process Group and Management for consideration in future training improvements. |

TSP Task Planning Template - Form TASK

| Name |  | Date |  |
| --- | --- | --- | --- |
| Project |  | Launch/Phase |  |

| Task |  |  | Plan |  |  |  |  |  |  |  | Actual |  |  |
| --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- |
| Phase | Part | Task Name | Number of Team members | Hours | Cumulative Hours | Size Units | Size | Week No. | Planned Value - PV | Cumulative PV | Hours | Cumulative EV | Week No. |
| Totals |  |  |  |  |  |  |  |  |  |  |  |  |  |

TSP Task Planning Template Instructions - Form TASK

| Purpose | - To estimate the development time for each project task - To compute the planned value for each project task - To estimate the planned completion date for each task - To provide a basis for tracking schedule progress even when the tasks are not completed in the planned order |
| --- | --- |
| General | - Complete the SCHED and TASK templates together. - Expand this template or use multiple pages as needed. - Include every significant task. - Use task names and numbers that support the activity and are consistent with the project work breakdown structure. - This form is used only when a tool with equivalent functionality, features, or purpose is not available. |
| Header | Enter your name, project name, launch phase, and date. |
| Task | - Enter the project phase for each task. - Enter the product, part, or assembly to which the task relates. - Enter task names and/or numbers in the order in which you expect to complete them. - Select tasks that have explicit completion criteria, i.e., plan completed, program compiled and defects corrected, etc. |
| Plan: No. of Team members | Enter the number of team members who will equally share in this task. If their individual times will differ, use different task names. |
| Plan: Hours | Enter the total planned hours for each task. |
| Plan: Cumulative Hours | Enter the cumulative sum of the total planned hours. |
| Plan: Units | For each product produced, enter the units of the size measure, i.e., LOC, KLOC, pages, classes, scripts, etc. |
| Plan: Size | For each task, enter the size of the product produced, if any. |
| Plan Week | - On form SCHED, find the plan cumulative hours entry that equals or just exceeds each cumulative hours entry on this form. - The week number in that row of the form SCHED is the plan week number for the task on form TASK. - If several weeks on the schedule template have the same cumulative value, enter the earliest week number. - Pick the plan date as the Monday of the week during which completion for that task is planned. |
| Plan: Planned Value (PV) | - Total the planned hours for all tasks. - Find the percent each task's planned hours are of total hours. - Enter this percent as the planned value for each task. |
| Plan: Cumulative PV | Enter the cumulative sum of the planned values. |
| Actual: Hours | When a task is completed, enter the hours spent on the task. |
| Actual: Cumulative Earned Value (EV) | - Each week, total the EV for all completed tasks and enter that total beside the latest completed task. - Also enter the weekly and cumulative total EV on form SCHED. |
| Actual: Week No. | As a task is completed, enter the week number it was completed. |

TSP Test Log - Form TESTLOG

| Name |  | Date |  |
| --- | --- | --- | --- |
| Project |  | Launch/Phase |  |
| Part/Assembly |  | Assembly Level |  |

| Date |  | Test |  |  | Product |  | Start |  | Stop |  | Delta Time |  | Problems |
| --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- |
| Comments |  |  |  |  |  |  |  |  |  |  |  |  |  |
| Date |  | Test |  |  | Product |  | Start |  | Stop |  | Delta Time |  | Problems |
| Comments |  |  |  |  |  |  |  |  |  |  |  |  |  |
| Date |  | Test |  |  | Product |  | Start |  | Stop |  | Delta Time |  | Problems |
| Comments |  |  |  |  |  |  |  |  |  |  |  |  |  |
| Date |  | Test |  |  | Product |  | Start |  | Stop |  | Delta Time |  | Problems |
| Comments |  |  |  |  |  |  |  |  |  |  |  |  |  |
| Date |  | Test |  |  | Product |  | Start |  | Stop |  | Delta Time |  | Problems |
| Comments |  |  |  |  |  |  |  |  |  |  |  |  |  |
| Date |  | Test |  |  | Product |  | Start |  | Stop |  | Delta Time |  | Problems |
| Comments |  |  |  |  |  |  |  |  |  |  |  |  |  |
| Date |  | Test |  |  | Product |  | Start |  | Stop |  | Delta Time |  | Problems |
| Comments |  |  |  |  |  |  |  |  |  |  |  |  |  |
| Date |  | Test |  |  | Product |  | Start |  | Stop |  | Delta Time |  | Problems |
| Comments |  |  |  |  |  |  |  |  |  |  |  |  |  |

TSP Test Log Instructions – Form TESTLOG

| Purpose | - To report test data and results |
| --- | --- |
| General | - You need test data to improve the testing processes. - the tests run - how long they took to run - the numbers and types of defects found - You also need to demonstrate the benefits of a quality process. - the testing time required to produce a workable product - the numbers of defects found in the product - the relative costs of fixing defects in test as opposed to earlier in the development process - This form is used only when a tool with equivalent functionality, features, or purpose is not available. |
| Header | - Enter your name, project name, part or assembly name, launch phase, and date. - Assembly level specifies the level of this part: module, component, product, sub-system, or system. |
| Date | Enter the date each test was run. |
| Test | - Uniquely identify each test. - Use the same name or number as in the test plan. |
| Product | Name the product being tested. |
| Test Time | - Enter the test time. - Start: when the test was started - Stop: when the test was stopped, either because it finished successfully or it was interrupted for any program or test-related reason - Delta time: the time between starting and stopping the test. |
| Problems | - Enter the number of test problem reports. - If one or more problems is determined to be a defect, note that under comments. |
| Comments | - Briefly note the test results. For example - The test finished successfully - The test was completed, but the result was incorrect - The test failed with 3 problems, 1 defect - Where possible, give additional information on test results, test configuration, or anything else that would permit reproducing the test results. |

TSP+ Training Matrix Form – Form TRNM

| Organization |  | Page Number |  |
| --- | --- | --- | --- |

| Roles | Management | Leadership Team Member | Customer / Marketing | Team Lead | Customer Interface Manager | Design Manager | Implementation Manager | Planning Manager | Process Manager | Support Manager | Quality Manager | Test Manager | PG Team Lead | PG Planning Manager | PG Support Manager | PG Process Manager | PG Implementation Manager | PG Quality Manager | Coaching Manager / Lead TSP Coach | Process Asset Library Manager | Training Manager | Software Developer Team Member * | Other Team Member * | TSP Coach | PSP Instructor | Configuration Control Board Member |  |
| --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- |
| Skills, Courses, OJT Experience |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| TSP Executive Strategy Seminar | R | R | D | D |  |  |  |  |  |  |  |  | D |  |  |  |  |  | D |  |  |  |  |  |  | D |  |
| Leading a Development Team | D | R |  | R |  |  |  |  |  |  |  |  | R |  |  |  |  |  | D |  |  |  |  |  |  |  |  |
| PSP Fundamentals |  | D |  | D |  |  |  |  |  |  |  |  | D |  |  |  |  |  | R |  |  | R | D | R | R |  |  |
| PSP Advanced |  | D |  | D |  | R | R |  | R |  | R |  | D |  |  |  |  |  | R |  |  | D |  | R | R |  |  |
| Introduction to Personal Process or TSP Team Member Training |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  | R |  |  |  |  |
| PSP Instructor Training |  |  |  |  |  |  |  |  |  |  |  |  | D |  |  |  |  |  | R |  |  |  |  | D | R |  |  |
| TSP Coach Training |  |  |  |  |  |  |  |  |  |  |  |  | D |  |  |  |  |  | R |  |  |  |  | R | D |  |  |
| Introduction to CMMI | D | D | D | R |  |  |  |  | R |  |  |  | R | R | R | R | R | R | R | R | R | D | D | R | D |  |  |
| Intermediate Concepts of CMMI |  | D |  | D |  |  |  |  | D |  |  |  | R |  |  | R |  |  | D |  |  |  |  |  |  |  |  |
| Configuration Management |  |  |  |  |  |  |  |  |  | R |  |  |  |  | R |  |  |  |  |  |  |  |  |  |  | D |  |
| Test Methodologies |  |  |  |  |  |  |  |  |  |  |  | R |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| Training Coordination |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  | R |  |  |  |  |  |  |
| Lean Six Sigma |  |  |  |  |  |  |  |  |  |  |  |  | D | D | D | D | D | D | D |  |  |  |  | D |  |  |  |
| Etc. |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| * All members of a TSP-team or a PG TSP-team are considered a Software Developer Team Member or an Other Team Member in addition to other assigned roles. |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |

TSP+ Training Matrix Form Instructions – Form TRNM

| Purpose | The training matrix outlines the minimum required training for the primary roles within the organization and its projects. |
| --- | --- |
| General | - The training matrix and the training plan must be assessed periodically to ensure that it meets the immediate needs of the organization’s projects and the long term business objectives of the organization. - Note that the training matrix has been pre-populated with a minimal set of roles, skills, course, and on-the-job experiences as an example. Each organization and project must evaluate the example and tailor the matrix for completeness. - Note that this form is typically used as a template in a spreadsheet or database. |
| Header | Enter the organization’s name and page number. |
| Roles | List all organizational and project specific roles. |
| Skills, Course, OJT Experience | - List all organizational and project specific skill required to meeting project needs and the long term business objectives of the organization. - For each skill listed, determine if it is required or desired for each defined role by entering a “R” or “D”, respectively, in the corresponding row and column. |
| Training Manager | - Periodically review the TRNM with teams, projects, the process group and management for completeness and approval. - Make changes as required. - When changes are made, update all individual team member training logs (form LOGTRNM) to reflect changes made to the TRNM. - When changes are made, review all individual team member training logs (form LOGTRNM) to determine impact of changes to individuals. Notify affected individuals of new training requirements. |

TSP+ On-the-Job Training Form - Form TRNOJT

| Name |  |  | Date |  |
| --- | --- | --- | --- | --- |
| E-mail |  | Organization |  |  |
| Project |  | Launch/Phase |  |  |

| Course Title or Type of Training |  |  |  |  |  |  |  |  |  |  |  |  |
| --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- |
| Individual/Company who will Provide Training |  |  |  |  |  |  |  |  |  |  |  |  |
| Training Requirement Being Fulfilled? |  |  |  |  |  |  |  |  |  |  |  |  |
| Starting Date; Ending Date. Starting Time; Ending Time. |
| Course Description |  |  |  |  |  |  |  |  |  |  |  |  |
| Training Material (Attach any handouts, exercises, etc. provided during the training session.) |  |  |  |  |  |  |  |  |  |  |  |  |
| When completed and reviewed, submit to the Training Manager and keep a copy. |  |  |  |  |  |  |  |  |  |  |  |  |
| Do not write below this line. |  |  |  |  |  |  |  |  |  |  |  |  |
| Date Received |  |  |  |  |  | Approved |  |  | Denied |  |  |  |
| Comments/Information Needed/Reason Denied |  |  |  |  |  |  |  |  |  |  |  |  |
| Approvals |  |  |  |  |  |  |  |  |  |  |  |  |
| Training Manager |  |  |  |  |  |  |  |  |  | Date |  |  |
| Team Lead |  |  |  |  |  |  |  |  |  | Date |  |  |

TSP+ On-the-Job Training Form Instructions - Form TRNOJT

| Purpose | To provide a mechanism for documenting on-the-job, computer-based, or self-directed training in fulfillment of required or desired training |
| --- | --- |
| General | Any team member may request on-the-job training in fulfillment of required or desired training by filling out this form. Once the form has been completed, the form should be submitted to the training manager to obtain the necessary approvals. |
| Header | - Enter your name, date, e-mail and organization. - Provide the current project name and launch/phase the project is in. |
| Course Title | Enter the course title or type of training obtained |
| Provider of Training | Enter name of individual or company who provided the training. |
| Training Requirement being fulfilled? | Enter the name of the skills, courses or OJT experience, as listed in the Training Matrix (form TRNM), being fulfilled by this training. |
| Start and Ending Date and Time | - Enter the starting and ending date of the training. - Enter the starting and ending time of the training. |
| Course Description | - Enter a detailed description of the training course. - There must be enough information about the course to enable the approval authority to make an informed decision as to whether the training is sufficient. |
| Training Material | - Enter explanation of the training material or provide a copy of the training material used. - If training material is available, please attach the material to the form. |
| Training Manager | - Review the TRNOJT - Evaluate the TRNOJT for completeness. If incomplete return for more information. - Enter date received. - If concur that the on-the-job training meets the intent of the specified skills, courses, or OJT experience specified in the training matrix (form TRNM), sign and date approval line. - Obtain approval from team lead. - Inform requester of approval or denial. - If approved, update individual’s team member training log (form LOGTRNM). - Upon completion of on-the-job training, provide the individual with an evaluation form (form TRNSUR), in order to evaluate the effectiveness of the on-the-job training. Periodically review on-the-job training surveys collected with the process group and management for consideration in future training improvements. |

TSP+ Training Request Form - Form TRNR

| Name |  |  | Date |  |
| --- | --- | --- | --- | --- |
| E-mail |  | Organization |  |  |
| Project |  | Launch/Phase |  |  |

| Proposed Training Activity (Course Title) |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- |
| Proposed Date(s) |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| Number of students (if requesting internal training) |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| Length of Course |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| Source of Funding |  |  |  |  |  |  | Organization |  |  |  | Project |  |  |  | Other, specify |  |  |  |  |
| How will this training contribute to established goals? |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| Personal goals |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| Project goals |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| Organizational goals |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| How can this information be shared across the organization? |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| Is this part of a certification program? |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| (If so, list courses completed and remaining courses that need to be completed.) |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| When completed and reviewed, submit to the Training Manager and keep a copy. |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| Do not write below this line. |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| Date Received |  |  |  |  |  |  |  |  |  | Approved |  |  |  |  | Denied |  |  |  |  |
| TRNR Control # |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| Comments/Information Needed/Reason Denied |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| Approvals |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| Training Manager |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  | Date |  |  |  |
| Team Lead |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  | Date |  |  |  |

TSP+ Training Request Form Instructions - Form TRNR

| Purpose | To provide a way to request training in order to meet a project or organizational need. |
| --- | --- |
| General | Any team member may request internal or external training by filling out this form. Once the form has been completed, the form should be submitted to the training manager to obtain the necessary approvals. |
| Header | - Enter your name, date, e-mail and organization. - Provide the current project name and launch/phase the project is in. |
| Proposed Training Activity | Enter the course title or description of the proposed training activity. |
| Proposed Date(s) | Enter the dates or time frame in which this course would be most beneficial to the team member requesting the training. |
| Number of students | Enter the number of students for which the training session should be conducted. This field is applicable only if the team member is requesting internal or in-house training. |
| Length of course | Enter the length of the course. The length should be entered in terms of hours or days. |
| Source of funding | If known, select the source of funding (organization, project, or other) that will be used to pay for the training. If other, specify source. |
| Contribute to Established Goals | Enter how the requested training will accomplish the team member’s personal professional goals and how this training may benefit the project and organization in accomplishing their goals. |
| Sharing Information | Indicate who would benefit from the requested training. Indicate the best method for sharing the information to all members who would benefit. |
| Certification Program | Indicate if this training is part of a certificate program. If it is part of a certificate program, list the courses that have already been completed and the remaining courses that need to be taken to complete the program. |
| Training Manager | - Review the TRNR - Evaluate the TRNR for completeness. If incomplete, return for more information. - Enter TRNR into LOGTRNR and allocate unique TRNR Control Number. - Enter date received. - Enter TRNR Control No. - Ensure funding is available for training. - If concur with request and funding is available, sign and date approval line. - Obtain approval from team lead. - Inform requester of approval or denial. - If approved, arrange for training. - Maintain training request status in LOGTRNR. |

TSP+ Training Sign-in Form – Form TRNSI

| Course Title(s) |  |  |  |  |  |  |  |
| --- | --- | --- | --- | --- | --- | --- | --- |
| Instructor(s) |  |  |  |  |  |  |  |
| Date |  |  | Start Time |  |  | End Time |  |
| Attendee (Print) |  |  | Phone Number |  | Email Address |  |  |

TSP+ Training Sign-in Form Instructions – Form TRNSI

| Purpose | To provide a mechanism for course instructors to document attendance and for training manager to determine fulfillment of individual training requirements |
| --- | --- |
| General | Course instructors should pass the training sign-in form around for students to complete. Upon course completion, a copy of the training sign-in form should be sent to the training manager so that students may obtain credit for fulfillment of required or desired training. If any student fails to complete the course, the instructor must inform the training manager so that the incomplete student is not given credit for attending the course. |
| Header | - Enter name of the course or courses being taught. - Enter instructor(s) name(s). - Enter date course was conducted. - Enter start and end time of course. |
| Attendee | For each attendee, print attendee’s name, phone number, and email address. |
| Training Manager | - Evaluate the TRNSI for completeness. If incomplete, return to instructor for more information. - Upon completion of training course, update team member training logs (form LOGTRNM) for all individuals who completed the training. - Send each course attendee a training survey form (form TRNSUR). |

TSP+ Training Survey Form – Form TRNSUR

| Name (Optional) |  |
| --- | --- |
| Course Attended |  |
| Date(s) Attended |  |
| Instructor(s) |  |

| How would you rate: | Excellent | Good | Fair | Poor | N/A |
| --- | --- | --- | --- | --- | --- |
| the contents of the course? …………......………………………………………..…... |  |  |  |  |  |
| the organization of the course materials?……………..………………………….….. |  |  |  |  |  |
| the quality of the instruction?………………...……………………………………… |  |  |  |  |  |
| your current understanding of the material covered?………………………………... |  |  |  |  |  |
| how well the course matched its stated goals and objectives?………………..……... |  |  |  |  |  |
| the quality of the exercises (if applicable)?…….……………….…………………… |  |  |  |  |  |

| How much of the subject matter was: | Most (>80%) | Much (>50%) | Some (<50%) | Little (<20%) | N/A |
| --- | --- | --- | --- | --- | --- |
| important/relevant to your job?………………………………………………………. |  |  |  |  |  |

| How would you rate the: | Too Much |  | About Right |  | Too Little |
| --- | --- | --- | --- | --- | --- |
| length of time for the course?…………...……………………….…….……………... |  |  |  |  |  |
| amount of material covered?……………………………………….….……………... |  |  |  |  |  |
| depth of material covered?……………………………………………..…………….. |  |  |  |  |  |

(continued on next page)

TSP+ Training Survey Form – Form TRNSUR (continued)

| Were there opportunities for: | Too Much |  | About Right |  | Too Little | NA |
| --- | --- | --- | --- | --- | --- | --- |
| individual/ “hands on” learning?…………………………………………….…... |  |  |  |  |  |  |
| group exercises?………………………………………………………………..… |  |  |  |  |  |  |
| direct interaction with instructors?…………………………………………….… |  |  |  |  |  |  |
| asking questions?……………………………………………………………….... |  |  |  |  |  |  |
| breaks/intermissions?…………………………………………………………..… |  |  |  |  |  |  |
| testing your understanding of the content?……………………………..………... |  |  |  |  |  |  |

| Was the instructional material: | Often |  | Sometimes |  | Rarely |
| --- | --- | --- | --- | --- | --- |
| easy to understand?…………………………………………………………………... |  |  |  |  |  |
| complete?…….………………..…………………………………………………….. |  |  |  |  |  |
| well-designed?…………………..………………………………….………………… |  |  |  |  |  |
| relevant to the course?……………………………………………………..…………. |  |  |  |  |  |

Describe the best aspects of the course

Describe the worst aspects of the course

Overall, how can the course be improved to better satisfy your needs?

Provide any additional information

TSP+ Training Survey Form Instructions – Form TRNSUR

| Purpose | To provide an opportunity for attendees to provide feedback on a given course. This information can then be used to evaluate the effectiveness of the course and determine ways to improve the course for future attendees. |
| --- | --- |
| General | The training survey form will be distributed to attendees upon training completion. All completed training surveys (form TRNSUR) should be returned to the training manager for analysis. |
| Header | - Enter attendee’s name (optional). - Enter name of the course being taught. - Enter date course was conducted. - Enter instructor(s) name(s). |
| Attendee | - Fill in header information. - Answer each question by putting an “X” in the box that corresponds to your response to the question. - Briefly describe the best aspects of the course in the space provided. - Briefly describe the worst aspects of the course in the space provided. - Briefly describe how the course could be improved to better satisfy your needs. - Provide any additional information. - When completed and reviewed, submit to the training manager. |
| Training Manager | - Collect all training survey forms for the given class. - Input survey results into the training survey summary form (form SUMTRNS). - Provide instructors with a copy of the completed survey results (form SUMTRNS). |

TSP+ Training Waiver Request Form - Form TRNWR

| Name |  |  | Date |  |
| --- | --- | --- | --- | --- |
| E-mail |  | Organization |  |  |
| Project |  | Launch/Phase |  |  |

| Course title from which waiver is requested |  |  |  |  |  |  |  |  |  |  |
| --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- |
| Explain why training waiver request should be approved |  |  |  |  |  |  |  |  |  |  |
| Training Evidence |  |  |  |  |  |  |  |  |  |  |
| (attach certificate of completion, transcripts, or other evidence of obtained knowledge.) |  |  |  |  |  |  |  |  |  |  |
| When completed and reviewed, submit to the Training Manager and keep a copy. |  |  |  |  |  |  |  |  |  |  |
| Do not write below this line. |  |  |  |  |  |  |  |  |  |  |
| Date Received |  |  |  |  | Approved |  | Denied |  |  |  |
| Comments/Information Needed/Reason Denied |  |  |  |  |  |  |  |  |  |  |
| Approvals |  |  |  |  |  |  |  |  |  |  |
| Training Manager |  |  |  |  |  |  |  | Date |  |  |
| Team Lead |  |  |  |  |  |  |  | Date |  |  |

TSP+ Training Waiver Request Form Instructions - Form TRNWR

| Purpose | To provide a way to request a training waiver for an individual that is able to show evidence that he/she has received similar training or that he/she does not need to attend required training to effectively perform his/her job or in satisfying project or organizational business objectives. |
| --- | --- |
| General | Anyone may request to be waived from attending required training when they already possess the knowledge and skills needed to satisfy the training objectives by filling out this form. Once the form has been completed, the form should be submitted to the training manager to obtain the necessary approvals. |
| Header | - Enter your name, date, e-mail and organization. - Provide the current project name and launch/phase the project is in. |
| Course Title | Enter the name of the Skills, Courses, OJT Experience, as listed in the Training Matrix (form TRNM), from which waiver is requested |
| Why | Explain why this training waiver request should be approved, by providing a detailed description of the training or experience, already taken or obtained. |
| Training Evidence | - Provide training evidence. Attach certificate of completion, transcripts, or other evidence of obtained knowledge. - Note: depending on the amount of time since the course was completed, completeness of the material learned and other factors, your waiver request may still be denied, regardless of evidence provided. |
| Training Manager | - Review the TRNWR. - evaluate the TRNWR for completeness. If incomplete return for more information - enter date received - If concur that the individual does not need to attend required training to effectively perform his/her job or in satisfying project or organizational business objectives, mark the approved box else, check the denied box. - Sign and date approval line. - Obtain approval from team lead. - Inform requester of approval or denial. - If approved, update individual’s team member training log (form LOGTRNM). |

TSP Weekly Status Report - Form WEEK

| Name |  | Date |  |
| --- | --- | --- | --- |
| Project |  | Week No. |  |

| Weekly Data |  |  |  | Planned |  |  |  | Actual |  |
| --- | --- | --- | --- | --- | --- | --- | --- | --- | --- |
| Project hours for this week |  |  |  |  |  |  |  |  |  |
| Project hours this phase to date |  |  |  |  |  |  |  |  |  |
| Earned value for this week |  |  |  |  |  |  |  |  |  |
| Earned value this phase to date |  |  |  |  |  |  |  |  |  |
| Non earned-value project tasks |  |  |  |  |  |  |  |  |  |
| Role Tasks Completed |  | Hours |  | Earned Value |  |  |  | Planned Week |  |
| Totals |  |  |  |  |  |  |  |  |  |
| Development Tasks Completed |  | Hours |  | Earned Value |  |  |  | Planned Week |  |
| Totals |  |  |  |  |  |  |  |  |  |
| Other Project Activities This Week |  |  |  |  |  |  | Hours |  |  |
| Totals |  |  |  |  |  |  |  |  |  |
| Risk/Issue Tracking |  |  |  |  |  |  |  |  |  |
| Risk Name |  | Status |  |  |  |  |  |  |  |
| Issue Name |  | Status |  |  |  |  |  |  |  |

TSP Weekly Status Report Instructions - Form WEEK

| Purpose | Use this form to prepare your weekly status reports. |
| --- | --- |
| General | - This form is used only when a tool with equivalent functionality, features, or purpose is not available. - Complete a copy of this form each week and give it to the planning manager before the weekly meeting. - The planning manager prepares the team summary form. - Role tasks are those tasks you perform for a team assigned role such as planning manager, quality manager, etc. - Development tasks are those tasks you perform while developing the product such as designing, coding, or inspecting. |
| Header | Enter your name, project name, date, and the week number reported. |
| Weekly Data | - Enter the hours you actually spent on the project this week and the hours you planned to spend. - Enter the actual and planned cumulative hours you have spent on this phase of the project. - Enter the earned value planned for the week and your actual earned value. - Enter your cumulative earned value planned and actual for the project phase to date. - Note: the team may choose to track time and earned value for the entire project to date, rather than just for the current phase. |
| Role Tasks Completed | For each of your team roles: - Enter the name of each task you completed this week. - Enter the total time you spent on each of these tasks. - Enter the week number when you planned to finish the task. - Total the week’s earned value. |
| Development Tasks Completed | For your development work: - Enter the name of each task you completed this week. - Enter the total time you spent on each of these tasks. - Enter the week number when you planned to finish the task. - Total the week’s earned value. |
| Other Project Activities | For any other project work that is not on the task schedule: - Enter the activity on which you spent time this week. - Enter the total time you spent on each of these activities. |
| Risk/Issue Tracking | - For the risks you track, summarize the status and any important changes or exposures for this week. - For the issues you track, summarize the status and any important changes this week. |