Copyright 2018 Carnegie Mellon University.  All rights reserved.

This material is based upon work funded and supported by the Department of Defense under Contract No. FA8721-05-C-0003 with Carnegie Mellon University for the operation of the Software Engineering Institute, a federally funded research and development center.

Any opinions, findings and conclusions or recommendations expressed in this material are those of the author(s) and do not necessarily reflect the views of the United States Department of Defense.

NO WARRANTY. THIS MATERIAL IS FURNISHED ON AN “AS-IS” BASIS WITH NO WARRANTIES OF ANY KIND, EITHER EXPRESSED OR IMPLIED, INCLUDING, BUT NOT LIMITED TO, WARRANTY OF FITNESS FOR PURPOSE OR MERCHANTABILITY, ANY WARRANTY WITH RESPECT TO FREEDOM FROM PATENT, TRADEMARK, OR COPYRIGHT INFRINGEMENT, OR THIRD PARTY INTELLECTUAL PROPERTY RIGHTS.

[Distribution Statement A] This material has been approved for public release and unlimited distribution.  The United States Government has Unlimited Rights in this material as defined by DFARS 252.227-7013.

The text and illustrations in this material are licensed by Carnegie Mellon University under a Creative Commons Attribution 4.0 International License.

The Creative Commons license does not extend to logos, trade marks, or service marks of Carnegie Mellon University.

TSP+ Scripts

All TSP, TSPm, and TSP+ scripts are listed.  After the first four, the scripts are listed in the alphabetical order of their abbreviated names.  The POPS and TOPS scripts provide overall guidance to the TSP+ and TSPm processes.  The scripts titled with TSP are core scripts which may have additional changes made for TSP+.  The scripts titled TSP+ are add-on scripts used to address other aspects of a mature software development organization.  The scripts titled TSPm are multi-team scripts used for projects which consist of more than one sub-team.

| Script Abbreviation | Script Name | Page Reference |
| --- | --- | --- |
| POPS | TSP+ Overall process operations, the initiating process improvement script | 3 |
| POPS7 | TSP+ Process group formation | 5 |
| TOPS | TSP+ Team operations, overall guidance for TSP introduction | 6 |
| TOPS4 | TSP+ Post launch TSP and TSPm team operation | 7 |
| ANA | TSP Impact Analysis | 8 |
| CHECKPOINT | TSP Checkpoint Assessment | 10 |
| CMAUDIT | TSP+ Configuration Management Audit | 12 |
| CYCLE | TSP Cycle | 14 |
| DAR | TSP+ Decision Analysis and Resolution | 16 |
| DEV | TSP Overall Development and Enhancement Process | 18 |
| HLD | TSP High-Level Design | 19 |
| IMP | TSP Implementation | 21 |
| IMP6 | TSP Unit Test and Test Development (step 6 in script IMP) | 22 |
| INS | TSP Inspection Process | 23 |
| LAU | TSP Team Launch | 26 |
| LAUm | TSPm Multi-team launch | 27 |
| LAU1 | TSP Launch Meeting 1 - Launch overview and kick-off | 29 |
| LAU1A | TSPm Multi-team launch Meeting 1A – strategy presentation | 30 |
| LAU2 | TSP Launch Meeting 2 - Roles and goals | 31 |
| LAU3 | TSPm Launch Meeting 3 - Strategy, process, support | 32 |
| LAU3A | TSPm Multi-team leadership meeting 3A | 35 |
| LAU4 | TSP Launch Meeting 4 - Overall team plan | 36 |
| LAU5 | TSP Launch Meeting 5 - Quality plan | 38 |
| LAU5B | TSPm Multi-team planning manager role meeting | 39 |
| LAU5C | TSPm Multi-team quality manager role meeting | 40 |
| LAU6 | TSP Launch Meeting 6 - Detailed next-phase plans | 41 |
| LAU6B | TSPm Multi-team planning manager meeting, plan consolidation | 43 |
| LAU7 | TSP Launch Meeting 7 - Risk assessment | 44 |
| LAU7A | TSPm Multi-team leadership meeting to plan the management meeting | 46 |
| LAU8 | TSP Launch Meeting 8 - Management meeting preparation | 47 |
| LAU9 | TSP Launch Meeting 9 – Wrap-up management meeting | 49 |
| LAUPM | TSP Launch Postmortem Meeting – Postmortem on the launch | 50 |
| LTL | TSPm Leadership team launch (LTL) | 51 |
| LTL1 | TSPm LTL meeting 1, business goals | 52 |
| LTL2 | TSPm LTL meeting 2, leadership team goals | 53 |
| LTL3 | TSPm LTL meeting 3, team oversight strategy | 54 |
| LTL4 | TSPm LTL meeting 4, role team assignments | 55 |
| LTL5 | TSPm LTL meeting 5, role team goals and responsibilities | 56 |
| LTLPM | TSPm LTL postmortem meeting | 57 |
| MAINT | TSP Overall Maintenance and Enhancement Process | 58 |
| MTG | TSP General Meeting Process | 59 |
| PM | TSP Project Postmortem | 60 |
| PMTD | TSP Postmortem Test Defects | 62 |

(continued on next page)

TSP+ Scripts (continued)

| Script Abbreviation | Script Name | Page Reference |
| --- | --- | --- |
| PREP | TSPm Preparation script for a multi-team launch or relaunch | 63 |
| PREPT | TSP+ Team Launch Preparation | 64 |
| PREPW | TSPm Weekly meeting to review multi-team launch/relaunch preparation | 65 |
| PSSPE | TSP+ Project’s Set of Standard Processes Establishment | 66 |
| REL | TSP Team Relaunch | 67 |
| REL1 | TSP Relaunch Meeting 1 - Status and management update | 68 |
| REL1A | TSPm Multi-team relaunch meeting 1A, status and strategy presentation | 69 |
| RELm | TSPm Multi-team relaunch script | 70 |
| REQ | TSP Requirements | 72 |
| RTL | TSPm Role manager team launch (RTL) | 73 |
| RTL1 | TSPm RTL meeting 1, leadership team goals | 74 |
| RTL2 | TSPm RTL meeting 2, role manager team goals and leader selection | 75 |
| RTL3 | TSPm RTL meeting 3, defining products and processes | 76 |
| RTL4 | TSPm RTL meeting 4, developing the role manager team plan | 77 |
| RTL5 | TSPm RTL meeting 5, balancing the role manager team plan | 78 |
| RTL6 | TSPm RTL meeting 6, preparing for the leadership team review | 79 |
| RTL7 | TSPm RTL meeting 7, role manager plan review with leadership team | 80 |
| RTLPM | TSPm RTL postmortem meeting | 81 |
| STATUS | TSP Management and Customer Status Meeting | 82 |
| TEST | TSP Release Test | 83 |
| TEST1 | TSP Product Build (step 1 in script TEST) | 84 |
| TEST2 | TSP Integration (step 2 in script TEST) | 85 |
| TEST3 | TSP System Test (step 3 in script TEST) | 86 |
| TESTD | TSP Test Defect Handling | 87 |
| WEEK | TSP Weekly Team Meeting | 88 |
| WEEKL | TSPm Weekly leadership team meetings for a multi-team | 89 |
| WEEKLR | TSPm The leadership role manager team meeting | 90 |

| TSP+ Process Operations - Script POPS |  |
| --- | --- |
| Purpose | - To guide an organization in improving its software performance - To couple the TSP, CMMI, and Lean Six Sigma improvement initiatives |
| Entry Criteria | Management seeks to improve the performance of its software-related operations. |
| General | - This script assumes a TSP/CMMI implementation. The use of Lean Six Sigma methods and tools is optional. |

| Step | Activities | Description |
| --- | --- | --- |
| 1 | Contact | - Determine how the TSP and CMMI can address management’s concerns. - Talk with working level engineers and managers to build interest. |
| 2 | Awareness | - Expose senior management to the opportunity. - Describe the potential benefits and the operating level interest. - Provide credible references. |
| 3 | Obtain Sponsorship | - Hold a one-day executive seminar for the senior managers and executives, which include a CMMI overview. - Hold a half-day planning workshop to identify initial areas for TSP trial use - Identify a manager to be responsible for the transition plan and execution. |
| 4 | Develop Transition Plan | - The responsible manager produces a plan for TSP trial use. - arranges for qualified training and coaching support - schedules managers and team members for training - schedules initial TSP launches, checkpoints, and relaunches |
| 5 | TSP Trial Use | - The organization conducts trial TSP projects (TOPS script). - trains the engineers and managers - launches the teams and regularly reviews performance - identifies internal candidates to be initial PSP instructors and TSP coaches |
| 6 | Evaluation | - The organization assesses team and TSP performance and decides to proceed with the process improvement initiative. - identifies a manager to lead the long-term improvement effort and become the process group team lead - allocates initial resources - issues a policy describing the process improvement initiative and its importance to the business - defines management responsibilities |
| 7 | Adoption: Process Group Formation | - The process group team lead, with the help of the TSP Coach (POPS7 script) - produces a process improvement plan proposal - reviews this plan proposal with management and gets their approval - recruits a staff and trains that staff in CMMI, PSP, and TSP - launches the process group team to plan and execute the process improvement plan proposal |
| 8 | Adoption: Institutionalize TSP | - Working with project management, the process manager - develops a TSP introduction plan and schedule for each project team - assists projects in launching and running TSP projects (TOPS script) |
| 9 | Continuing Improvement | - Using the project’s needs as a guide and reviewing the Process Group Roles and Responsibilities specification, set priorities and build and execute a plan (script CYCLE) based on organizational business objectives for - defining team and organizational processes - establishing and maintaining a process asset library - providing continuing training and coaching guidance - obtaining needed tools and methods - providing tool and method training and support - assessing the organization annually to identify further improvement needs - Apply Lean Six Sigma methods and tools to improve current process performance. |

(continued on next page)

TSP+ Process Operations - Script POPS (continued)

| # Continuing Review | - Management annually reviews the organization’s software operations. - analyzes cost and benefit data - obtains customer, manager, and engineer feedback on improvement results - adjusts the improvement program to address identified problems and capitalize on new improvement opportunities during Meeting 1 of the process group’s (re)launches (script CYCLE) |
| --- | --- |

| TSP+ Process Group Formation - Script POPS7 |  |
| --- | --- |
| Purpose | - To guide the process group (PG) team lead in planning for and staffing a process improvement group |
| Entry Criteria | - The organization has initiated a software process improvement program. - Management has issued a process improvement policy statement and named a responsible manager. - Initial process improvement resources have been allocated. |

| Step | Activities | Description |
| --- | --- | --- |
| 1 | Define Responsibilities | - The PG team lead, with help from the TSP Coach - documents the principal responsibilities of the job and proposed group (specification Process Group (PG) Roles and Responsibilities) - reviews PG roles and responsibilities with existing staff groups (configuration management, quality assurance, and test for example) - reviews PG roles and responsibilities with development department managers - revises PG roles and responsibilities based on the review results - reviews PG roles and responsibilities with senior management for approval |
| 2 | Develop Improvement Plan | - The TSP Coach works with the PG team lead in developing a proposal for the process improvement work. - tasks to be performed - training, support, and assistance to be provided - resources needed, both full and part time - proposed recruiting schedule - proposed task schedule |
| 3 | Obtain Plan Approval | - The PG team lead - reviews this proposal with existing staff groups (configuration management, quality assurance, and test for example) - reviews the proposal with development department managers - obtains agreement from the development and staff groups to provide the needed part time process improvement resources - revises the proposal based on the review results - reviews the proposal with senior management for approval |
| 4 | Recruit Initial Staff | - The PG team lead recruits the process staff. - obtains a core staff of process experts (trained and experienced if possible) - utilizes part-time support from the development groups where planned - recruits experienced professionals from internal development groups where possible - maintains a mix of engineering, process, technology, and management skills |
| 5 | Train Initial Staff | - Using internal skills where possible, the PG team lead trains the process staff in the key process improvement technologies. - the Capability Maturity Model (CMMI, P-CMM, and so forth) - the Personal Software Process (PSP) - the Team Software Process (TSP) - Lean Six Sigma methods and tools for subsequent improvement analysis - the principal tools and methods used in the organization |
| 6 | Process Group Team Launch | - The process group launches in order to plan and execute the approved process improvement proposal (script LAU). |

| # Exit Criteria | - The PG has successfully launched. |
| --- | --- |

| TSP+ Team Operations - Script TOPS |  |
| --- | --- |
| Purpose | To guide managers, teams, and engineers in introducing and using the TSP process |
| Entry Criteria – Trial Use | - Senior management has participated in the TSP executive strategy seminar and planning workshop and supports TSP introduction. - An initial TSP trial program has been approved. |
| Entry Criteria – TSP Adoption | - To move beyond trial use and start broad TSP introduction - TSP trial use has been successful. - A TSP adoption plan has been developed and approved. - Initial PSP instructors and TSP coaches have been selected and are scheduled for training. |
| Entry Criteria – TSPm Initial Use | - To launch a TSPm multi-team or distributed multi-team - TSP trial use has been successful. - The organization has at least one authorized TSP coach on its staff and enough additional coaches are to be trained to support team operation. |
| General | - To use the TOPS script, one or more of the entry criteria must be satisfied. |

| Step | Activities | Description |
| --- | --- | --- |
| 1 | Team Formation and Training | - For each TSP or TSPm team, a project is identified and the staff has been trained. - All managers on each project or in its management chain are TSP trained before the launch. - All project software professionals are PSP trained before the launch. - All other project professionals are trained in the personal process before the launch. |
| 2 | Launch Preparation | - Prepare to launch each TSP or TSPm team (checklist PREPL). - For each TSPm multi-team or distributed multi-team, also follow scripts PREP and PREPW during launch preparation. |
| 3 | TSP Cycle | - Follow script CYCLE until project conclusion in order to guide the team in: - launching the project - executing the team’s detailed planning - undergoing a checkpoint (script CHECKPOINT) - conducting a phase, cycle or project postmortem - preparing for subsequent relaunches (if needed) |
| 4 | Multi-Team (TSPm) Project Operations | - For multi-teams only, follow script TOPS4 concurrently for each sub-team following the TSP cycle (script CYCLE) in order to manage the sub-team interdependencies and overall project. |

| # Exit Criteria | - Project completed with team and team member plan and actual data - Project data filed in the project notebook (specification NOTEBOOK) - Final project report prepared and presented to management |
| --- | --- |

| TSP+ Project Operations - Script TOPS4 |  |
| --- | --- |
| Purpose | To guide managers, team leaders and team members in managing a TSPm project |
| Entry Criteria | The project has completed a launch or relaunch. |

| Step | Activities | Description |
| --- | --- | --- |
| 1 | The Leadership Team Launch | Following the project (re)launch and under the guidance of a qualified TSP coach, the leadership team holds a one-day launch (script LTL). - reviews the organization’s and this project’s goals - develops the leadership team’s management strategy - defines the role manager teams’ goals and responsibilities - allocates tasks and responsibilities among the leadership team members |
| 2 | Leadership Team Operations | Following the leadership team launch, the leadership team - manages the project and each sub-team in performing its work - holds weekly meetings to review project status and issues (script WEEKL) - provides guidance to the role manager team launches (script RTL) - meets at least monthly with each role manager team (script WEEKLR) - regularly reports to senior management and the customer on project status and progress (specification STATUS) |
| 3 | Sub-team Operations | Following the team and sub-team (re)launches, each sub-team follows its defined process and detailed plan in doing its work. |
| 4 | Role Manager Team Launches | Soon after the team (re)launch and under the guidance of a TSP coach, each role manager team holds a two-day launch (script RTL). - the leadership team defines its goals for the role manager team - the role managers establish their strategy and plan to meet these goals - the role managers allocate tasks and responsibilities among team members - the role managers prepare and review their plan with the leadership team |
| 5 | Quarterly or Monthly Management Reviews | The leadership team and senior management periodically - review project status, progress, and projections - assess the team for quality level performance - assess the team for expert level performance - identify issues and problems and assign responsibilities |
| 6 | Periodic Customer Reviews | The leadership team regularly reviews status and progress with the customer. - planned versus actual performance - outstanding issues and problems, actions planned, and assistance needed |

| # Exit Criteria | - Project or project phase completed with team and team member plan and actual data filed in the project notebook (specification NOTEBOOK). - Final project report prepared and presented to management |
| --- | --- |

| TSP Impact Analysis - Script ANA |  |
| --- | --- |
| Purpose | To produce a complete, valid, and accurate release specification (SRS) and impact analysis report |
| Entry Criteria | - Completed analysis-phase launch, a detailed next-phase plan, and a current list of project risks and exposures - Defined impact analysis process - Enhancement requirements statement and preliminary fix list - Forms: INS, ITL, LOGD, LOGT, MTG, PIP, SUMP, SUMQ - Specification: NOTEBOOK |
| General |  |

| Step | Activities | Description |
| --- | --- | --- |
| 1 | Enhancement Requirements Study | - Study the enhancement and fix requirements to identify errors and omissions and clarify questions. - Produce an elicitation plan and detailed questions. - Double-check correctness of ALL requirements assumptions. |
| 2 | Market Requirements Elicitation | - Hold customer/marketing elicitation meeting(s) (script MTG). - Document each elicitation meeting and its results (form MTG). |
| 3 | Requirements Prototypes | - Prototype and/or simulate all important specification questions and review results with systems, marketing and the customer. - Where needed, use prototypes to obtain data for validating design, planning, resource, or size assumptions. |
| 4 | System Requirements Specification | - Produce the System Requirements Specification (SRS). - normal, abnormal, and recovery behavior and performance - operational and user interfaces - documentation, training, distribution, installation, maintenance, and support requirements - For each SRS item, reference its source in the enhancement requirements. - Identify required user manual changes and produce an outline. - Ensure that bi-directional traceability is maintained and that changes to the SRS do not impact other source requirements or lower level requirements. Where needed documented changes to source and lower level specifications. |
| 5 | SRS Inspection | - Inspect the SRS, impacted source and lower level specifications, and user manual outline and draft (script INS). - Record size, time, and defect data (form INS). - Include all relevant stakeholders. - Resolve all issues and update and baseline the SRS. |
| 6 | Impact Analysis Report | Produce the impact analysis report. - components to be changed for each planned fix - predicted new and changed components for the enhancements - estimated resources for each fix, change, or addition - impact to other product lifecycle activities and their impact on project commitments - This analysis can be done during a (re)launch (script LAU or REL). In the event a large impact is expected, a DAR may be planned in order to identify the best solution. |
| 7 | Impact Analysis Review | Review the impact analysis. - Determine if the estimates are reasonable, and adjust them as needed. - Identify and drop unjustified fixes and enhancements. - Update the impact analysis report. |

(continued on next page)

TSP Impact Analysis - Script ANA (continued)

| 8 | Test Specification | Define tests to verify the system and products to the specifications. - normal and abnormal interfaces, functions, and performance - security, safety, failure, and recovery conditions |
| --- | --- | --- |

| Exit Criteria | - Inspected and completed SRS and impact analysis documents - Completed INS, LOGD, LOGT, MTG, PIP, SUMP, SUMQ forms - Analysis plan, actual, and earned-value data recorded and entered in the project notebook (specification NOTEBOOK) |
| --- | --- |

| TSP Checkpoint Assessment - Script CHECKPOINT |  |
| --- | --- |
| Purpose | To identify the issues and problems limiting a TSP team's performance and recommend actions to address them |
| Entry Criteria | - The team has successfully completed a TSP launch. - The team has used the TSP process for one or more months. - A qualified coach is available to conduct the checkpoint. - Forms: CHECKTMDR, RSIM |
| General | - A checkpoint is conducted as a process assessment, not an audit. - Confidentiality is maintained and no statements by any individual team member are reported to anyone else. |

| Step | Activities | Description |
| --- | --- | --- |
| 1 | Team Leader Review | The coach meets with the team leader to review the checkpoint objectives and plan and agree on the plan and schedule. |
| 2 | Management Review | The coach and team leader review the checkpoint plan and schedule with senior management. |
| 3 | Team Review | The coach and team leader review the checkpoint objectives, plan, and schedule with the team and answer questions. |
| 4 | Data Review | The coach reviews each members personal data (Form CHECKTMDR) |
| 5 | Role Review | The coach reviews material created by the role managers in performing their role (Specification Roles) by reviewing the scripts and forms marked as Responsible (R) for the respective role in the Relevant Stakeholder Involvement Matrix form (Form RSIM) using form CHECKTMDR. |
| 6 | Process Review | - If applicable, the coach reviews the previous checkpoint report to determine which prior findings and recommendations have been addressed or are still outstanding. - The coach reviews the team’s performance against all applicable specifications, guidelines, policies and procedures to ensure they are being followed, noting any findings or recommendations in the checkpoint report. |
| 7 | Individual Discussions | The coach meets with individual team members to discuss - any questions about the team member's data - any questions about the team member’s team role - how to address any problems or concerns the member has raised - accomplishments, progress, things working well - how the team uses the process and how it works for them - any problems or issues with the team’s process - what the team leader or management could do to better support the team - suggestions for improvement at the individual, team, and organizational levels - other problems or suggestions |
| 8 | Preliminary Findings | The coach prepares preliminary checkpoint findings and recommendations report for review with the team. |
| 9 | Team Discussion | The coach meets with the team to discuss - the preliminary checkpoint findings - any team problems or issues concerning management and the team leader - the coach's recommendations for addressing these problems - any problems, issues, or improvement suggestions by the team - the team’s ideas for changes or additions to the checkpoint report - review the checkpoint findings and recommendations with the team (the team may develop an action plan to address finding and recommendations prior to management review of checkpoint finding) |
| 10 | Findings Review | The coach and team leader - review the checkpoint findings and recommendations with management - obtain agreement to develop an action plan to address the recommendations |

(continued on next page)

TSP Checkpoint Assessment - Script CHECKPOINT (continued)

| 11 | The Checkpoint Report | The coach - submits the final report to the team leader and other levels of management as appropriate for distribution in the organization |
| --- | --- | --- |

| # Exit Criteria | - The checkpoint report is prepared and submitted. - There is agreement to develop a plan to address the recommendations. |
| --- | --- |

| TSP+ Configuration Management Audit – Script CMAUDIT |  |
| --- | --- |
| Purpose | To provide the team with a mechanism for objectively evaluating that what is supposed to be controlled is controlled and can be retrieved. Retrieval of accurate information is one of configuration management’s primary functions. |
| Entry Criteria | - The person performing the configuration management audit is independent of the configuration management processes and has the ability to objectively evaluate adherence of the configuration management process against its process descriptions, standards, and procedures, and address noncompliance. - All configuration management records are available for review (Forms: CCR, LOGCCR, LOGCI, CIBPS, CIR) - Access to all configuration item storage locations is provided. - Forms: ITL, PIP |
| General | The amount of time required to perform this audit will vary, depending on project status, product complexity, number of configuration items, number of configuration change requests and the team’s experience with configuration management. |

| Step | Activities | Description |
| --- | --- | --- |
| 1 | Review Configuration Management Process | - Meet with the Support Manager, or the Configuration Management Coordinator (CMC), and discuss the processes being used to perform the CM function - Compare discussion with CM process documentation and record any discrepancies found (ITL). |
| 2 | - Review LOGCCR | - Review the LOGCCR - Are all fields complete and accurate? - Is the corresponding CCR present? - Are all CCR forms recorded in the LOGCCR? - Record any discrepancies found (ITL) |
| 3 | Review LOGCI | - Review the LOGCI - Are all fields complete and accurate? - Is the corresponding CIR present? - Are all CIR forms recorded in the LOGCI? - Record any discrepancies found (ITL) |
| 4 | Review CCR | - Review all CCR forms - Are all fields complete and accurate? - Are all CCR Control Numbers unique? - Are there any gaps in the CCR Control Number sequence? - Have all approvals been obtained? - Record any discrepancies found (ITL) |
| 5 | Review CIR | - Review all CIR forms - Are all fields complete and accurate? - Are CI numbers unique? - Do the CI numbering scheme conform to standard? - Are there any gaps in the CI numbering sequence? - Have all approvals been obtained? - Record any discrepancies found (ITL) |
| 6 | Review CIBPS | - Review the CIBPS forms - Are all fields complete and accurate? - Record any discrepancies found (ITL) |

(continued on next page)

| TSP+ Configuration Management Audit – Script CMAUDIT (continued) |  |  |
| --- | --- | --- |
| Step | Activities | Description |
| 7 | Verify Location of Configuration Items | - Make copy of LOGCI - Starting at the beginning of the configuration item list - Verify that all configuration items are retrievable by verifying CI location is accurate - In the Physical Configuration Audit field of form LOGCI, mark the configuration item as “Present”, “Missing”, or “Incomplete” |
| 8 | Review findings with Support Manager or CMC | - Review all discrepancies found (ITL) with Support Manager or CMC for resolution. - Review all configurations items marked as “Missing” or “Incomplete”, in form LOGCI, with Support Manager or CMC for resolution. - Inform Support Manager or CMC that all unresolved items will be reported to the team and may also be reported to management. |
| 9 | Review all unresolved CM issues with Team | - Review all unresolved discrepancies found (ITL) with the team for resolution. - Review all configuration items marked as “Missing” or “Incomplete”, in form LOGCI, that were not addressed by the Support Manager or CMC, for resolution. |
| 10 | Summarize Findings | - Summarize discrepancies found as a result of conducting the CM Audit - Describe all unresolved issues |
| 11 | Review finding with Team | - Review CM Audit Summary with team during a regularly scheduled team meeting (see Script WEEK). |
| 12 | Review findings with PG Quality Manager | - Review all unresolved discrepancies found (ITL) with the PG Quality Manager. - Review all configuration items marked as “Missing” or “Incomplete,” in form LOGCI, that have not been addressed by the team. - Review any corrective actions being taken by the team to resolve issues. |
| 13 | Report findings to management | - Report CM Audit Summary as a quality issue to management (see Specification STATUS). |
| 14 | Tack to resolution | - Track all CM issues to resolution - Periodically review unresolved CM issues with Team (Script WEEK) and management (Specification STATUS). |

| Exit Criteria | - All CM records have been review (Forms: CCR, LOGCCR, LOGCI, CIBPS, CIR). - All discrepancies have been recorded (Form: ITL). - All process improvement suggestions have been recorded (form PIP). - All unresolved CM issues have been reviewed with the team and management. - All CM issues have been tracked to resolution |
| --- | --- |

| TSP Cycle - Script CYCLE |  |
| --- | --- |
| Purpose | - To guide teams through the use of a defined and structured process, with repeatable and measurable steps, which provides a rapid feedback on the quality of the product and progress towards completion - To guide teams in the establishment of a shared understanding of the work and how it is to be done, which includes a common understanding of the team goals, team member roles, product or components to be produced, available resources and existing constraints, and measures of success. - To provide the mechanisms required in order for a team to practice self-management |
| Entry Criteria | - All team members have been adequately trained in the use of PSP and TSP. - All team members and the team leaders has been identified and allocated to the project. - A qualified TSP coach is available to guide and coach the team through the TSP Cycle. |
| General | - Depending on the size and needs of the project, a TSP Cycle can range from a period of a few weeks to a few months. - Depending on a project’s overall duration and needs, the team may choose to use phases, cycles, or both in determining when it needs to conduct a (re)launch. A phase represents a part of the development lifecycle such as the implementation phase, and a cycle represents the time between planning horizons. A phase can encompass several cycles, just as a cycle can encompass several phases. |

| Step | Activities | Description |
| --- | --- | --- |
| 1 | Team (Re)Launch (LAU/LAUm or REL/RELm) | - During the launch, the team learns from management what it is supposed to do, make a plan for doing the desired work, and then reviews the plan with management. The two desired outcomes of the launch are an approved team plan for producing a particular product, both the overall project plan and a detailed next phase plan, and a jelled self-directed team. - During a relaunch (script REL or RELm), the team members update their overall plan and develop a new next phase plan based on what they have done since the initial launch or the prior relaunch. The team has already committed to management what it intends to do and, if that commitment is unchanged, the members do not need to repeat the management meetings. However, if the project has changed in any significant way (such as changes to the product requirements, the team membership, project schedule, project scope, etc.), then the relaunch should be regarded as a new project launch and all of the meetings (script LAU or LAUm) and activities should be held. |
| 2 | Plan Execution | - The team executes the cycle plan created during the (re)launch, making updates or changes to the plan as necessary. - The team uses scripts DEV and MAINT to guide the team in developing, maintaining and enhancing software-intensive products. - The team meets weekly (script WEEK) to ensure that all team members understand current project status and know what to do next. - The team leader conducts periodic management and customer status meetings (script STATUS). |
|  | Checkpoint | About a month into the TSP cycle or halfway through the cycle, whichever is shorter, the TSP Coach leads the team through a checkpoint (scripts CHECKPOINT) |

(continued on next page)

| 3 | Cycle or Project Postmortem | - The cycle postmortem is held before any subsequent launch or relaunch and includes only the data on the work completed during the earlier project phases or cycles. The focus of these postmortems is to evaluate interim project status and calibrate planning parameters to revise goals and improve performance in subsequent cycles (see script PM). - The project postmortem is conducted at the end of the project and includes the full product or project data. Organizational process baseline data may be updated at this time (see script PM). |
| --- | --- | --- |

| Exit Criteria | - A completed high-quality product - A project summary report (see specification SUMMARY) - PIPs for all identified process improvements |
| --- | --- |

| TSP+ Decision Analysis and Resolution - Script DAR |  |
| --- | --- |
| Purpose | To define the steps required to conduct a formal evaluation. This process may be used at any point in the project life-cycle whenever a formal decision is needed. This ensures that a controlled decision process, rather than a reactionary decision process, for critical decisions. |
| Entry Criteria | - An issue has been identified for which there is a clear definition of the issue requiring a decision and there is a reasonable assumption that more than 1 valid option exists. - The decision owner has been identified. This person is ultimately responsible for making the final decision. This includes: - ensuring that the appropriate evaluation criteria and evaluation method(s) are identified for the solutions under consideration - ensuring that a final decision is reached - The decision participants have been identified. They must have the knowledge and background required to assist in evaluating the alternative solutions and making an informed decision. - The decision stakeholders have been identified, which is anyone that is affected by the decision but does not necessarily participate in the decision making process. - The work associated with performing the formal evaluation has been planned for in the individual’s current task plans. - Forms: DAR, ITL, PIP |
| General | - Care should be taken to limit the use of the DAR process to key decisions, so as to not impede progress. The DAR process should only be used when one or more of the following is true: - a decision is directly related to a high risk - a decision could cause significant cost overruns or affect a teams ability to achieve commitments - a decision is regarding major architecture choices - the cost of the formal evaluation process is acceptable when compared to the costs of a decision’s possible negative impact |

| Step | Activities | Description |
| --- | --- | --- |
| 1 | Define the Issue | - The decision owner defines the issue to be addressed (form DAR). - Review definition of issue with decision participants and decision stakeholders for concurrence of the issue being resolved. - Update definition of issue as required. |
| 2 | Identify Alternative Solutions | - The decision owner and decision participants identify and document possible solutions to the defined problem. - There should be no less than 2 and no more than about 4 prospective solutions identified for consideration. When determining the number of solutions under consideration, keep in mind that if there are too many solutions under consideration, it is likely that time constraints will dictate that some of them will not be given proper consideration. This in turn detracts from a more thorough analysis of the other potential solutions. - Typical methods of identifying alternative solutions include, but are not limited to; brainstorming, solicitation, market research, competitor analysis, customer feedback, and analysis of similar problems solved on other projects and their solutions. - Record up to 4 of the most likely viable solutions identified on form DAR. |

(continued on next page)

| TSP+ Decision Analysis and Resolution - Script DAR (continued) |  |  |
| --- | --- | --- |
| Step | Activities | Description |
| 3 | Determine Evaluation Criteria | - The decision owner and decision participants identify and document the evaluation criteria on form DAR. - There should be no less that 2 and no more than about 7 evaluation criteria. - Due to the unique constraints associated with each project or team, no single set of evaluation criteria can be created. As such, the DAR evaluation criteria, and associated factors, must be identified by the evaluators. - Typical evaluation criteria used to evaluate alternative solutions include, but are not limited to; cost, schedule, risk, performance, reliability, reusability, efficiency, maintainability, scalability, and portability. |
| 4 | Determine Evaluation Methods | - The decision owner and decision participants identify and document the evaluation method to be used for each evaluation criteria selected on form DAR. - Typical methods used to evaluate alternative solutions include, but are not limited to; cost study/model, simulation, prototypes, benchmarks, trade studies, extrapolation based on experience and open discussion, user comments, testing, data comparison, feature comparison, and analysis of solutions to similar problems. |
| 5 | Stakeholder Review | - Review identified alternative solutions, evaluation criteria and associated factors, and selected evaluation methods with identified decision stakeholders for concurrence. - Update evaluation plan (form DAR) as required. |
| 6 | Collect Data | - The decision owner and decision participants collect the information required to compare selected alternatives using the selected evaluation methods. |
| 7 | Evaluate Alternatives | - Evaluate the alternatives against the evaluation criteria. - Substantiate scoring and conclusion through selected evaluation method(s). - Identify all unknowns and assumptions made about the solution meeting evaluation criteria and document observations that support or disprove those assumptions. - Identify new alternatives, if alternative solutions prove unsatisfactory and conduct evaluation of new alternatives. - Document evaluation results, including any unsatisfactory alternatives on form DAR. Include rationale for additions of new alternative solutions and any changes to the evaluation criteria and methods. |
| 8 | Select Solution | - Select the most auspicious solution. - Identify risks associated with selected solution (form ITL). - Document justification of selected solution (form DAR) - Review evaluation results and selected solution with decision stakeholders for concurrence. |
| 9 | Configure DAR Data Package | - Place completed and approved DAR data package under configuration control. The DAR data package should include at a minimum; a completed DAR form, copy of all data collected which was required to compare selected alternatives using the selected evaluation methods. |

| Exit Criteria | - Decision analysis and resolution activities have been completed. - A solution to the defined issue has been selected and agreed to by the decision owner, participants, and stakeholders. - All process improvement suggestions have been recorded (form PIP). - The DAR data package is under formal configuration control. |
| --- | --- |

| TSP Overall Development and Enhancement Process - Script DEV |  |
| --- | --- |
| Purpose | - To guide integrated teams in developing and enhancing software-intensive products - Use script MAINT for maintenance and enhancement projects. |
| Entry Criteria | - The work has been planned during a (re)launch |
| General | For small development and enhancement projects, the TSP cycle may span several phases or even the entire project. For iterative methods, the steps in this script may take place concurrently. All steps should be planned and executed within one or multiple TSP cycles (script CYCLE) |

| Step | Activities | Description |
| --- | --- | --- |
| 1 | Requirements (REQ) | - Set requirements goals, roles, processes, and procedures. - Produce the overall project plan and detailed requirements plan. - Assess requirements risks and exposures. - Document, review, and validate the requirements. - Develop and inspect the requirements specifications. - Define system tests and produce the user manual outline. |
| 2 | High-Level Design (HLD) | - Set design goals, roles, processes, and procedures. - Produce the overall project plan and detailed HLD plan. - Assess design risks and exposures. - Produce and inspect the high-level design. - Produce the performance and integration test specifications. |
| 3 | Implementation (IMP) | - Set implementation goals, roles, processes, and procedures. - Produce the overall project plan and detailed implementation plan. - Assess implementation risks and exposures. - Design, code, inspect, and unit test the product components. - Produce the unit and product test specifications and draft documentation. |
| 4 | Release Test (TEST) | - Set integration and test goals, roles, processes, and procedures. - Produce the detailed integration and test plan. - Assess integration and test risks and exposures. - Develop test materials and test data. - Build the integrated product. - Run the integration and system tests. - Return defective components for rework and retest. - Produce and review the final documentation. - Deliver the completed product. |

| Exit Criteria | - A completed high-quality product - A project summary report (see specification SUMMARY) - PIPs for all identified process improvements |
| --- | --- |

| TSP High-Level Design - Script HLD |  |
| --- | --- |
| Purpose | - To produce the (hardware-)software system design specification - To establish the product development and design strategy |
| Entry Criteria | - Completed detailed next-phase plan which include high level design tasks and a current list of project risks and exposures - Inspected and baselined SRS and ERS documents - Draft user’s manual - Forms: INS, ITL, LOGD, LOGT, MTG, PIP, SUMP, SUMQ - Specification: NOTEBOOK |
| General | On small projects, steps 1-3 could be accomplished during a (re)launch |

| Step | Activities | Description |
| --- | --- | --- |
| 1 | Structural Design | Produce the overall product design concept. - system architectural framework - product components, principal functions, and interfaces |
| 2 | Development Strategy | Define the development strategy. - component development sequence and dependencies - component integration sequence and dependencies - reuse and testing strategies |
| 3 | High-Level Design Strategy | Depending on system size and complexity, determine whether to - design the overall system in one high-level design cycle - design in multiple cycles, a layer or product area at a time |
| 4 | First Cycle Design | - Review the requirements. - For the first high-level design cycle, produce the class definitions, relationships, and transition diagrams. - Ensure that interface requirement, both external and internal to the product, are adequately addressed by the design. - Establish bi-directional traceability between requirements and associated high-level design elements. |
| 5 | Subsequent Design Cycles | - Assess the design issues from previous cycles. - Review the current design against the requirements. - Ensure that interface requirement, both external and internal to the product, are adequately addressed by the design. - Produce class definitions, relationships, transition diagrams. - Maintain bi-directional traceability between requirements and associated high-level design elements. - Reassess the design, and recycle as needed. |
| 6 | Integration and System Test Strategies | - Define testing sequence, dependencies, and use cases. - Define normal, limit, and out-of-limit data values. - Define normal, limit, and out-of-limit interface conditions for both external and internal interfaces. - Specify tests for operator normal and error behaviors. - Specify installation and operational tests. - Establish bi-directional traceability between system design elements and associated test cases. |
| 7 | System Design Specification (SDS) | - Document the system design specifications: structural design; development and test strategies; interface, data, and component specifications; and any fix prerequisites and co-requisites. - For each SDS item, establish and maintain bi-directional traceability between the source and lower level specifications, such as the SRS and test plans. |

(continued on next page)

TSP High-Level Design - Script HLD (continued)

| 8 | Design Walkthrough | Conduct a high-level design walkthrough (script MTG and form MTG). - Involve customer, marketing, systems, and test personnel. - Cover the functional, performance, and test specifications. - Rework the design to address identified deficiencies. |
| --- | --- | --- |
| 9 | Design Inspection | Conduct a high-level design inspection (script INS). - Inspect all design, test, performance, interface, and strategy materials, including bi-directional references to source and lower level specifications. - Rework to address identified deficiencies. - Record inspection data on form INS. |
| 10 | SDS Baseline | Submit the SDS to the CCB for entry in the system baseline. |
| 11 | Postmortem | Follow script PM to conduct the phase postmortem. |

| Exit Criteria | - A completed, inspected, corrected, and baselined SDS - Component functional, performance, and test specifications - Forms INS, ITL, LOGD, LOGT, MTG, PIP, SUMP, SUMQ - Requirements plan, actual, and earned-value data recorded and entered in the project notebook (specification NOTEBOOK) |
| --- | --- |

| TSP Implementation - Script IMP |  |
| --- | --- |
| Purpose | To produce high-quality system components |
| Entry Criteria | - A detailed next-phase plan and a current list of project risks and exposures - Inspected and baselined SRS, EDS, and SDS documents - Forms: INS, ITL, LOGD, LOGT, PIP, SUMP, SUMQ - Specification: NOTEBOOK |
| General | During the (re)launch process, team members create detailed processes to be followed by each team member. At a minimum, these processes will include personal reviews and inspections |

| Step | Activities | Description |
| --- | --- | --- |
| 1 | Component Plan | Produce an implementation plan for each component and each fix. - Use personal or team data for the size, time, and defect estimates. Organizational data can be used when no personal or team data is available. - Produce a cycle development plan. - Record the SDS, EDS, or SRS reference for each function. - Complete forms SUMP, SUMQ. |
| 2 | Detailed Design | For each component and each fix - Produce the detailed design and unit test plan (script IMP6). - Map detailed design elements to associated high level design elements and requirements. - Conduct a design review, using the team's standard design verification methods and a personal review checklist. - Record design time, product size, review time, and review defects (forms LOGD, LOGT, SUMP, SUMQ). |
| 3 | Detailed Design Inspection | - Have team members conduct a DLD inspection (script INS). - Record inspection data (form INS). |
| 4 | Coding | - Produce the component and fix source code. - Using a personal checklist, conduct a code review and update the design. - Compile the code until it compiles without error. - Record coding time, product size, review time, and review defects (forms LOGD, LOGT, SUMP, SUMQ). |
| 5 | Code Inspection | - Have team members do a code inspection (script INS). - Record inspection data (form INS) |
| 6 | Unit Test | Follow script IMP6 - develop the unit tests cases and data, and conduct the unit tests - record unit test data (forms LOGD, LOGT, SUMP, SUMQ) |
| 7 | Component Release | - When component implementation is complete, release the component to the support manager. - The support manager enters the component in the configuration management system and releases to test, when appropriate. |
| 8 | Component Postmortem | For each component, the implementing engineer conducts a postmortem to ensure that all work is completed and the data are properly recorded. |
| 9 | Product Baselines | Submit the products to the CCB for entry into the system baseline. |

| Exit Criteria | - All components implemented, inspected, and accepted - INS, ITL, PIP, SUMP, SUMQ forms - Implementation plan, actual, and earned-value data recorded and entered in project notebook (specification NOTEBOOK) |
| --- | --- |

| TSP Unit Test and Test Development - Script IMP6 |  |
| --- | --- |
| Purpose | - To guide you in unit testing fixes, modules, or components - While all defects should already have been found, thorough unit testing ensures that few if any defects remain. - Care is warranted because defects missed in unit test can take five to 40 hours each to find in later testing. |
| Entry Criteria | - The fix, module, or component program has been developed, reviewed, compiled, and inspected. - Forms: LOGD, LOGT, SUMP, SUMQ |
| General | - If properly done, unit testing can find all remaining defects. - It is important to carefully review and retest every test fix. - Errors are much more likely with test fixes than new code. |

| Step | Activities | Description |
| --- | --- | --- |
| 1 | Unit Test Development | - Develop a test plan to cover steps 2 through 8 of this script with a minimum of test case and testing duplication. - Develop the required test cases and test data. - Map the test cases and test data to detailed design elements and associated requirements. - Review the test materials to ensure that they are not defective. - A careful review of the test materials will save time since test case defects are generally harder to find and take longer to fix than product defects. |
| 2 | Scenario Tests | Test all the use case scenarios. |
| 3 | Logic Tests | - Test every logic branch path. - Test every condition of every case statement. - Verify the proper stepping and termination of every loop. - Check for pointer allocate, free, null, and stepping problems. |
| 4 | Interface Tests | Check the proper behavior of every interface. - proper returns for all input cases - the types match - interface error conditions handled as specified, etc. |
| 5 | Error Tests | Test all program error conditions. - improper values or types - overflow and underflow - integer, long integer, precision problems, etc. |
| 6 | Variable Tests | Check every variable and parameter value - at nominal, maximum, and minimum values - above the upper specified value - below the minimum specified value - for proper operation with 0, no input, incorrect data type, etc. |
| 7 | Device Tests | Check for proper device operation. - printers, displays, inputs, sensors, etc. - normal and incorrect operation: no paper, jam, power off, etc. |
| 8 | Other Tests | Check other important product specifications. - buffer size, limits, and overflow - throughput performance and response time - data rates and limits - dates and date calculations - security, compatibility, conversion, installation, recovery |

| Exit Criteria | - A completed unit test, with all defects fixed - Unit test data entered in forms LOGD, LOGT, SUMP, SUMQ |
| --- | --- |

| TSP Inspection Script - Script INS |  |
| --- | --- |
| Purpose | - To help team members produce quality products and product fixes - To identify poor quality products for rework or redevelopment |
| Entry Criteria | - A completed and personally reviewed high-quality product - The requirements and/or design documents are available. - The producer's personal process data: size, defects, and time - All inspection participants are present. - Forms: LOGT, INS |
| General | - Inspection roles are defined in the Inspection Roles and Responsibilities - The purpose of inspections is to focus on sophisticated design issues, not on finding simple defects. - Even a few simple defects can distract reviewers so they are more likely to miss sophisticated design issues. - In general, one of the reviewers performs the role of the moderator. - For large inspections with more than 5 reviewers, the moderator should not be a reviewer. - The producer developed the product. He or she - arranges with a qualified moderator to lead the inspection - provides the product briefing and supplies the product materials - answers product questions during the inspection process - fixes the identified defects and verifies the defect fixes - A qualified moderator - leads the inspection process and chairs the inspection meeting - reports the inspection results and data (form INS) - The reviewers are usually other engineers who work on the project. - The recorder and timekeeper supply meeting data to the moderator for the inspection report. - The recorder records the defect data on a visible medium. - The timekeeper keeps track of the meeting time. |

| Step | Activities | Description |
| --- | --- | --- |
| 1 | Preliminary Review | - Before starting the inspection process, the moderator - reviews the product to ensure it is of inspection quality - notes all defects found during this review - does not tell the developer about the defects found - may ask a reviewing engineer to do this review. - If the product is of high quality, it is inspected. If not, the developer is asked to re-review the product, record all defects found, and resubmit the product for the inspection. - When the developer resubmits the product, use the quality projection methods on form INS to estimate product quality. - Until the product is of reasonable quality, it is not inspected. |

(continued on next page)

| TSP Inspection Script - Script INS (continued) |  |  |
| --- | --- | --- |
| Step | Activities | Description |
| 2 | Inspection Briefing | - A briefing meeting is only required when the reviewers are unfamiliar with the products being produced. When a briefing meeting is needed: - The moderator verifies that the inspection entry criteria have been met, or defers the briefing meeting until they are met. - reviews the inspection process and meeting roles (script MTG) - The producer familiarizes the inspection team with the product. - When a meeting is not required, the moderator assigns the following; else it is decided during the briefing meeting. - The reviewers select viewpoints or areas for product concentration. - example viewpoints: operation, recovery, maintenance, security, installation, size, performance - In design inspections, the reviewers also ensure that at least one reviewer will - verify each segment of the design - use a trace table, state machine, or other design analysis method on every design segment - The moderator schedules the inspection meeting. |
| 3 | Inspection Preparation | - The reviewers separately make detailed product reviews, and mark their defects on the product documentation. - The reviewers concentrate on selected viewpoints or product areas. - The reviewers record preparation time in their individual form LOGT and record defect data to bring to the inspection meeting. |
| 4 | Inspection Meeting: Opening | The moderator opens the inspection meeting and - if any reviewers are not prepared, reschedules the meeting - outlines the inspection meeting procedure - selects the timekeeper and recorder - enters the inspection preparation data on form INS |
| 5 | Product Walk-through | - The reviewers review each section of the product materials. Each reviewer - describes any defects found in that section - records each defect on form INS - checks form INS for every reviewer who found each defect - resolves questions with the producer and other reviewers - does not attempt to solve or fix defects during the inspection - The recorder verifies each defect report with the reviewers. - This process continues until all materials have been reviewed. |
| 6 | Defect Check | After all issues have been discussed and defects recorded - The moderator asks the reviewers for any unrecorded defects. - Each new defect is clarified, recorded, and verified as before. |

(continued on next page)

| TSP Inspection Script - Script INS (continued) |  |  |
| --- | --- | --- |
| Step | Activities | Description |
| 7 | Estimating Remaining Defects | - After all defects are entered, count the major defects that each reviewer found, and that no other reviewer found (the reviewer's unique defects). - Identify the engineer who found the most unique defects. - Check the defects that reviewer found in column A. - In column B, check all of the defects found by the other reviewers. - Count the common defects (C) between columns A and B. - The estimated number of defects in the product is AB/C. - Round fractional results to the nearest integer. - The number of defects found in the inspection is A+B-C. - Number remaining: total less the number found: (AB/C)-A-B+C. - This defect estimate is only reliable when all the numbers A and B are greater than 4 and A-C, and B-C are both greater than 1. - Even with these criteria, estimate error is likely 10% or more. - Generally, larger numbers, give more reliable estimates. - If A=B=C, you are likely to have found all the defects. - If several reviewers found the most unique defects, repeat these calculations, using each of these reviewers as A, and use the largest resulting number as the total defect estimate. - Enter total meeting time, inspection hours, and inspection rate. |
| 8 | Inspection Meeting: Conclusion | - The team decides if a reinspection is needed and who will do it. - The reviewers decide how to verify the defect corrections. - The recorder and moderator complete form INS. |
| 9 | Product Rework and Verification | The producer makes repairs and updates documentation. - holds needed re-reviews and/or re-inspections - has the fixes verified as the reviewers recommended in step 8 |

| Exit Criteria | - Form INS completed and recorded in the project notebook (specification NOTEBOOK) - A fully inspected and high-quality product |
| --- | --- |

| TSP Team Launch - Script LAU |  |
| --- | --- |
| Purpose | To guide teams in launching a software-intensive project |
| Entry Criteria | - The launch preparation work has been completed (script PREPT and checklists PREPL, PREPT). - All team members and the team leader are committed to attend launch meetings 1 through 9 and the launch postmortem, and management and marketing representatives are prepared and available for meetings 1 and 9. - A certified TSP coach is on hand to lead the launch process. |
| General | Day; 1; 2; 3; 4. Timing; 8:30-6:45; 8:00-5:00; 8:30-5:30; 8:30-4:30. Meetings; 1, 2, and 3; 3 (cont.), 4, 5, and 6; 6 (cont.), 7 and 8; 9 and PM. Notional schedule can be compressed or extended to meet scope of launch |

| Step | Activities | Description |
| --- | --- | --- |
| 1 | Project and Management Objectives | Hold team launch meeting 1 (script LAU1). - Review the launch process and introduce team members. - Discuss the project goals with management and marketing. |
| 2 | Team Goals and Roles | Hold team launch meeting 2 (script LAU2). - Define and document the team's goals. - Allocate team roles among team members. |
| 3 | Project Strategy and Support | Hold team launch meeting 3 (script LAU3). - Produce a system conceptual design, and, if needed, a fix list. - Determine the development strategy and products to be produced. - Define the development process to be used. - Produce the process and support plans. |
| 4 | Overall Plan | Hold team launch meeting 4 (script LAU4). - Develop size estimates and the overall team plan. |
| 5 | Quality Plan | Hold team launch meeting 5 (script LAU5). - Develop the quality plan. |
| 6 | Balanced Plan | Hold team launch meeting 6 (script LAU6). - Allocate work to team members. - Produce bottom-up next-phase or cycle plans for each team member. - Produce a balanced next-phase or cycle plan for the team and each team member. |
| 7 | Project Risk Analysis | Hold team launch meeting 7 (script LAU7). - Identify and evaluate project risks. - Define risk assessment checkpoints and responsibilities. - Propose mitigation actions for near-term, high-impact risks. |
| 8 | Launch Report Preparation | Hold team launch meeting 8 (script LAU8). - Prepare a launch report for management. |
| 9 | Management Review | Hold team launch meeting 9 (script LAU9). - Review the launch report with management. - Discuss project risks, responsibilities, and planned actions. |
| PM | Launch Postmortem | Hold team launch postmortem meeting (script LAUPM). - Gather launch data and produce a launch report. - Put the launch report in the project notebook. - Assess the launch process and prepare PIPs. |

| Exit Criteria | - The launch is completed with documented team and team member plans. - Team roles, goals, processes, and responsibilities are defined. - Management agrees with the team plan, or resolution actions have been identified and responsibilities assigned. - The launch data are in the project notebook (NOTEBOOK specification). |
| --- | --- |

| TSPm Team Launch - Script LAUm |  |
| --- | --- |
| Purpose | To guide multi-teams in conducting a TSP launch workshop |
| Entry Criteria | - The launch preparation work has been completed (scripts PREP and PREPW). - For the launch, the management and customer representatives are prepared and available for meetings 1 and 9. - All team members and the team leader are committed to attend launch meetings 1 through 9 and the launch postmortem. - For distributed teams, meetings 1, 1A, and 9 are held via videoconference at all team locations. - A certified TSP coaches are on hand at all team locations. |
| General | Day; 1; 2; 3; 4; 5. Meeting; 1, 2, and 3; 3 and 4; 4 and 5; 6 and 7; 8, 9, and PM. - Notional schedule can be compressed or extended to meet scope of launch. |

| Step | Activities | Description |
| --- | --- | --- |
| 1 | Management and Customer Objectives | - Hold launch meeting 1 (script LAU1). - Review the launch process and introduce team members. - Discuss the team’s goals with management and customer representatives. |
| 1A | Project Strategy and Sub-team Responsibilities | - The leadership team presents the project strategy (script LAU1A). - product conceptual design - overall development strategy - sub-team product responsibilities - roles and role manager team responsibilities - other significant issues |
| 2 | Team Goals and Roles | - Hold sub-team launch meetings 2 (script LAU2). - Select sub-team roles and backup roles. - Define and document the sub-team's goals. |
| 3 | Project Strategy and Support | - Hold sub-team launch meetings 3 (script LAU3). - Review and adjust the system conceptual design. - Review and adjust the development strategy. - Consider the product assignments and make recommendations for needed changes. - Define and document the team processes. - Produce the process and support plans. |
| 3A | Leadership Meeting: Status | - The leadership team meets to review launch status (script LAU3A). - Review launch status and resolve issues. - If not done during launch preparation, review role assignments and name the interim lead role manager for each role manager team. |
| 4 | Overall Plan | - Hold sub-team launch meetings 4 (script LAU4). - Develop size estimates and the overall sub-team plans. |
| 5 | Quality Plan | - Hold sub-team launch meetings 5 (script LAU5). - Develop the sub-team quality plans. |
| 5A | Leadership Meeting: Status | - The leadership team reviews launch status and resolves issues (script LAU3A). |
| 5B | Role Manager Meeting: Planning | - The planning managers hold launch meeting 5B (script LAU5B). - Consolidate the overall team plan. - Identify issues and interdependencies among the teams. - Establish the committed and required dates for these dependencies. - Establish responsibilities for handling the identified issues. - Log the issues in ITL. |

(continued on next page)

| TSPm Distributed Team Launch - Script LAUm (continued) |  |  |
| --- | --- | --- |
| Step | Activities | Description |
| 5C | Role Manager Meeting: Quality | - The quality role managers hold launch meeting 5C (script LAU5C). - Resolve issues among the quality plans. - Consolidate the quality plans into an overall quality plan. |
| 6 | Balanced Plan | - The sub-teams hold launch meeting 6 (script LAU6). - Review work allocations to the team members. - Review the bottom-up next-phase or cycle plans for each team member. - Produce a balanced next-phase or cycle plan for each sub-team and each team member. |
| 6A | Leadership Meeting: Status | - The leadership team reviews launch status and resolves issues (script LAU3A). |
| 6B | Planning Manager Meeting: Balanced Plan | - The planning role managers hold launch meeting 6B (script LAU6B). - Consolidate the sub-team bottom-up plans into a team plan. - Determine if load balancing is required among the sub-teams. - Recommend needed adjustments. |
| 7 | Project Risk Analysis | - The sub-teams hold launch meetings 7 (script LAU7). - Identify and evaluate project risks. - Define risk assessment checkpoints and responsibilities. - Propose mitigation actions for immediate high-impact risks. |
| 7A | Leadership Meeting: Risk Analysis and Report | - The leadership team reviews the sub-team risk assessments and plans for the final management meeting (script LAU7A). - Decide which risks to track at the leadership level. - Make other needed changes or additions. - Define the content of the management presentation. - Identify the work done to prepare the management presentation. - Assign responsibilities for the preparation work. |
| 8 | Sub-team Report Preparation | - The sub-teams hold launch meetings 8 (script LAU8). - Prepare the assigned parts of the launch report to management. |
| 9 | Management Review | - The entire team holds launch meeting 9 (script LAUm9). - Review launch activities and project plans with management. - Discuss project risks, responsibilities, and planned actions. |
| PM | Launch Postmortem | - The sub-teams hold launch postmortem meetings (script LAUPM). - Gather launch data and produce a launch report. - Enter this report in the project notebook. - Assess the launch process and prepare PIPs. |

| # Exit Criteria | - Launch completed with documented team and member plans - Defined team roles, goals, processes, and responsibilities - Management agreement with the team plan - Resolution actions identified and responsibilities assigned - Launch data filed in the project notebook (specification NOTEBOOK). |
| --- | --- |

| TSP Launch Meeting 1 - Script LAU1 |  |
| --- | --- |
| Purpose | To review management goals and product objectives with the team |
| Entry Criteria | - The team and team leader are prepared. - All participants are present (TSP coach, team members, team leader, management and marketing representatives). - Forms: MTG, ITL, PIP |
| General | Meeting 1 generally takes from 1 to 2 hours. |

| Step | Activities | Description |
| --- | --- | --- |
| 1 | TSP and Launch Overview Meeting Role Assignments | The TSP coach leads the meeting (script MTG). The TSP coach - describes the TSP launch process and the launch products - reviews the TSP team roles - reviews the meeting roles and assigns a timekeeper and recorder (specification ROLE) - discusses the work to be done in this meeting |
| 2 | Project Goals | A senior management representative - describes the business reasons for wanting to do this project - describes the business goals for the project - answers the team's questions |
| 3 | Goal Questions | The team members should satisfy themselves that they understand the project goals (Team Member Meeting 1 Discussion Guidelines). - management's goals for the project - the reasons for these goals - how management will measure goal attainment - management's minimum and ideal goals for the project |
| 4 | Product Objectives | A marketing or customer representative - describes the characteristics of the desired product - summarizes the customers' needs for the product - compares these needs with competitive offerings - answers the team's questions |
| 5 | Product Questions | The team members should satisfy themselves that they understand the product objectives (Team Member Meeting 1 Discussion Guidelines). - users' and customer's needs - any items that are especially important to the customer |
| 6 | Launch Meeting Documentation | The recorder completes form MTG. - lists the attendees and the time spent by agenda item - describes decisions made and by whom - documents pending actions: what, when, and by whom - verifies the meeting report with the meeting attendees - saves the completed form MTG to give to the planning manager in launch meeting 2 |

| Exit Criteria | - Launch meeting 1 activities have been completed. - The team understands the customer's needs and management's goals. - All of the team's questions have been answered, or actions are planned to get answers for the team. - All issues have been recorded (form ITL). - All process improvement suggestions have been recorded (form PIP). - The meeting report has been completed (form MTG and attachments). - The planning manager has copies of all meeting products. |
| --- | --- |

| TSPm Launch Meeting 1A - Script LAU1A |  |
| --- | --- |
| Purpose | - The entire team meets to - review the project strategy with all project team members - divide the overall team into sub-teams of about 3 to 15 members - provide these sub-teams with sufficient guidance so they can plan their portions of the overall project - establish mechanisms for these sub-teams to coordinate their work and adjust their responsibilities as they learn more about the project |
| Entry Criteria | - The entire team has participated in launch meeting 1. - For distributed teams, remote locations participate via videoconference. - Forms: MTG, ITL |
| General | - Meeting 1A takes from 1 to 2 hours. |

| Step | Activities | Description |
| --- | --- | --- |
| 1 | Meeting Role Assignments | - Select the meeting roles (specification ROLE). - The lead TSP coach leads the meeting (script MTG). - The timekeeper tracks time and keeps the meeting on schedule. - The recorder notes meeting decisions and actions and writes the meeting report (form MTG). |
| 2 | Meeting Overview | - The project manager briefly summarizes the meeting purpose and agenda. |
| 3 | Overall Development Strategy | - The project manager or designee describes the project strategy. - version structure and contents - principal prototype activities and objectives - integration and system testing approach |
| 4 | Conceptual Design | - The design team describes the overall product conceptual design. - key product elements and their principal functions - major interfaces and dependencies among the elements |
| 5 | Product Responsibilities | - The project manager or designee describes the product elements that each sub-team is initially responsible for planning and developing. |
| 6 | Prototyping Responsibilities | - The project manager or designee describes the prototypes that each sub-team is initially responsible for planning and developing. |
| 7 | Required Team Roles | - The project manager or designee lists the roles required for this project. - The standard TSP roles are: customer interface manager, design manager, implementation manager, test manager, quality manager, process manager, support manager, planning manager. - Possible additional role responsibilities are: security manager, configuration control manager, performance manger, etc. |
| 8 | Team Role Responsibilities | - The project manager or designee summarizes the responsibilities that the leadership team has assigned to each role manager team. |
| 9 | Discussion | - The project manager asks for questions and discussion. |
| 10 | Launch Meeting Documentation | - The recorder gives the completed form MTG to the TSP coach. - lists the attendees and the time spent by agenda item - describes decisions made and by whom - documents pending actions: what, when, and by whom - verifies the meeting report with the meeting attendees |

| # Exit Criteria | - Launch meeting 1A activities have been completed. - Each sub-team understands its assigned responsibilities for launch planning and product development. - Each role manager team understands its responsibilities. - All issues recorded on ITL forms. - The meeting report (form MTG and any attachments) has been completed. - The Planning Manager has copies of all meeting products. |
| --- | --- |

| TSP Launch Meeting 2 - Script LAU2 |  |
| --- | --- |
| Purpose | To guide the team in setting goals and establishing roles |
| Entry Criteria | - All participants are present (TSP coach, team members, team leader). - Forms: GOAL, ITL, MTG, PIP, ROLE, ROLEMX |
| General | Meeting 2 generally takes 3 to 5 hours. |

| Step | Activities | Description |
| --- | --- | --- |
| 1 | Meeting Roles | Select the meeting roles (specification ROLE). - The TSP coach leads the meeting (script MTG). - The timekeeper tracks time and keeps the meeting on schedule. - The recorder notes meeting decisions and actions and writes the meeting report (form MTG). |
| 2 | Meeting Overview | The TSP coach reviews the work to be done in this meeting and the products to be produced. |
| 3 | Review Management's Stated Goals | The team leader leads the team in reviewing management's goals to - get agreement on what management stated as the goals - identify one or more measure for the key management goals - record results on form GOAL |
| 4 | Implied Goals | The team leader leads the team in defining the goals that are implied by management's stated goals. Considerations include customer satisfaction, financial performance, and competitive capability. |
| 5 | Team Goals | The team leader leads the team in - establishing team goals to meet management's stated and implied goals - defining product, process, quality, and project goals - identifying one or more measures for each key team goal - record results on form GOAL |
| 6 | Team Role Selection | The team uses the procedure given with form ROLEMX to - review the team roles - allocate the roles among the team members - identify an alternate for each role - document the role assignments (form ROLE) - Note that the team leader generally is not assigned any of the TSP team roles. |
| 7 | Goal Tracking | The team leader leads the team in - assigning team-member tracking responsibility for each goal - recording the assignments on form GOAL - establishing a tracking schedule for each goal - Note that role assignments may determine goal-tracking responsibility. |
| 8 | Launch Meeting Documentation | The recorder completes form MTG. - lists the attendees and the time spent by agenda item - describes decisions made and by whom - documents pending actions: what, when, and by whom - verifies the meeting report with the meeting attendees and gives the completed form MTG to the planning manager. |

| Exit Criteria | - Launch meeting 2 activities have been completed. - Team roles and alternates are documented (form ROLE). - Project goals are documented (form GOAL). - All issues have been recorded (form ITL). - All process improvement suggestions have been recorded (form PIP). - The meeting report has been completed (form MTG and attachments). - The planning manager has copies of all meeting products. |
| --- | --- |

| TSP Launch Meeting 3 - Script LAU3 |  |
| --- | --- |
| Purpose | To help the team produce the development strategy, development process, and support plan |
| Entry Criteria | - All participants are present (TSP coach, team members, team leader). - Documented project goals and team roles are available. - Forms: CIBPS, INV, ITL, MTG, PIP, STRAT, SUMS, SUMTASK, SPDR |
| General | - Meeting 3 generally takes from 3 to 5 hours, depending on project status, product complexity, team size, and the team's TSP experience. - Throughout this meeting many decisions are being made. When important issues are identified which required a decision, time should be taken to determine if a formal evaluation of alternative solutions is needed, in which case the decision analysis and resolution (script DAR) process should be planned for to select the best solution. |

| Step | Activities | Description |
| --- | --- | --- |
| 1 | Meeting Roles | Select the meeting roles (specification ROLE). - The TSP coach leads the meeting (script MTG). - The timekeeper tracks time and keeps the meeting on schedule. - The recorder notes meeting decisions and actions and writes the meeting report (form MTG). |
| 2 | Meeting Overview | The TSP coach reviews the work to be done in this meeting and the products to be produced. |
| 3 | Product Conceptual Design | The design manager leads the team in - producing a conceptual design - defining the principal product components, elements, or features of the conceptual design - making a gross size estimate of each component, element, or feature |
| 4 | Development Strategy | - The team leader leads the team in establishing the project strategy. In developing the project strategy, the team considers - the gross size of each principal product component, element, or feature - whether the product should be developed in one or multiple versions - the general content of each development version - the number of development cycles, and estimated size and hours of each - whether prototypes are needed, when they are needed, and their purpose - critical internal and external dependencies - The results, principal product components or elements, estimated size and development hours, and development cycle, are recorded on form STRAT. |
| 5 | Products Produced | - The team leader leads the team in defining the work products to be produced for the next phase or cycle, and all subsequent phases or cycles. These items are recorded on form SUMS. Examples include - prioritized list of fixes to the existing product - requirements documents and specifications - design documents and specifications - prototypes - principal product elements or components - installation, user, and maintenance manuals - test programs, scripts, data, and plans - When defining the principal product elements or components, use a level of detail that is appropriate for the phase being planned. Subsystems or components are sufficient for the requirements and high-level design phases, and modules or objects may be needed for the implementation phase. The items on form STRAT may be used as a starting point and may be further refined as needed. |

(continued on next page)

| TSP Launch Meeting 3 - Script LAU3 (continued) |  |  |
| --- | --- | --- |
| Step | Activities | Description |
| 6 | Development Process | - The process manager leads the team in defining the development process by reviewing the PSSP (form CIBPS) to determine if the standards meet project needs and if they do not meet the projects needs, how they should be tailored or deviated (form SUMPD). - Define the overall development process up to final delivery. - principal process phases - major activities in each phase - items to be baselined at each phase - Refine the process steps for the next project phase or cycle to sufficient detail to support planning individual tasks that are 10 hours or less. - detailed steps required to produce each of the phase or cycle products - steps required to verify the quality of the inputs and the products - the point at which each product will be baselined - items to be baselined at each phase - Using form INV, make a plan to develop, modify, or obtain each missing development process element. Include the estimated size; estimated hours; the date, phase, or cycle when needed; and who will document the process. Then update form CIBPS. - Using form INV, make a plan for standard process deviations approvals as required (form SPDR). |
| 7 | Process Plan | - The process manager leads the team in identifying any other process elements that are needed. Examples include - design, code, size, naming, and message standards - guidelines for team processes and procedures; i.e. resolving issues, making decisions, approving standards - Make a plan on form INV for each missing process element. - Identify processes in the PSSP (form CIBPS) that requires a deviation request (form SUMPD). The need to deviate occurs when a team finds that how they work does not match the documented process or is not applicable to the project. Then update form CIBPS. - Using form INV, make a plan for standard process deviations approvals as required (form SPDR). - Identify training needs for each process element and make a plan on form INV to obtain training. |
| 8 | Support Plan | - The support manager leads the team in reviewing - the available development and process support tools and facilities, and identifying any that are missing - requirements and design aids - editors, compilers, debug aids, testing tools - defect tracking, configuration management, issue tracking - LOC counting, difference counting, data analysis - the plan for managing the project data, and identifying missing elements - Make a plan on form INV for obtaining each missing item. - Identify training needs for each support item and make a plan on form INV to obtain training. |

(continued on next page)

TSP Launch Meeting 3 - Script LAU3 (continued)

| 9 | Configuration Management Plan | The TSP coach leads the team in identifying the membership of the configuration control board (CCB) and the CCB chair. - The support manager typically chairs the CCB. - Other typical members are the design manager, team leader, and customer interface manager. - The support manager leads the team in creating a configuration management plan by: - identifying all existing configuration items that will be used as a reference or base for implementing the work identified in the current plan and establishing criteria for determining when to place any modifications made under configuration control - identifying new configuration items that will be created as a result of implementing the current plan and establish criteria for determining when to place new items under configuration control - recording the base CI number and CI titles of all identified configuration items in form CIBPS, as well as the product owner of each CI and the criteria for placing new and modified items under configuration management - reviewing the current configuration control mechanisms to ensure they are adequate for controlling existing and newly planned configuration items, and making a plan on form INV to address any identified issues or needs. |
| --- | --- | --- |
| 10 | Role Plan | The TSP coach leads the team in defining the tasks and weekly reporting for each role (see TSP Roles), and records the tasks on form INV. |
| 11 | Launch Meeting Documentation | The recorder completes form MTG. - lists the attendees and the time spent by agenda item - describes decisions made and by whom - documents pending actions: what, when, and by whom - verifies the meeting report with the meeting attendees and gives the completed form MTG to the planning manager |

| Exit Criteria | - Launch meeting 3 activities have been completed. - Development strategy is defined (form STRAT). - List of products to be produced has been recorded (form SUMS). - Overall and detailed development process steps are documented. - Process plan and support plan are documented (form INV). - All issues have been recorded (form ITL). - All process improvement suggestions have been recorded (form PIP). - The meeting report has been completed (form MTG and attachments). - The planning manager has copies of all meeting products. |
| --- | --- |

| TSPm Launch Meeting 3A - Script LAU3A |  |
| --- | --- |
| Purpose | - The leadership team meets to - review launch status - identify and resolve outstanding issues - review the team role assignments - designate the leader for each role manager team |
| Entry Criteria | - The project manager and team leaders participate in launch meeting 3A. - For distributed teams, remote team leaders and coaches participate via telephone or videoconference. - The team role assignments have been made and are available. - Forms: MTG, ITL, |
| General | - Meeting 3A takes from 1 to 2 hours. |

| Step | Activities | Description |
| --- | --- | --- |
| 1 | Meeting Role Assignments | - Select the meeting roles (specification ROLE). - The lead TSP coach leads the meeting (script MTG). - The timekeeper tracks time and keeps the meeting on schedule. - The recorder notes meeting decisions and actions and writes the meeting report (form MTG). |
| 2 | Meeting Overview | - The lead TSP coach reviews the purpose of the meeting and the results to be produced. |
| 3 | Meeting Agenda | - The project manager - reviews the meeting agenda - asks for any changes or additions |
| 4 | Status Review | - Each team leader - reviews the status of his or her team launch - summarizes the principal results to date - identifies problems or issues requiring leadership team attention |
| 5 | Issues Review | - The project manager or designee - leads a discussion of cross team issues - settles issues that can be resolved in the meeting - identifies the team leader responsible for resolving each deferred issue and the date by which it is to be settled - has each deferred issue recorded in the project ITL |
| 6 | Role Manager Team Leaders | - If not already done, the project manager leads a discussion of team roles (see TSPm Role Manager Team Responsibilities and TSPm Lead Role Manager Responsibilities), and identifies the - members assigned to each role - member to be interim leader for each role manager team - team leader who will inform that member of the lead role assignment |
| 7 | Other Items | - The project manager leads the discussion of any other agenda topics. |
| 8 | Launch Meeting Documentation | - The recorder gives the completed form MTG to the project manager. - lists the attendees and the time spent by agenda item - describes decisions made and by whom - documents pending actions: what, when, and by whom - verifies the meeting report with the meeting attendees |

| # Exit Criteria | - Launch meeting activities have been completed. - The status of each team’s launch has been reviewed. - All issues are recorded on ITL forms. - The leader has been identified for each role manager team. - The meeting report has been completed (form MTG and any attachments). - The planning manager has copies of all meeting products. |
| --- | --- |

| TSP Launch Meeting 4 - Script LAU4 |  |
| --- | --- |
| Purpose | To guide the team in producing the overall plan |
| Entry Criteria | - All participants are present (TSP coach, team members, team leader). - The team development strategy and the process and support plans - Forms: INV, ITL, MTG, PIP, SCHED, SUMP, SUMS, TASK - Guideline: Planning |
| General | Meeting 4 generally takes 3 to 5 hours, depending on team size, project status, product complexity, and the team’s TSP experience. |

| Step | Activities | Description |
| --- | --- | --- |
| 1 | Meeting Roles | Select the meeting roles (specification ROLE). - The TSP coach leads the meeting (script MTG). - The timekeeper tracks time and keeps the meeting on schedule. - The recorder notes meeting decisions and actions and writes the meeting report (form MTG). |
| 2 | Meeting Overview | The TSP coach reviews the work to be done in this meeting and the products to be produced. |
| 3 | Size Estimate | - The design manager leads the team in estimating the size of each item on form SUMS. Record the estimates on SUMS. Examples include - requirement pages, design classes, high-level design pages, screen forms, reports, document text pages - program LOC and test case LOC, test and operational data - The size estimates made earlier on form STRAT can be used as a starting point for the estimates on form SUMS. |
| 4 | Determine Project Tasks | - The team leader leads the team in producing a detailed task plan for the near term and a high-level plan for the remainder of the project. - Use the project’s development process defined in meeting 3 as a template for defining tasks for every product element listed on SUMS that meet the detailed plan criteria. - Review the process plan and support plan items documented on form INV and ensure that tasks are also identified to produce these items. - Use the following guidelines for the detailed plan. - The detailed plan generally extends to the end of the next phase or cycle. - The detailed plan tasks are each 10 hours or less per team member. - Use the following guidelines for the high-level plan that covers the remaining project phases and/or cycles. - Tasks for the high-level plan may be of any duration. - At least one task must be defined in the high-level plan for each TSP phase on forms SUMP to produce the quality plan (LAU5). - The planning manager records the tasks on form TASK. |
| 5 | Overall Resource Estimate | - The planning manager leads the team in estimating the resources required for every task defined in step 4. - Use team data, organizational data, or available standards (Planning Guidelines). - When available, use personal, team, and/or organizational data for similar work. - Use methods and data that are appropriate for the level of detail represented by the task. - Enter the time required for each task on form TASK and calculate the total plan task hours for the project. |

(continued on next page)

| TSP Launch Meeting 4 - Script LAU4 (continued) |  |  |
| --- | --- | --- |
| Step | Activities | Description |
| 6 | Resource Availability | - The planning manager leads the team in estimating the aggregate team tasks hours for each project week. Consider - vacations, training, and other assignments - allocation percentages and new members - Enter week schedule hours on form SCHED and calculate the total plan schedule hours until they meet or exceed the total plan task hours on form TASK. |
| 7 | Generate the Overall Plan | The planning manager generates the size and time estimates and the team plan for the entire project. - team task and schedule templates - earned-value plan to the project completion - size and resource data (forms SUMP, SUMS) - Gantt schedule (optional) |
| 8 | Review and Assess Plan | - The team leader leads the team in reviewing the plan to ensure that it - follows the defined strategy - produces the required products - meets the established team goals - addresses all critical internal and external dependencies - includes tasks for every product defined on SUMS or INV - When issues are identified, they are entered on ITL forms and assigned to a team member for tracking. - In the event that all cost, schedule, and functionality goals are not met, consider alternative plans (i.e., increase cost to meet schedule and functionality, or reduce functionality to meet cost and schedule constraints) to present to management. |
| 9 | Launch Meeting Documentation | The recorder completes form MTG. - lists the attendees and the time spent by agenda item - describes decisions made and by whom - documents pending actions: what, when, and by whom - verifies the meeting report with the meeting attendees and gives the completed form MTG to the planning manager |

| Exit Criteria | - Launch meeting 4 activities have been completed. - Overall size and resource estimates are documented (forms SUMP, SUMS, INV). - The overall development plan has been documented. - The earned value plan has been documented (forms TASK and SCHED). - A Gantt schedule has been produced (optional). - All issues have been recorded (form ITL). - All process improvement suggestions have been recorded (form PIP). - The meeting report has been completed (form MTG and attachments). - The planning manager has copies of all meeting products. |
| --- | --- |

| TSP Launch Meeting 5 - Script LAU5 |  |
| --- | --- |
| Purpose | To guide the team in producing the quality plan |
| Entry Criteria | - All participants are present (TSP coach, team members, team leader). - Forms: ITL, MTG, PIP, SUMP, SUMQ, SUMS - Guidelines: Planning, Quality |
| General | Meeting 5 generally takes about 1 hour, depending on team size, project status, product complexity, and the team’s TSP experience. |

| Step | Activities | Description |
| --- | --- | --- |
| 1 | Meeting Roles | Select the meeting roles (specification ROLE). - The TSP coach leads the meeting (script MTG). - The timekeeper tracks time and keeps the meeting on schedule. - The recorder notes meeting decisions and actions and writes the meeting report (form MTG). |
| 2 | Meeting Overview | The TSP coach reviews the work to be done in this meeting and the products to be produced. |
| 3 | Quality Goals | The quality manager leads a review of the team's quality goals (form GOAL). - identifies quality data or uses Quality and Planning guidelines - establishes the quality guidelines for the quality plan |
| 4 | Estimate Defects Injected | Using the quality guidelines and historical data, the quality manager guides the team in estimating the defects to be injected by phase for each process identified in Meeting 3 (script LAU3). - The planned defects injected for phase P are estimated as the planned hours for phase P times the hourly defect injection rate for phase P. Defects injectedp = Time in phasep* Defect injection ratep - If phase injection rates are not available, the team makes a best estimate. |
| 5 | Estimate Defects Removed | - Using the quality guidelines and historical data, the quality manager guides the team in estimating the defects to be removed by phase for each process identified in Meeting 3 (script LAU3). - The number of defects removed in a phase is the phase defect-removal yield times defects present at the phase divided by 100. - Defects removedp = Defects present in phasep* Phase yieldp / 100 - Defects present in phase are the total defects injected by the end of the phase less the total removed before phase entry. - Defects present in phasep = Defects injected(1…p) - Defects removed(1..p-1) - If phase yields are not available, the team makes a best estimate. |
| 6 | Produce the Quality Plan | - The quality manager leads the team in calculating the remainder of the quality plan (form SUMQ), and in evaluating and adjusting the plan until the team’s quality goals and schedule are met. - evaluating the resulting defect densities and removal rates - making needed adjustments in phase times or yields if goals are not met - recalculating the quality parameters and checking again |
| 7 | Launch Meeting Documentation | The recorder completes form MTG. - lists the attendees and the time spent by agenda item - describes decisions made and by whom - documents pending actions: what, when, and by whom - verifies the meeting report with the meeting attendees and gives the completed form MTG to the planning manager |

| Exit Criteria | - Launch meeting 5 activities have been completed. - Overall quality plan has been documented (forms SUMP, SUMQ). - All issues have been recorded (form ITL). - All process improvement suggestions have been recorded (form PIP). - The meeting report has been completed (form MTG and attachments). - The planning manager has copies of all meeting products. |
| --- | --- |

| TSPm Launch Meeting 5B - Script LAU5B |  |
| --- | --- |
| Purpose | - The planning manager team meets to - conduct the initial planning manager team meeting - produce a consolidated team plan and dependency issue list |
| Entry Criteria | - The planning managers have been selected for each team. - The leadership team has named the leader for the planning manager team. - For distributed teams, remote planning managers participate via telephone or videoconference. - A TSP coach is available to guide the planning manager team meeting. - Specifications PLAN and ROLE - Forms: MTG, ITL |
| General | - Meeting 5B follows launch meeting 5, with the specific time depending on the availability of all team members and a TSP coach. - Meeting 5B takes from 1 to 2 hours. |

| Step | Activities | Description |
| --- | --- | --- |
| 1 | Meeting Role Assignments | - Select the meeting roles (specification ROLE). - The TSP coach leads the meeting (script MTG). - The timekeeper tracks time and keeps the meeting on schedule. - The recorder notes meeting decisions and actions and writes the meeting report (form MTG). |
| 2 | Meeting Overview | - The TSP coach reviews the purpose of the meeting and the results to be produced. |
| 3 | Consolidate the Team Plan | - The lead planning manager leads the team in - reviewing the plans for each sub-team - deciding which plans should be consolidated into higher level plans - assigning responsibility for producing these consolidations |
| 4 | Identifying Internal Team Dependencies | - The lead planning manager leads the team in - identifying the dependencies each sub-team has on other sub-teams - determining when each item is required and when it is to be available - assigning a person on each team to track that dependency - listing the dependencies, dates, and responsibilities on the ITL |
| 5 | Identifying External Team Dependencies | - The lead planning manager leads the team in - identifying the dependencies each sub-team has on external groups - determining when each item is required and when it is to be available - assigning a person on the sub-team to track that dependency - listing the dependencies, dates, and responsibilities on ITL forms |
| 6 | Reporting | - The lead planning manager leads the team in - deciding what items should be reported to the leadership team - preparing the report - deciding how and when to present the report |
| 7 | Launch Meeting Documentation | - The recorder gives the completed form MTG to the lead planning manager. - lists the attendees and the time spent by agenda item - describes decisions made and by whom - documents pending actions: what, when, and by whom - verifies the meeting report with the meeting attendees. |

| # Exit Criteria | - The consolidated plan prepared or assignments made to prepare it - Team dependencies identified and responsibilities defined - All issues and dependencies have been recorded (form ITL) - The meeting report has been completed (form MTG and attachments). |
| --- | --- |

| TSPm Launch Meeting 5C - Script LAU5C |  |
| --- | --- |
| Purpose | - The quality manager team meets to - conduct the initial quality manager team meeting - identify quality issues and produce a consolidated quality plan |
| Entry Criteria | - The quality managers have been selected for each team. - The leadership team has named the leader for the quality manager team. - For distributed teams, remote quality managers participate via telephone or videoconference. - A TSP coach is available to guide the quality manager team meeting. - Specifications QUAL and ROLE - Forms: MTG, ITL |
| General | - Meeting 5C follows launch meeting 5, with the specific time depending on the availability of all team members and the TSP coach. - Meeting 5C takes from 1 to 2 hours. |

| Step | Activities | Description |
| --- | --- | --- |
| 1 | Meeting Role Assignments | - Select the meeting roles (specification ROLE). - The TSP coach leads the meeting (script MTG). - The timekeeper tracks time and keeps the meeting on schedule. - The recorder notes meeting decisions and actions and writes the meeting report (form MTG). |
| 2 | Meeting Overview | - The TSP coach reviews the purpose of the meeting and the results to be produced. |
| 3 | Review Team Quality Plans | - The lead quality manager leads the team in - reviewing the quality plans for each sub-team - identifying areas where the plans do not meet the team goals - deciding where changes are required and the changes to recommend - assigning responsibility for getting the changes made - recording the item in the ITL as an issue to be tracked |
| 4 | Consolidate the Team Quality Plan | - The lead quality manager leads the team in - deciding which plans should be consolidated into higher level quality plans - assigning responsibility for making these consolidations |
| 5 | Other Items | - The lead quality manager leads the team in - identifying any other issues that need attention across the teams - deciding how to handle these issues - assigning responsibilities for handling and tracking these issues - recording each issue in the ITL |
| 6 | Reporting | - The lead quality manager leads the team in - deciding what items should be reported to the leadership team - preparing the report - deciding how and when to present the report |
| 7 | Launch Meeting Documentation | - The recorder gives the completed form MTG to the lead quality manager. - lists the attendees and the time spent by agenda item - describes decisions made and by whom - documents pending actions: what, when, and by whom - verifies the meeting report with the meeting attendees. |

| # Exit Criteria | - Consolidated quality plan prepared or assignments made to prepare it. - Quality issues identified and responsibilities defined for resolving. - All quality issues have been recorded (form ITL). - The meeting report has been completed (form MTG and attachments). |
| --- | --- |

| TSP Launch Meeting 6 - Script LAU6 |  |
| --- | --- |
| Purpose | To help the team produce a balanced next-phase or cycle plan |
| Entry Criteria | - All participants are present (TSP coach, team members, team leader). - Documented process, quality, and support plans are available. - Documented overall plan has been prepared. - Overall and next-phase or cycle effort estimates are available. - Forms: CIBPS, SCHED, TASK, INV, ITL, MTG, PIP, SUMP, SUMQ, SUMS |
| General | Meeting 6 generally takes 3 to 5 hours, depending on team size, project status, product complexity, and team TSP experience. |

| Step | Activities | Description |
| --- | --- | --- |
| 1 | Meeting Roles | Select the meeting roles (specification ROLE). - The TSP coach leads the meeting (script MTG). - The timekeeper tracks time and keeps the meeting on schedule. - The recorder notes meeting decisions and actions and writes the meeting report (form MTG). |
| 2 | Meeting Overview | The TSP coach reviews the work to be done in this meeting and the products to be produced. |
| 3 | Allocate Tasks to Team Members | - The team allocates the tasks for the next phase or cycle to individual team members using the following guidelines. - The team and team leader review the tasks for the next phase, and allocate these tasks among the team members. - The team may do load balancing during task allocation, or may do load balancing after each team member has produced their individual plans. - To maintain a balanced workload while allocating tasks, the team works through the plan one week at a time. - agrees on which team member will do each task - maintains a balanced workload among the team members |
| 4 | Build Bottom-up Plans | - Using personal data where possible, each team member - assesses his or her work and adds any role tasks - subdivides tasks longer than about 10 hours into smaller steps - produces personal task, schedule, and earned value plans |
| 5 | Review and Rebalance Team Workload | The planning manager leads the team review of the bottom-up plans. - ensures that the quality criteria are met - resolves conflicts, duplications, dependency issues, and critical path conflicts - rebalances tasks until a minimum schedule is achieved |
| 6 | Produce the Next-Phase or Cycle Development Plan | The planning manager combines the bottom-up plans and generates the consolidated next-phase or cycle team plan, which contains - consolidated team size estimates on form SUMS - combined team plan on TASK and SCHED forms - a team earned-value plan for tracking planned value, earned value, and projected earned value by week for the next phase or cycle - an optional Gantt schedule for the next phase or cycle - SUMP and SUMQ forms with size, resource, and quality data for the system and its components (as appropriate for the phase) - In the event that all cost, schedule, and functionality goals are not met, consider alternative plans (i.e., increase cost to meet schedule and functionality, or reduce functionality to meet cost and schedule constraints) to present to management. |

(continued on next page)

| TSP Launch Meeting 6 - Script LAU6 (continued) |  |  |
| --- | --- | --- |
| Step | Activities | Description |
| 7 | Identify CI Release Dates | The planning manager leads the team in reviewing the current project plan to identify completion dates for all new and modified configuration items. The support manager records all expected CI release dates in form CIBPS. |
| 8 | Launch Meeting Documentation | The recorder completed form MTG. - lists the attendees and the time spent by agenda item - describes decisions made and by whom - documents pending actions: what, when, and by whom - verifies the meeting report with the meeting attendees and gives the completed form MTG to the planning manager |

| Exit Criteria | - Launch meeting 6 activities have been completed. - Detailed next-phase or cycle plans for each team member and the team are documented (forms INV, SUMP, SUMQ, TASK, SCHED). - All issues have been recorded (form ITL). - All process improvement suggestions have been recorded (form PIP). - The meeting report has been completed (form MTG and attachments). - The planning manger has copies of all meeting products. |
| --- | --- |

| TSPm Launch Meeting 6B - Script LAU6B |  |
| --- | --- |
| Purpose | - The planning manager team meets to - identify project imbalances that require resource adjustment - produce a consolidated detailed team plan for the next phase or cycle |
| Entry Criteria | - All the team members for all the teams have produced detailed plans for the next project phase or cycle. - The planning managers have these detailed plans. - For distributed teams, remote planning managers participate via telephone or videoconference. - A TSP coach is available to guide the planning manager team meeting. - Forms: MTG, ITL |
| General | - Meeting 6B follows launch meeting 6, with the specific time depending on the availability of all team members and a TSP coach. - Meeting 6B takes from 1 to 2 hours. |

| Step | Activities | Description |
| --- | --- | --- |
| 1 | Meeting Role Assignments | - Select the meeting roles (specification ROLE). - The TSP coach leads the meeting (script MTG). - The timekeeper tracks time and keeps the meeting on schedule. - The recorder notes meeting decisions and actions and writes the meeting report (form MTG). |
| 2 | Meeting Overview | - The TSP coach reviews the purpose of the meeting and the results to be produced. |
| 3 | Review Team Plans | - The lead planning manager leads the team in - reviewing the detailed plans for each sub-team - identifying imbalance problems that might impact other teams - deciding what changes are required to balance the overall team plan - assigning responsibility for making these changes - listing each change as an issue in ITL |
| 4 | Consolidate Team Plans | - The lead planning manager leads the team in - deciding which sub-team detailed plans should be consolidated - assigning responsibility for making these consolidations |
| 5 | Other Items | - The lead planning manager leads the team in - identifying any other planning issues that need attention across the teams - deciding how to handle these issues - assigning responsibilities for handling and tracking these issues - recording each issue in the ITL |
| 6 | Reporting | - The lead planning manager leads the team in - deciding what items should be reported to the leadership team - preparing the report - deciding how and when to present the report |
| 7 | Launch Meeting Documentation | - The recorder gives the completed form MTG to the lead planning manager. - lists the attendees and the time spent by agenda item - describes decisions made and by whom - documents pending actions: what, when, and by whom - verifies the meeting report with the meeting attendees. |

| # Exit Criteria | - Team workload imbalances identified and responsibilities defined. - Consolidated plan prepared or assignments made to prepare it. - All issues have been recorded (form ITL). - The meeting report has been completed (form MTG and attachments). |
| --- | --- |

| TSP Launch Meeting 7 - Script LAU7 |  |
| --- | --- |
| Purpose | To guide the team through a project risk assessment |
| Entry Criteria | - All participants are present (TSP coach, team members, team leader). - Documented overall and next-phase development plan are available. - Forms: ITL, MTG, PIP |
| General | - A risk is something that may or may not happen. Something that is certain is an issue, not a risk. - Meeting 7 generally takes 1 to 2 hours, depending on project dynamics. |

| Step | Activities | Description |
| --- | --- | --- |
| 1 | Meeting Roles | Select the meeting roles (specification ROLE). - The TSP coach leads the meeting (script MTG). - The timekeeper tracks time and keeps the meeting on schedule. - The recorder notes meeting decisions and actions and writes the meeting report (form MTG). |
| 2 | Meeting Overview | The TSP coach reviews the work to be done in this meeting and the products to be produced. |
| 3 | Risk Identification | The team leader asks the team to identify risks. - All team members participate in suggesting risks. - Use a brainstorm approach; i.e., do not evaluate risks during this step. - The process continues until no one can think of any more risks. - Record each risk to aid subsequent evaluation by the team. |
|  | Impact Evaluation | For each risk, the team evaluates its likely impact. - Impact is high if the project schedule impact would be high. - Risks may also have medium or low schedule impact. |
|  | Likelihood Evaluation | For each risk, the team judges its likelihood. Likelihood is also measured as high, medium, or low. |
|  | Source | For each risk, the team determines the source of the risk based on the risk categories. - Engineering: Requirements, Design, Code & Unit Test, Integration & Test, or Engineering Specialties - Development Environment: Development Process, Development System, Management Process, Management Methods, or Work Environment - Program Constraints: Resources, Contract, or Program Interfaces |
|  | Assign Risks | For the high and medium priority risks (i.e., high-high, high-medium, medium-high, or medium-medium), the team - assigns a member to track the risk - sets a date by which mitigation action must be taken - documents the risk, responsibility, and flag date on form ITL |
| 4 | Risk Mitigation | For the high and medium priority risks, identify those that are near-term. - Determine an effective mitigation plan. - Recommend actions to reduce or eliminate risk impact. - If multiple mitigation plans are available, determine if the risk warrants a formal evaluation. If it does, then update plans to execute the decision analysis and resolution process (script DAR). |
| 5 | Launch Meeting Documentation | The recorder completes form MTG. - lists the attendees and the time spent by agenda item - describes decisions made and by whom - documents pending actions: what, when, and by whom - verifies the meeting report with the meeting attendees and gives the completed form MTG to the planning manager |

(continued on next page)

TSP Launch Meeting 7 - Script LAU7 (continued)

| Exit Criteria | - Launch meeting 7 activities have been completed. - All risks and issues are documented (form ITL). - The high-priority risks have mitigation plans. - All process improvement suggestions have been recorded (form PIP). - The meeting report has been completed (form MTG and attachments). - The planning manger has copies of all meeting products. |
| --- | --- |

| TSPm Launch Meeting 7A - Script LAU7A |  |
| --- | --- |
| Purpose | - The leadership team meets to - review launch status and to identify and resolve issues - review the sub-team risk assessments - plan for the management meeting |
| Entry Criteria | - The project manager and team leaders participate in launch meeting 7A. - For distributed teams, remote team leaders and coaches participate via telephone or videoconference. - The team risk assessments have been made and are available. - Forms: MTG, ITL |
| General | - Meeting 7A follows immediately after launch meeting 7. - Meeting 7A takes from 1 to 2 hours. |

| Step | Activities | Description |
| --- | --- | --- |
| 1 | Meeting Role Assignments | - Select the meeting roles (specification ROLE). - The TSP coach leads the meeting (script MTG). - The timekeeper tracks time and keeps the meeting on schedule. - The recorder notes meeting decisions and actions and writes the meeting report (form MTG). |
| 2 | Meeting Overview | - The lead TSP coach reviews the purpose of the meeting and the results to be produced. |
| 3 | Meeting Agenda | - The project manager - reviews the meeting agenda - asks for changes or additions |
| 4 | Status Review | - Each team leader - reviews the status of his or her team launch - summarizes the principal results to date - identifies problems or issues requiring leadership team attention |
| 5 | Risks Review | - The project manager asks the team leaders to - discuss the major risks the teams have identified - decide which if any risks should be tracked at the project level - decide if any risk evaluations should be changed - identify any additional risks that should be tracked - assign responsibilities for tracking any newly identified risks - record any new or changed risks in the project ITL |
| 6 | Planning for the Management Meeting | - The project manager reviews the agenda items for the management meeting. - discusses the material to be covered (specification STATUS) - assigns the preparation work |
| 7 | Other Items | - The project manager leads the discussion of any other agenda topics. |
| 8 | Launch Meeting Documentation | - The recorder gives the completed form MTG to the project manager. - lists the attendees and the time spent by agenda item - describes decisions made and by whom - documents pending actions: what, when, and by whom - verifies the meeting report with the meeting attendees |

| # Exit Criteria | - The status of each team’s launch reviewed. - All risks and issues are documented (form ITL). - Assignments made for preparing the management report presentation. - The meeting report has been completed (form MTG and any attachments). |
| --- | --- |

| TSP Launch Meeting 8 - Script LAU8 |  |
| --- | --- |
| Purpose | To guide the team in preparing for the management meeting (LAU9) |
| Entry Criteria | - All participants are present (TSP coach, team members, team leader). - All team members have copies of - personal task and schedule spreadsheets - team task and schedule spreadsheets - project goals and role assignments - risk evaluation, assessments, and mitigation plans - Forms: ITL, MTG, PIP - Guideline: Management Briefing Guideline - Specifications: NOTEBOOK and STATUS |
| General | - In the management meeting (meeting 9), the team will - review the launch process and launch products - review the project plan and any questions or issues with this plan - demonstrate to management that they have made a thoughtful, realistic, and complete plan. - Meeting 8 generally takes 1 to 2 hours, depending on team size, project status, product complexity, and the team’s TSP experience. Additional time is needed to prepare materials for the management meeting (meeting 9). |

| Step | Activities | Description |
| --- | --- | --- |
| 1 | Meeting Roles | Select the meeting roles (specification ROLE). - The TSP coach leads the meeting (script MTG). - The timekeeper tracks time and keeps the meeting on schedule. - The recorder notes meeting decisions and actions and writes the meeting report (form MTG). |
| 2 | Meeting Overview | The TSP coach reviews the objectives and procedure for the meeting, and describes the example contents of the management presentation. |
| 3 | Determine Plan Dates | The planning manager leads the team in establishing an initial schedule for all known meetings, including: - time and day of weekly team meeting - team checkpoints - status reporting to management - milestone reviews - phase and project postmortems |
| 4 | Planning for the Management Meeting | - The team leader reviews each agenda item for the management meeting (guideline Management Briefing and script LAU9). - discusses the material to be covered - decides what to present and who will present it - assigns the preparation work to one or more team members - The team leader recommends what to present, but the team should be in agreement. |
| 5 | Management Meeting Preparation | The team leader summarizes - the work to be done - who will produce each item - the times when the items will be completed - who will present each item |
| 6 | Launch Meeting Documentation | The recorder completes form MTG. - lists the attendees and the time spent by agenda item - describes decisions made and by whom - documents pending actions: what, when, and by whom - verifies the meeting report with the meeting attendees and gives the completed form MTG to the planning manager |

(continued on next page)

TSP Launch Meeting 8 - Script LAU8 (continued)

| Exit Criteria | - Launch meeting 8 activities have been completed. - The management meeting topics were decided and the preparation work planned. - All issues have been recorded (form ITL). - All process improvement suggestions have been recorded (form PIP). - The meeting report has been completed (form MTG and attachments). - The planning manger has copies of all meeting products. |
| --- | --- |

| TSP Launch Meeting 9 - Script LAU9 |  |
| --- | --- |
| Purpose | To guide the team through the final launch management meeting |
| Entry Criteria | - All participants are present (TSP coach, team members, team leader, management and marketing representatives). - The management briefing guidelines were reviewed before the meeting. - Copies of the launch products and team presentation are available. - Forms: ITL, MTG, PIP |
| General | - In the management meeting, the team reviews with management their project plan and any questions or issues on the plan. - If management asks the team to modify or provide an alternate plan, the team needs to understand - the desired plan changes - what resource or work content changes to plan - Under no conditions should the team agree to a new schedule or plan without taking time to study and replan the work. - Meeting 9 generally takes 1 to 2 hours, depending on team size, project status, product complexity, and the team’s TSP experience. |

| Step | Activities | Description |
| --- | --- | --- |
| 1 | Meeting Roles | Select the meeting roles (specification ROLE). - The TSP coach leads the meeting (script MTG). - The timekeeper tracks time and keeps the meeting on schedule. - The recorder notes meeting decisions and actions and writes the meeting report (form MTG). |
| 2 | Agenda and Objectives | The team leader reviews the meeting agenda and objectives. |
| 3 | Overview of Work Done | The team leader or a team member hands out copies of the launch products, reviews the launch process, and describes how the plan was produced. |
| 4 | Team Goal and Plan Comparison | The team leader or a team member summarizes the project goals. - management's stated and implied goals - a summary of the team's plan and goals - how the team's plan and goals compares with management’s goals |
| 5 | Alternate Team Plan | If an alternate plan was prepared, the team leader or a team member distributes and reviews the alternate plan and the expected impact. |
| 6 | Risks | The team leader or a team member reviews each key project risk. - summarizes the risk's likelihood and schedule impact - discusses mitigation recommendations for high-impact risks |
| 7 | Stakeholder Involvement | The team leader reviews the relevant changes made to the Relevant Stakeholder Involvement Matrix (form RSIM) and the Stakeholder Role Assignment Matrix (form SRAM) for approval. |
| 8 | Discussion | The team leader asks for any questions and closes the meeting. |
| 9 | Launch Meeting Documentation | The recorder completes form MTG. - lists the attendees and the time spent by agenda item - describes decisions made and by whom - documents pending actions: what, when, and by whom - verifies the meeting report with the meeting attendees and gives the completed form MTG to the planning manager |

| Exit Criteria | - Management agrees with the team plan or resolution actions identified and responsibilities assigned. - All issues have been recorded (form ITL). - All process improvement suggestions have been recorded (form PIP). - The meeting report has been completed (form MTG and attachments). - The planning manger has copies of all meeting products. |
| --- | --- |

| TSP Launch Postmortem Meeting - Script LAUPM |  |
| --- | --- |
| Purpose | To guide the team through the launch postmortem |
| Entry Criteria | - All participants are present (TSP coach, team members, team leader). - Team members’ personal task and schedule templates are available. - The planning manager has produced copies for the team of the - overall team task and schedule plan - team plan for the next phase - Forms: ITL, MTG, PIP, LAUTEAMEVAL, LAULCEVAL - Specification: NOTEBOOK |
| General | - Timing: - The launch postmortem meeting is held after meeting 9 on day 4, or at the end of day 3 right after meeting 8. - The PM generally takes about 1 hour, depending on team size, project status, product complexity, and the team’s TSP experience. |

| Step | Activities | Description |
| --- | --- | --- |
| 1 | Meeting Roles | Select the meeting roles (specification ROLE). - The TSP coach leads the meeting (script MTG). - The timekeeper tracks time and keeps the meeting on schedule. - The recorder notes meeting decisions and actions and writes the meeting report (form MTG). |
| 2 | Meeting Overview | The TSP coach reviews the work to be done in this meeting and the products to be produced. |
| 3 | Launch Postmortem | The planning manager reviews the launch data to ensure that - all required launch data are gathered and recorded - data are properly entered in the appropriate project forms and databases - responsibility is assigned for preparing the launch materials for entry in the project notebook (specification NOTEBOOK) |
| 4 | Prepare PIPs | The TSP coach leads the team through a process evaluation. - identify launch process problems or inconveniences - suggest process improvements and complete PIPs for these suggestions |
| 5 | Launch Evaluation | - The team and team leader complete team launch evaluation forms (LAUTEAMEVAL) and submit a copy of these forms to the SEI. - The TSP coach completes the TSP coach launch evaluation form (LAULCEVAL) and submits a copy of this form to the SEI. |
| 6 | Launch Meeting Documentation | The recorder completes form MTG. - lists the attendees and the time spent by agenda item - describes decisions made and by whom - documents pending actions: what, when, and by whom - verifies the meeting report with the meeting attendees and gives the completed form MTG to the planning manager |

| Exit Criteria | - Launch postmortem activities have been completed. - The management presentation has been added to the project notebook. - All issues have been recorded (form ITL). - All process improvement suggestions have been recorded (form PIP). - The meeting report has been completed (form MTG and attachments). - The planning manger has copies of all meeting products. |
| --- | --- |

| TSPm Leadership Team Launch - Script LTL |  |
| --- | --- |
| Purpose | To guide the leadership team in conducting a launch workshop |
| Entry Criteria | - The leadership team has completed a TSPm team launch. - Senior management is available for LTL meeting 1. - All leadership team members attend meetings 1 through 5 and the postmortem. - For distributed teams, the remote team leaders participate in the entire launch either in person or via telephone or videoconference. - An authorized TSP coach is on hand to lead the launch. |
| General | - Timing - All LTL meetings are held on one day. - To complete the launch in one day, the entire team may have to stay late. |

| Step | Activities | Description |
| --- | --- | --- |
| 1 | Business Objectives | - Hold launch meeting 1 (script LTL1). - review the launch process and objectives - discuss the team’s goals with senior management |
| 2 | Define the Team Goals | - Hold launch meeting 2 (script LTL2). The leadership team - defines and documents its goals - relates its goals to business goals - defines goal measures |
| 3 | Determine Oversight Strategy | - Hold launch meeting 3 (script LTL3). The leadership team - reviews its quality, productivity, commitment, and improvement objectives - determines the management and team practices required to meet these objectives - considers the ways to motivate these practices - selects a motivational strategy |
| 4 | Allocate Work to Role Manager Teams | - Hold launch meeting 4 (script LTL4). The leadership team - determines the work and data needed to cause and verify the desired behavior - decides how this work should be done - defines the reports and data needed to accomplish the desired oversight - decides which tasks should be done by which role manager team |
| 5 | Define Role Manager Team Goals and Responsibilities | - Hold launch meeting 5 (script LTL5). The leadership team - lists for each role manager team the results to be produced - decides on the needed frequency and timing of these results - decides which leadership team member will be the contact point for each role manager team - assigns that leadership team member responsibility for preparing and presenting the leadership team’s needs at that role manager team launch |
| PM | Launch Postmortem | - Hold the launch postmortem meeting (script LTLPM). - document the launch results - assess the launch process and prepare PIPs |

| # Exit Criteria | - Documented team goals and goal measures - Defined role manager team responsibilities - Leadership team contact designated for each role manager team - All risks and issues have been identified and recorded. - Launch completed and results documented |
| --- | --- |

| TSPm LTL Launch Meeting 1 - Script LTL1 |  |
| --- | --- |
| Purpose | To review the leadership team’s goals and expectations with senior management |
| Entry Criteria | - One or more senior managers are present and prepared. - All participants are present (TSP coach, team leaders, and project manager). - For distributed teams, remote members participate via telephone or videoconference. - Forms: MTG, ITL, PIP - Specification ROLE |
| General | - Meeting 1 takes from 1 to 2 hours. |

| Step | Activities | Description |
| --- | --- | --- |
| 1 | Launch Overview Meeting Role Assignments | The TSP coach leads the meeting (script MTG). The TSP coach - describes the LTL launch process and the launch products - reviews the meeting roles and assigns a timekeeper and recorder (specification ROLE) - discusses the work to be done in this meeting |
| 2 | Business Goals and Expectations | The senior manager - describes the business goals for the organization and how this project’s performance relates to these goals - discusses the business objectives for improved quality, productivity, and competitive capability - describes management’s process improvement objectives - outlines management’s expectations for this project - answers the team's questions |
| 3 | Goal Questions | The team members should satisfy themselves that they understand the business goals and the senior manager’s expectations. - the reasons for each goal and expectation - how the senior manager will determine if the goals and expectations are met |
| 4 | Launch Meeting Documentation | The recorder completes form MTG. - lists the attendees and the time spent by agenda item - describes decisions made and by whom - documents pending actions: what, when, and by whom - verifies the meeting report with the meeting attendees and gives the completed form MTG to the project manager |

| Exit Criteria | - Launch meeting 1 activities have been completed. - The leadership team understands senior management’s goals and expectations. - The team's questions have been answered, or actions planned to get the answers. - All risks and issues have been recorded (form ITL). - All process improvement suggestions have been recorded (form PIP). - The meeting report has been completed (form MTG and attachments). - The project manager has copies of all meeting products. |
| --- | --- |

| TSPm LTL Launch Meeting 2 - Script LTL2 |  |
| --- | --- |
| Purpose | To guide the leadership team in setting goals |
| Entry Criteria | - All participants are present (TSP coach, team leaders, and project manager). - For distributed teams, remote members participate via telephone or videoconference. - Forms: GOAL, ITL, MTG, PIP - Specifications ROLE, PLAN, QUAL |
| General | Meeting 2 generally takes 1 to 2 hours. |

| Step | Activities | Description |
| --- | --- | --- |
| 1 | Meeting Roles | Select the meeting roles (specification ROLE). - The TSP coach leads the meeting (script MTG). - The timekeeper tracks time and keeps the meeting on schedule. - The recorder notes meeting decisions and actions and writes the meeting report (form MTG). |
| 2 | Meeting Overview | The TSP coach reviews the work to be done in this meeting and the products to be produced. |
| 3 | Review Management's Stated Goals | The project manager leads the team review of the senior manager’s goals to - get agreement on the stated goals - identify one or more measures for each goal - record results on form GOAL. |
| 4 | Implied Goals | - The project manager leads the team in defining the goals that are implied by management's stated goals. - Considerations include team productivity, quality performance, process improvement, customer satisfaction, and competitive capability. |
| 5 | Team Goals | The project manager leads the team in - establishing team goals to meet the manager's stated and implied goals - identifying one or more measures for each team goal - recording results on form GOAL |
| 6 | Goal Tracking | The project manager leads the team in - assigning team-member tracking responsibility for each goal - recording the assignments on form GOAL - establishing a tracking schedule for each goal |
| 7 | Launch Meeting Documentation | The recorder completes form MTG. - lists the attendees and the time spent by agenda item - describes decisions made and by whom - documents pending actions: what, when, and by whom - verifies the meeting report with the meeting attendees - gives the completed form MTG to the project manager. |

| Exit Criteria | - Launch meeting 2 activities have been completed. - The team goals are documented (form GOAL). - All risks and issues have been recorded (form ITL). - All process improvement suggestions have been recorded (form PIP). - The meeting report has been completed (form MTG and attachments). - The project manager has copies of all meeting products. |
| --- | --- |

| TSPm LTL Launch Meeting 3 - Script LTL3 |  |
| --- | --- |
| Purpose | To guide the leadership team in defining the strategy it will use in overseeing the project |
| Entry Criteria | - All participants are present (TSP coach, team leaders, and project manager). - For distributed teams, remote members participate via telephone or videoconference. - The documented team goals are available. - Forms: ITL, MTG, PIP and REVIEW checklist - Specification ROLE |
| General | Meeting 3 generally takes from 1 to 2 hours. |

| Step | Activities | Description |
| --- | --- | --- |
| 1 | Meeting Roles | Select the meeting roles (specification ROLE). - The TSP coach leads the meeting (script MTG). - The timekeeper tracks time and keeps the meeting on schedule. - The recorder notes meeting decisions and actions and writes the meeting report (form MTG). |
| 2 | Meeting Overview | The TSP coach reviews the work to be done in this meeting and the products to be produced. |
| 3 | Review Objectives | - The project manager leads the team in - defining the project results required to meet the team’s quality, schedule, productivity, and process improvement goals - reviewing the team’s and sub-teams’ plans for meeting its goals - determining the needed team and sub-team actions to meet these goals |
| 4 | Assess Current Team Performance | The project manager leads the team in - discussing the team’s current performance - defining any needed changes - devising ways to obtain the desired results |
| 5 | Select Management Strategy | - The project manager leads the team in - defining the management actions required to obtain the desired results - determining a strategy for implementing these actions |
| 6 | Define Verification Strategy | The project manager leads the team in - defining ways to verify the desired team results (TSP REVIEW checklist) - identifying measures or other indicators of proper performance - defining a strategy for verifying that the sub-teams are following the desired practices |
| 7 | Launch Meeting Documentation | The recorder completes form MTG. - lists the attendees and the time spent by agenda item - describes decisions made and by whom - documents pending actions: what, when, and by whom - verifies the meeting report with the meeting attendees - gives the completed form MTG to the project manager |

| Exit Criteria | - Launch meeting 3 activities have been completed. - List of products to be produced has been recorded (form SUMS). - Overall and detailed development process steps are documented. - Process plan and support plan are documented (form INV). - All risks and issues have been recorded (form ITL). - All process improvement suggestions have been recorded (form PIP). - The meeting report has been completed (form MTG and attachments). - The lead role manager has copies of all meeting products. |
| --- | --- |

| TSPm LTL Launch Meeting 4 - Script LTL4 |  |
| --- | --- |
| Purpose | To guide the leadership team in assigning project oversight and support work |
| Entry Criteria | - All participants present (TSP coach, team leaders, and project manager). - For distributed teams, remote members participate via telephone or videoconference. - Forms: ITL, MTG, PIP - Specification ROLE |
| General | Meeting 4 generally takes 1 to 2 hours. |

| Step | Activities | Description |
| --- | --- | --- |
| 1 | Meeting Roles | Select the meeting roles (specification ROLE). - The TSP coach leads the meeting (script MTG). - The timekeeper tracks time and keeps the meeting on schedule. - The recorder notes meeting decisions and actions and writes the meeting report (form MTG). |
| 2 | Meeting Overview | The TSP coach reviews the work to be done in this meeting and the products to be produced. |
| 3 | Define Needed Reports and Data | - The project manager leads the team in - defining the data and reports needed to assess team and project performance - deciding how these data and reports should be produced |
| 4 | Define Required Work | - The project manager leads the team in - determining the work needed to implement the selected strategy - deciding which tasks must be done by the team leaders - specifying the tasks to be handled by the role manager teams - defining the tasks to be assigned to other groups |
| 5 | Make Initial Task Assignments | - The project manager leads the team in making the task assignments. - For the role manager tasks, the team makes an initial assignment. - The team determines who should handle the other delegateable tasks. - The team assigns a team leader to arrange for this other work |
| 6 | Assess Role Manager Team Workload | - The project manager leads the team in - reviewing the workload for each role manager team (TSPm Role Manager Team Responsibilities, TSPm Lead Role Manager Responsibilities) - identifying the role manager teams that are overloaded and those that are not adequately utilized - determining the role manager teams that have continuing reporting tasks and those that do not |
| 7 | Make Role Manager Team Assignments | - The project manager leads the team in assigning the workload so that - no role manager team has an excessive workload - every team has at least one continuing reporting responsibility - every team has sufficient cross-team workload to ensure its continued communication and involvement |
| 8 | Launch Meeting Documentation | The recorder completes form MTG. - lists the attendees and the time spent by agenda item - describes decisions made and by whom - documents pending actions: what, when, and by whom - verifies the meeting report with the meeting attendees - gives the completed form MTG to the lead role manager |

| Exit Criteria | - Launch meeting 4 activities have been completed. - The role manager team workload has been assigned - Other required oversight tasks have been assigned or delegated. - All risks and issues have been recorded (form ITL). - All process improvement suggestions have been recorded (form PIP). - The meeting report has been completed (form MTG and attachments). - The project manager has copies of all meeting products. |
| --- | --- |

| TSPm LTL Launch Meeting 5 - Script LTL5 |  |
| --- | --- |
| Purpose | To guide the leadership team in defining the role manager team goals and responsibilities |
| Entry Criteria | - All participants are present (TSP coach, team leaders, and project manager). - For distributed teams, remote members participate via telephone or videoconference. - Forms: ITL, MTG, PIP and REVIEW checklist - Specification ROLE |
| General | Meeting 5 generally takes 1 to 2 hours. |

| Step | Activities | Description |
| --- | --- | --- |
| 1 | Meeting Roles | Select the meeting roles (specification ROLE). - The TSP coach leads the meeting (script MTG). - The timekeeper tracks time and keeps the meeting on schedule. - The recorder notes meeting decisions and actions and writes the meeting report (form MTG). |
| 2 | Meeting Overview | The TSP coach reviews the work to be done in this meeting and the products to be produced. |
| 3 | List Role Tasks | The project manager leads the team in listing the assignments for each role manager team (see TSPm Role Manager Team Responsibilities). |
| 4 | Define Needed Reports and Data | - For each role manager team report or task, the leadership team - describes the information needed (TSP REVIEW Checklist) - specifies any format constraints or requirements - states the required timing or frequency for the reports - describes why the report is needed and how it will be used |
| 5 | Define Other Goals | - For each role manager team, the leadership team also - lists any other role manager responsibilities (quality alerts, risk evaluations, technical exposures) (Role Manager Team Responsibilities) - describes the leadership team’s other expectations for the role manager team (creative input, emerging opportunities, significant customer related issues) |
| 6 | Leadership Team Responsibilities | - For each role manager team, the leadership team - determines the team leader who will be the contact point for that role manager team - assigns that leadership team member the responsibility for preparing and presenting the leadership team’s needs to that role manager team at its team launch (Script RTL) - asks that team leader to periodically review that role manager team’s activities and to bring any problems to the leadership team (Script WEEKLR) |
| 7 | Launch Meeting Documentation | The recorder completes form MTG. - lists the attendees and the time spent by agenda item - describes decisions made and by whom - documents pending actions: what, when, and by whom - verifies the meeting report with the meeting attendees - gives the completed form MTG to the planning manager |

| Exit Criteria | - Launch meeting 5 activities have been completed. - Precise role manager team reporting responsibilities have been defined. - Other role manager team responsibilities have been specified. - All process improvement suggestions have been recorded (form PIP). - The meeting report has been completed (form MTG and attachments). - The lead role manger has copies of all meeting products. |
| --- | --- |

| TSPm LTL Postmortem Meeting - Script LTLPM |  |
| --- | --- |
| Purpose | To guide the leadership team through the launch postmortem |
| Entry Criteria | - All participants are present (TSP coach, team leaders, and project manager). - For distributed teams, remote members participate via telephone or videoconference. - Forms: ITL, MTG, PIP - Specification ROLE |
| General | Timing - The PM meeting generally takes about ½ to 1 hour. |

| Step | Activities | Description |
| --- | --- | --- |
| 1 | Meeting Roles | Select the meeting roles (specification ROLE). - The TSP coach leads the meeting (script MTG). - The timekeeper tracks time and keeps the meeting on schedule. - The recorder notes meeting decisions and actions and writes the meeting report (form MTG). |
| 2 | Meeting Overview | The TSP coach reviews the work to be done in this meeting and the products to be produced. |
| 3 | Launch Postmortem | The TSP coach ensures that all required launch data are gathered and recorded. |
| 4 | Prepare PIPs | The TSP coach leads the team through a process evaluation. - identifies launch process problems or inconveniences - suggests process improvements - completes PIPs for these suggestions |
| 5 | Launch Meeting Documentation | The recorder completes form MTG. - lists the attendees and the time spent by agenda item - describes decisions made and by whom - documents pending actions: what, when, and by whom - verifies the meeting report with the meeting attendees - gives the completed form MTG to the planning manager |

| Exit Criteria | - Launch postmortem activities have been completed. - All risks and issues have been recorded (form ITL). - All process improvement suggestions have been recorded (form PIP). - The meeting report has been completed (form MTG and attachments). - The TSP coach and project manger have copies of all meeting products. |
| --- | --- |

| TSP Overall Maintenance and Enhancement Process - Script MAINT |  |
| --- | --- |
| Purpose | - To guide integrated teams in maintaining and enhancing an existing software-intensive product - Use script DEV for development and enhancement projects. |
| Entry Criteria | - The work has been planned during a (re)launch. |
| General | For small maintenance and enhancement projects, the TSP cycle may span several phases or even the entire project. For iterative methods, the steps in this script may take place concurrently. All steps should be planned and executed within one or multiple TSP cycles (script CYCLE). |

| Step | Activities | Description |
| --- | --- | --- |
| 1 | Analysis (ANA) | - Set analysis goals, roles, processes, and procedures. - Produce the preliminary fix list, the overall project plan, and the detailed analysis plan. - Assess analysis risks and exposures. - Produce, document, and review the release impact analysis. - Develop and inspect the release specifications. - Define regression and system tests and user manual changes. |
| 2 | High-Level Design (HLD) | - Set design goals, roles, processes, and procedures. - Update the fix list, the overall project plan and detailed HLD plan. - Assess design risks and exposures. - Produce and inspect the high-level design. - Produce the performance and integration test specifications. |
| 3 | Implementation (IMP) | - Set implementation goals, roles, processes, and procedures. - Update the fix list, the overall project plan and detailed implementation plan. - Assess implementation risks and exposures. - Design, code, inspect, and unit test the enhancements and fixes. - Produce the unit and release test specifications. |
| 4 | Release Test (TEST) | - Set release test goals, roles, processes, and procedures. - Update the fix list and the detailed release test plan. - Assess integration and test risks and exposures. - Develop test materials and test data. - Build the integrated product release. - Run the integration, system, and regression tests. - Return defective components or fixes for rework and retest. - Produce and review the final updated documentation. - Deliver the completed product release. |

| Exit Criteria | - A completed high-quality product release - A project summary report (see specification SUMMARY) - PIPs for all identified process improvements |
| --- | --- |

| TSP General Meeting Process - Script MTG |  |
| --- | --- |
| Purpose | Use this script as a guide in planning and conducting meetings; it will help you hold useful meetings in a minimum time. |
| Entry Criteria | - You need a meeting and know who should attend. - Form: MTG - Specification: NOTEBOOK |
| General | Meetings can be held to - resolve issues or make decisions - inform or educate - produce work products; i.e., a design, plan, process, or standard |

| Step | Activities | Description |
| --- | --- | --- |
| 1 | Meeting Preparation | In planning a meeting, complete form MTG. - What is the meeting’s purpose? Write it down. - What outcome do you want? Be specific. - Who should attend the meeting and why? - What topics should be covered? - Who should present what and for how long? - Are discussion periods needed and for how long? - Are decisions needed, on what, and by whom? - Set the agenda topics, times, and speakers. - Are actions desired after the meeting? - List the data needed: responsibilities, dates, resources, etc. - After ensuring that the key attendees can attend, schedule the meeting. - Check facilities: setup, equipment, supplies, refreshments, etc. - Provide each attendee a completed copy of form MTG. |
| 2 | Meeting Roles | Select the meeting roles (specification Meeting Roles). - The chairperson leads the meeting. - The timekeeper keeps the meeting on schedule. - The recorder notes meeting decisions and actions and helps to write the meeting report. |
| 3 | Meeting Introduction | - Review the meeting purpose and agenda. - Check for any changes in the purpose or agenda. |
| 4 | The Meeting | During the meeting, all attendees should do the following. - Follow the agenda. - When important topics are raised that are not on the current subject, defer them to later in the agenda or to another meeting. Record the deferred topic on a visible chart, white board, etc. - Be specific on each decision: what was decided and by whom. - Be clear on each planned action: who will do what and when. - Give everyone an opportunity to contribute and speak up. |
| 5 | Meeting Conclusion | - The recorder reviews and confirms the decisions and actions. - Briefly review the meeting process for suggested improvements. |
| 6 | Meeting Report | Promptly issue the meeting report (form MTG). The recorder - lists the purpose, attendees, and results - describes decisions made, and by whom - documents pending actions: what, when, and by whom - verifies with the attendees that the report is correct and complete |

| Exit Criteria | The meeting was held and the meeting report was issued and filed in the project notebook. |
| --- | --- |

| TSP The TSP Postmortem - Script PM |  |
| --- | --- |
| Purpose | - To gather, analyze, and record phase or cycle and project data - To analyze project performance against plans and goals - To identify potential areas for improvement - To identify and submit PIPs |
| Entry Criteria | - All planned work for the phase or cycle has been completed or near completion. - All project and process data available. - Forms: all TSP forms - Specification: NOTEBOOK Note: to meet aggressive schedules, the next phase or cycle may be relaunched before the postmortem for the current phase or cycle. |

| Step | Activities | Description |
| --- | --- | --- |
| 1 | Meeting Roles | - The TSP coach leads the meeting (script MTG). - The timekeeper tracks time and keeps the meeting on schedule. - The recorder notes meeting decisions and actions and writes the meeting report (form MTG). |
| 2 | Baseline Evaluation | The support manager leads the team in evaluating the adequacy of the configuration management process, system baseline, and development environment. |
| 3 | Plan Evaluation | The planning manager leads the evaluation of team performance. - actual versus plan for size, resource, and schedule estimates |
| 4 | Quality Performance | The quality manager leads the evaluation of team performance. - quality of the products produced (script PMTD) - team performance versus the goals and quality plan |
| 5 | Planning Data | Provide updated planning data. - size, resource, and productivity data - defect, yield, PDF, ratio, rate data, and component quality criteria |
| 6 | Process Evaluation | Review all approved process deviation requests (Form SPDR) and document evaluation results (Form SPDE) Review PSSP for applicable scripts, forms, specifications, guidelines, instructions, and checklists, and identify items to be tailored (Form SUMPD) based on next phase/cycle or project requirements and SPDE recommendations. Review CIBPS for continued applicability of unimplemented processes changes to the PSSP based on next phase/cycle or project requirements. Where improvement is needed, - identify process, training, tool, support, or management actions needed - submit PIPs as required |
| 7 | Stakeholder Survey (optional) | For the final project postmortem, obtain stakeholder evaluations. - Standardize on one set of opinion surveys for all projects. - Request suggestions for improvement. - Prepare recommendations on areas requiring future action. |
| 8 | Goals Evaluation | The team leader leads the team in determining and documenting performance against team goals (form GOAL). |
| 9 | Final Project Report Preparation | - At the end of each project phase or cycle, it is important that the team decide who will prepare the final report materials for this phase or cycle. - This report should provide the information subsequent projects will need to make accurate plans (see SUMMARY specification). - At a minimum the report should conform to the PM Report Specification. |

(continued on next page)

TSP The TSP Postmortem - Script PM (continued)

| Exit Criteria | - The project has completed most, if not all, tasks for the current phase or cycle. - All project data are entered in the process asset library. - All PIPs have been identified, prioritized, and submitted. - Completed plan summary forms are available for all completed project phases or cycles (SUMP, SUMQ). - Completed meeting report (form MTG) - The final project report has been completed, submitted, and filed in the project notebook and submitted to the Process Asset and Data Repository Manager (see PM specification). |
| --- | --- |

| TSP Postmortem Test Defects - Script PMTD |  |
| --- | --- |
| Purpose | - To decide what actions to take to ensure that in the future - similar defects are found and fixed before release to test - actions are devised to prevent a repetition of similar defects |
| Entry Criteria | - Data on defects found during build, integration, or system testing. - Form: MTG - Specification: NOTEBOOK |
| General | - When testing finds defects in a system, they are generally clustered in a relatively small percentage of the code. - Re-inspecting defect-prone components and fixes can save substantial test time and produce high-quality products. |

| Step | Activities | Description |
| --- | --- | --- |
| 1 | Process Analysis | For each defect found during build, integration, or system testing, analyze the defect and process data to determine - what process steps missed finding the defect - the process step in which the defect was injected |
| 2 | Defect Meeting | The project leader - describes the meeting's purpose and the decisions to be made - determines who will fill the meeting roles (script MTG) |
|  |  | - The team reviews the available process data to decide - what mistakes or oversights permitted the defect to escape detection in each step that missed it - the actions to be taken to prevent this happening again (PIP) - The team also determines what caused the defect and, where they can, decides on prevention actions (PIP). |
|  |  | The recorder and timekeeper complete the meeting report, including - defect, product, and process analysis results - who, what, and when of each decision (MTG form) |

| Exit Criteria | - The defect meeting report, including all component, defect, and process data, has been entered in MTG form and the project notebook (specification NOTEBOOK). - Prevention actions have been identified, recorded (form PIP), prioritized, and submitted. |
| --- | --- |

| TSPm Launch Preparation - Script PREP |  |
| --- | --- |
| Purpose | To prepare an organization for a multi-team TSP launch or relaunch |
| Entry Criteria | - The project has been identified and team members and leaders have been named. - The launch or relaunch preparation for each team will be completed before the launch (checklist PREPLm or PREPRm). - A qualified lead TSP coach is available and a qualified TSP coach is available for each sub-team at each team location. |
| TSPm Criteria | - A multi-team TSPm launch is appropriate when - a project team has more than 12 to 15 members - the project has multiple specialties, processes, and team leaders |
| Distributed Launch Criteria | - A distributed team launch is appropriate when - the team members cannot be in one location for the launch or relaunch - the sub-teams’ work is sufficiently interdependent so simultaneous launches are required |
| General | - The leadership team (the project leader and sub-team leaders) reviews preparation status weekly with the lead TSP coach (script PREPW). - The TSPm launch schedule is 5 days instead of 4 for TSP. - The TSPm relaunch schedule is 4 days instead of 3 for TSP. |

| Step | Activities | Description |
| --- | --- | --- |
| 1 | The Conceptual Design | - The leadership team charges the lead design role manager with producing or revising the conceptual design and presenting it during meeting 1A. - The design team should include the lead designer from each sub-team at each location. - The conceptual design provides an initial picture of the total system structure, elements, and functions. - The conceptual design guides team planning. - The leadership team reviews the conceptual design before the launch. |
| 2 | The Project Strategy | - The leadership team defines or revises the initial project strategy. - This strategy covers architecture, system integration, incremental development, prototyping, and technology issues. |
| 3 | Team Assignments | - The leadership team assigns the planning and development responsibility for all system elements and prototypes. |
| 4 | Team Roles | - The leadership team reviews the standard TSP team roles and decides if additional roles are needed. |
| 5 | Role Team Responsibilities | - The leadership team identifies the interim lead role manager for each role manager team (TSPm Role Manager Team Responsibilities). - During the role manager team launch, the role managers elect their own leader. |
| 6 | Strategy Presentation | The leadership team prepares a strategy presentation and handout to be given during the project launch or relaunch (script LAU1A or REL1A). |
| 7 | Status Presentation | For a relaunch, the leadership team prepares the status presentation and handout to be given during the project relaunch (specification STATUS). |

| # Exit Criteria | - The leadership team has been formed or, if needed, restructured. - The product conceptual design has been produced or revised. - Sub-team membership and responsibilities have been specified. - The strategy and status presentations have been prepared. - The interim lead role managers have been identified for each role manager team. |
| --- | --- |

| TSP+ Team Launch Preparation - Script PREPT |  |
| --- | --- |
| Purpose | To prepare a team for a TSP launch |
| Entry Criteria | - The project has been identified and team members and leader named. - All participants are present (TSP coach, team members, team leader). - Forms: ITL, MTG, PIP |
| General | - This meeting generally takes 3 to 4 hours. |

| Step | Activities | Description |
| --- | --- | --- |
| 1 | TSP and Launch Overview | - The TSP coach leads the meeting (script MTG). The TSP coach - describes the TSP launch process and the launch products - reviews the TSP team roles - reviews the meeting roles and assigns a timekeeper and recorder (specification ROLE) - discusses the work to be done in this meeting |
| 2 | Project Goals and Objectives | - The team leader, based on his/her current understanding, gives a short description of the project and answers any questions. |
| 3 | Goal and Objective Questions | - The team members are satisfied that they understand the project goals and objectives, realizing that goals and objectives may change prior to the launch. |
| 4 | Review Prelaunch Work | - The TSP coach leads the team in reviewing the work to be completed in preparation for the launch (checklist PREPT) for each team member role (specification ROLE). |
| 5 | Prelaunch Work Assignments | - The team determines who will do what activities in preparation for the launch (checklist PREPT). |
| 6 | Meeting Documentation | The recorder completes the MTG. - lists the attendees and the time spent by agenda item - describes decisions made and by whom - documents pending actions (what, when, and by whom) - verifies the meeting report with the meeting attendees and gives completed form MTG to the planning manager |

| # Exit Criteria | - Team launch preparation activities have been completed. - All issues have been recorded (form ITL). - All process improvement suggestions have been recorded (form PIP). - The meeting report has been completed (form MTG and attachments). - The planning manager has copies of all meeting products. |
| --- | --- |

| TSPm Weekly Launch Preparation Meeting - Script PREPW |  |
| --- | --- |
| Purpose | - The leadership team meets with the lead TSP coach to review launch or relaunch preparation status and resolve outstanding issues. - These meetings may be held via telephone or videoconference. |
| Entry Criteria | - The project manager, team leaders, and the lead TSP coach are present. - For distributed teams, remote team leaders participate via telephone or videoconference. - Form: MTG |
| General | - The weekly launch or relaunch preparation meeting should be held every week for at least one month before a TSPm launch or relaunch. - The meeting should normally take about one hour. |

| Step | Activities | Description |
| --- | --- | --- |
| 1 | Meeting Role Assignments | - Select the meeting roles (specification ROLE). - The TSP coach leads the meeting (script MTG). - The timekeeper tracks time and keeps the meeting on schedule. - The recorder notes meeting decisions and actions and writes the meeting report (form MTG). |
| 2 | Meeting Agenda | - The project manager - reviews the meeting agenda - asks for changes or additions |
| 3 | Status Review | - The project manager leads a review of each preparation activity. |
|  | Team Membership | - Status of team membership - allocation or reallocation of current employees - hiring status for needed new team members - hiring status for needed new managers |
|  | Training Status | - The PSP and TSP training status for new managers and team members - precise training status for each on board person - plan to complete any required training - plan for training new hires |
|  | Conceptual Design and Strategy | - The status of the conceptual design and strategy work - who is working on the conceptual design and strategy - when they plan to be done - when the leadership team review is planned |
|  | Product and Prototyping Assignments | - The status of any needed product or prototyping assignments or reassignments - who is working on product and prototyping assignments - when the leadership team review is planned |
|  | Role Team Responsibilities | - The status of role team responsibility planning - who is defining the role team responsibilities - when the leadership team review is planned |
| 4 | Strategy Presentation | - The status of the strategy presentation - for a launch, the management and marketing presentations - for a relaunch, the status, goal, and update presentations - for both a launch and a relaunch, the conceptual design, strategy, product, prototyping, and roles presentations |
| 5 | Launch Meeting Documentation | - The recorder gives the completed form MTG to the project manager. - lists the attendees and the time spent by agenda item - describes decisions made and by whom - documents pending actions: what, when, and by whom - verifies the meeting report with the meeting attendees |

| # Exit Criteria | - Meeting agenda topics completed - Completed meeting report with form MTG and any attachments |
| --- | --- |

| TSP+ Project’s Set of Standard Processes Establishment - Script PSSPE |  |
| --- | --- |
| Purpose | - To help the team establish and maintain the project’s set of standard processes (PSSP) to be used in the execution of the given project. - To provide a mechanism for tailoring the organization’s set of standard processes (OSSP) to meet the needs of the project. - Forms: PIP, CIR, SUMPD, CIBPS |
| Entry Criteria | - A copy of the OSSP |
| General | - Tailoring Criteria - Requests to tailor the standard process shall be made at a minimum when: - Use of a new process tool or methodology is involved - New application domains - Custom requirements - A PIP against the OSSP was submitted and the Process Group (PG) has requested that the improvement be tailored / piloted prior to deployment to the entire organization. |

| Step | Activities | Description |
| --- | --- | --- |
| 1 | Obtain OSSP | - Obtain a copy of the OSSP Baseline from the PG Configuration Management Coordinator (CMC) (Form CIBPS) |
| 2 | Baseline PSSP | - Baseline the PSSP by configuring the OSSP as the project’s set of standard processes (Form CIR) - Submit the PSSP and CIR form to the project’s support manager for configuration. |
| 3 | Review PSSP | - Review PSSP for applicable scripts, forms, specifications, guidelines, instructions and checklists, and identify items to be tailored based on the team’s current understanding of project requirements. |
| 4 | Document rationale | - Document rationale for tailoring recommendations (Form SUMPD). - Be prepared to discuss tailoring recommendations with team during launch meeting 3 (Script LAU3). |

| Exit Criteria | - The PSSP has been established - A list of recommended tailoring of the PSSP have been documented (Form SUMPD) - All process improvement suggestions have been recorded (form PIP). |
| --- | --- |

| TSP Team Relaunch - Script REL |  |
| --- | --- |
| Purpose | To guide integrated teams in relaunching a software-intensive project |
| Entry Criteria | - The relaunch preparation work has been completed (PREPR, PREPT). - The team leader has prepared the project status report. - The team leader and team members are available for the entire relaunch. - An authorized TSP coach is on hand to lead the relaunch. - The updated project notebook is available. - Note: to meet aggressive schedules, the next phase may be relaunched before the postmortem for the current phase. |
| General | If there are significant project changes, follow script LAU. Timing; Day; 1; 2; 3. Meeting; 1, 2, and 3; 4 and 5; 6, 7, and PM. Notional schedule can be compressed or extended to meet scope of relaunch. |

| Step | Activities | Description |
| --- | --- | --- |
| 1 | Project Status and Objectives | Hold team relaunch meeting 1 (script REL1). - Review the relaunch process and introduce new team members. - Review the project status to date. - Understand management's goals for the project. |
| 2 | Team Goals and Roles | Hold team relaunch meeting 2 (script LAU2). - Update and document the team's goals. - Allocate team roles among team members. |
| 3 | Project Strategy and Support | Hold team relaunch meeting 3 (script LAU3). - Update the system conceptual design, and, if needed, a fix list. - Update the development strategy and products to be produced. - Review and update the development process to be used. - Review and update the process and support plans. |
| 4 | Overall Plan | Hold team relaunch meeting 4 (script LAU4). - Develop or update the size estimates and overall plan. |
| 5 | Quality Plan | Hold team launch meeting 5 (script LAU5). - Update the quality plan. |
| 6 | Balanced Plan | Hold team relaunch meeting 6. (script LAU6.). - Allocate work to team members. - Produce bottom-up next-phase plans for each team member. - Produce a balanced next-phase plan for the team and each team member. |
| 7 | Project Risk Analysis | Hold team relaunch meeting 7 (script LAU7). - Identify and evaluate any new project risks. - Define risk assessment checkpoints and responsibilities. - Propose mitigation actions for near-term, high-impact risks. |
| 8 | Launch Report Preparation | There is no relaunch meeting 8. |
| 9 | Management Review | There is no relaunch meeting 9. |
| PM | Launch Postmortem | Hold team launch postmortem meeting (script LAUPM). - Gather launch data and produce a launch report. - Put the launch report in the project notebook. - Assess the launch process and prepare PIPs. |

| Exit Criteria | - The relaunch is completed. - Team roles, goals, processes, responsibilities, and plans are defined. - The relaunch data are in the project notebook (specification NOTEBOOK). |
| --- | --- |

| TSP Relaunch Meeting 1 - Script REL1 |  |
| --- | --- |
| Purpose | To review project status and update the team on any customer requirements or management goal changes |
| Entry Criteria | - The team and team leader are prepared. - All participants are present (TSP coach, team members, team leader). - Forms: MTG, ITL, PIP |
| General | Meeting 1 generally takes from 1 to 2 hours. |

| Step | Activities | Description |
| --- | --- | --- |
| 1 | Meeting Roles | Select the meeting roles (specification ROLE). - The TSP coach leads the meeting (script MTG). - The timekeeper tracks time and keeps the meeting on schedule. - The recorder notes meeting decisions and actions and writes the meeting report (form MTG). |
| 2 | Relaunch Overview | The TSP coach - reviews the relaunch process and the products to be produced - discusses the work to be done in this meeting |
| 3 | New Members | The team leader introduces new team members. |
| 4 | Project Status | The team leader presents a full project status report to the team and TSP coach (specification STATUS). - schedule status versus plan - actual earned value and task hour performance versus plan - actual size and time data versus plan - quality performance versus plan |
| 5 | Goal Performance | - The team leader reviews the team's quality, schedule, and cost performance versus goals. - Where performance fell short, the team discusses recovery options. - Where performance met or exceeded goals, the team discusses improvement opportunities. |
| 6 | Management Update | The team leader describes any changes in management's goals for the project. - reasons for any goal changes - how management will measure goal attainment - answers questions on the goals |
| 7 | Launch Meeting Documentation | The recorder completes form MTG. - lists the attendees and the time spent by agenda item - describes decisions made and by whom - documents pending actions: what, when, and by whom - verifies the meeting report with the meeting attendees - saves the completed form MTG to give to the planning manager in launch meeting 2 |

| Exit Criteria | - Relaunch meeting 1 activities have been completed. - The team fully understands project status and any changes in management's goals. - All of the team's questions have been answered, or actions are planned to get the answers for the team. - All issues have been recorded (form ITL). - All process improvement suggestions have been recorded (form PIP). - The meeting report has been completed (form MTG and attachments). - The planning manager has copies of all meeting products. |
| --- | --- |

| TSPm Relaunch Meeting 1A - Script REL1A |  |
| --- | --- |
| Purpose | - The entire team meets to - review the project status and update the team on any customer requirements or management goal changes - provide the sub-teams with sufficient guidance so they can plan their portions of the overall project |
| Entry Criteria | - The leadership team and all team members are present. - For distributed teams, remote members participate via videoconference. - Forms: MTG, ITL |
| General | - Meeting 1A follows relaunch meeting 1. - Meeting 1A takes from 2 to 3 hours. |

| Step | Activities | Description |
| --- | --- | --- |
| 1 | Meeting Role Assignments | - Select the meeting roles (specification ROLE). - The TSP coach leads the meeting (script MTG). - The timekeeper tracks time and keeps the meeting on schedule. - The recorder notes meeting decisions and actions and writes the meeting report (form MTG). |
| 2 | Meeting Overview | - The project manager briefly summarizes the meeting purpose and agenda. |
| 3 | Review the Conceptual Design | The design team describes any changes in the product conceptual design. |
| 4 | Review Project Strategy | The project manager or designee describes any changes in the project strategy. |
| 5 | Product Responsibilities | The project manager or designee describes the product elements each sub-team is responsible for planning and developing. |
| 6 | Prototyping Responsibilities | The project manager or designee describes any changes in the prototypes each sub-team is responsible for planning and developing. |
| 7 | Required Team Roles | The project manager or designee describes any changes in the roles or sub-team role responsibilities. |
| 8 | Discussion | The project manager asks for questions and discussion. |
| 9 | Launch Meeting Documentation | - The recorder gives the completed form MTG to the TSP coach. - lists the attendees and the time spent by agenda item - describes decisions made and by whom - documents pending actions: what, when, and by whom - verifies the meeting report with the meeting attendees |

| # Exit Criteria | - Relaunch meeting 1A activities have been completed. - Each sub-team understands its assigned responsibilities for relaunch planning and product development. - All issues have been recorded on ITL forms. - The completed meeting report has been completed (form MTG and any attachments). - The planning manager has copies of all meeting products. |
| --- | --- |

| TSPm Team Relaunch - Script RELm |  |
| --- | --- |
| Purpose | To guide multi-teams in conducting a TSPm relaunch workshop |
| Entry Criteria | - The relaunch preparation work has been completed (script PREP). - For the relaunch, the management and customer representatives are available for meetings 1 and 9 if needed. - All team members and the team leader are committed to attend relaunch meetings 1 through 9 and the relaunch postmortem. - For distributed teams, meetings 1, 1A, and 9 are held via videoconference at all team locations. - Certified TSP coaches are on hand for all teams. |
| General | - If there are significant project changes, follow script LAU. Day; 1; 2; 3; 4. Meeting; 1, 2, and 3; 4, 5, and 6; 7 and 8; 9 and PM. - Notional schedule can be compressed or extended to meet scope of relaunch. |

| Step | Activities | Description |
| --- | --- | --- |
| 1 | Management and Customer Objectives | - Hold team relaunch meeting 1 (script REL1). - Review the relaunch process and introduce team members. - Review project status to date. - Describe changes in management’s goals for the project. - Discuss the team’s goals with management and customer representatives. |
| 1A | Project Strategy and Sub-team Responsibilities | - The leadership team presents the project strategy (script REL1A). - Summarize changes in the product strategy. - Describe changes in sub-team product responsibilities. - Review changes in roles and sub-team role responsibilities. |
| 2 | Team Goals and Roles | - Hold sub-team relaunch meetings 2 (script LAU2). - Select sub-team roles and backup roles. - Define and document the sub-team's goals. |
| 3 | Project Strategy and Support | - Hold sub-team relaunch meetings 3 (script LAU3). - Review and adjust the system conceptual design. - Review and adjust the development strategy. - Consider the product assignments and make recommendations for needed changes. - Define and document the team processes. - Produce the process and support plans. |
| 3A | Leadership Meeting: Status | - The leadership team meets to review relaunch status (script LAU3A). - Review relaunch status and resolve issues. - If not done during relaunch preparation, review role assignments and name the lead member for each role team. |
| 4 | Overall Plan | - Hold sub-team relaunch meetings 4 (script LAU4). - develop size estimates and the overall sub-team plans. |
| 5 | Quality Plan | - The sub-teams hold relaunch meetings 5 (script LAU5). - Develop the sub-team quality plans. |
| 5A | Leadership Meeting: Status | - The leadership team reviews relaunch status and resolves issues (script LAU3A). |
| 5B | Role Manager Meeting: Planning | - The planning managers hold relaunch meeting 5B (script LAU5B). - Consolidate the overall team plan. - Identify issues and interdependencies among the teams. - Establish the committed and required dates for these dependencies. - Establish responsibilities for handling the identified issues. - Log the issues in ITL. |
| 5C | Role Manager Meeting: Quality | - The quality role managers hold relaunch meeting 5C (script LAU5C). - Resolve issues among the quality plans. - Consolidate the quality plans into an overall quality plan. |

(continued)

| TSPm Team Relaunch - Script RELm (continued) |  |  |
| --- | --- | --- |
| Step | Activities | Description |
| 6 | Balanced Plan | - The sub-teams hold relaunch meeting 6 (script LAU6). - Review work allocations to the team members. - Review the bottom-up next-phase plans for each team member. - Produce a balanced next-phase plan for each sub-team and each team member. |
| 6A | Leadership Meeting: Status | - The leadership team reviews relaunch status and resolves issues (script LAU3A). |
| 6B | Planning Manager Meeting: Balanced Plan | - The planning role managers hold relaunch meeting 6B (script LAU6B). - Consolidate the sub-team bottom-up plans into a team plan. - Determine if load balancing is required among the sub-teams. - Recommend needed adjustments. |
| 7 | Project Risk Analysis | - The sub-teams hold relaunch meetings 7 (script LAU7). - Identify and evaluate project risks. - Define risk assessment checkpoints and responsibilities. - Propose mitigation actions for immediate high-impact risks. |
| 7A | Leadership Meeting: Risk Analysis and Report | - The leadership team reviews the sub-team risk assessments and plans for the final management meeting (script LAU7A). - Decide which risks to track at the leadership level. - Make other needed changes or additions. - Define the content of the management presentation. - Identify the work done to prepare the management presentation. - Assign responsibilities for the preparation work. |
| 8 | Sub-team Report Preparation | - The sub-teams hold relaunch meetings 8 (script LAU8). - Prepare the assigned parts of the relaunch report to management. |
| 9 | Management Review | - The entire team holds relaunch meeting 9 (script LAU9). - Review relaunch activities and project plans with management. - Discuss project risks, responsibilities, and planned actions. |
| PM | Launch Postmortem | - The sub-teams hold relaunch postmortem meetings (script LAUPM). - Gather relaunch data and produce a relaunch report. - Enter this report in the project notebook. - Assess the relaunch process and prepare PIPs. |

| # Exit Criteria | - Relaunch completed with documented team and member plans - Defined team roles, goals, processes, and responsibilities - Management agreement with the team plan - Resolution actions identified and responsibilities assigned - Relaunch data filed in the project notebook (specification NOTEBOOK) |
| --- | --- |

| TSP Requirements - Script REQ |  |
| --- | --- |
| Purpose | To produce a complete, valid, and accurate system requirements specification (SRS) and (hardware-)software engineering requirement spec (ERS). |
| Entry Criteria | - Completed requirements-phase launch, a detailed next-phase plan, and a current list of project risks and exposures - Product requirements statement or request for proposal - Forms: INS, ITL, LOGD, LOGT, MTG, PIP, SUMP, SUMQ - Specification: NOTEBOOK |
| General |  |

| Step | Activities | Description |
| --- | --- | --- |
| 1 | Market Requirements Study | Study the requirements to identify errors and omissions and clarify questions. - Produce an elicitation plan and detailed questions. - Double-check correctness of ALL requirements assumptions. |
| 2 | Requirements Elicitation | - Hold customer/marketing elicitation meeting(s) (script MTG). - Document each elicitation meeting and its results (form MTG). |
| 3 | Requirements Prototypes | - Prototype and/or simulate all important specification questions and review results with systems, marketing and the customer. - Where needed, use prototypes to obtain data for validating design, planning, resource, or size assumptions. |
| 4 | System Requirements Specification | - Produce or update the system requirements specification (SRS). - normal, abnormal, and recovery behavior and performance - operational and user interfaces - documentation, training, distribution, installation, maintenance, and support requirements - For each SRS item, reference its source in the market requirements. |
| 5 | User Manual Draft | Produce a detailed user manual outline and initial draft or update existing user manual. |
| 6 | System Test Plan | Define tests to verify the system and products to the specifications. - normal and abnormal interfaces, functions, and performance - security, safety, failure, and recovery conditions - Establish and maintain bi-directional traceability between test plan and SRS. |
| 7 | SRS Inspection | Inspect the SRS, user manual draft, and system test plan (script INS). - Record size, time, and defect data (form INS). - Include customer/marketing/systems personnel. - Clarify and/or resolve all issues and update the SRS. |
| 8 | Engineering Requirements Specification | Produce or update the hardware/software engineering requirements specification (ERS). - principal (hardware-)software functions and performance - (hardware-)software-system interfaces - For each ERS item, reference its source in the SRS. - Establish and maintain bi-directional traceability between the ERS and SRS. |
| 9 | ERS Inspection | - Inspect the ERS (script INS). - Record size, time, and defect data (form INS). - Include hardware, software, and systems personnel. - Where appropriate, include customer personnel. - Clarify and/or resolve all issues and update the ERS. |
| 10 | SRS Baseline | Submit the SRS, ERS, and system test plan to the CCB for baselining. |
| 11 | Postmortem | Follow script PM for the phase postmortem, and submit PIPs. |

| Exit Criteria | - Inspected, completed SRS, ERS, user manual draft, and system test plan - Forms INS, ITL, LOGD, LOGT, MTG, PIP, SUMP, SUMQ - Requirements plan, actual, and earned-value data recorded and entered in the project notebook (specification NOTEBOOK) |
| --- | --- |

| TSPm Role Manager Team Launch - Script RTL |  |
| --- | --- |
| Purpose | To guide role manager teams in conducting an RTL launch workshop |
| Entry Criteria | - The role manager team members have all completed a TSPm team launch. - They all hold the same role manager position on their sub-teams. - The leadership team is available for RTL meetings 1 and 7. - All team members will attend meetings 1 through 7 and the postmortem. - For distributed teams, the remote role managers participate in the entire launch either in person or via telephone or videoconference. - An authorized TSP coach is on hand to lead the launch. |
| General | - Timing - RTL meetings 1 through 6 are held on the first launch day. - Meeting 7 and the postmortem (RTLPM) are on day 2. - Meetings 1 and 7 may be held simultaneously with the planning, process, quality, and support manager teams. - A subsequent launch could also hold meetings 1 and 7 with the customer interface, design, implementation, and test manager teams. |

| Step | Activities | Description |
| --- | --- | --- |
| 1 | Leadership Team Objectives | - Hold launch meeting 1 (script RTL1). - review the launch process and introduce team members - discuss the team’s goals with the leadership team |
| 2 | Goals and Lead Role Manager Selection | - Hold launch meeting 2 (script RTL2). The role manager team - defines and documents its goals - selects the lead role manager |
| 3 | Products Produced and Processes Used | - Hold launch meeting 3 (script RTL3). - define the products (processes, analyses, reports, judgments, and so forth) the team is to produce - determine the frequency and content of the periodic products - define the requirements and structure for the one-time products - define the processes to produce these products - assign documentation responsibility for these processes - list the processes on form INV and products on form SUMS |
| 4 | Produce the Overall Plan | - Hold launch meeting 4 (script RTL4). - estimate the sizes or other workload measures for the intended products - estimate the time to produce each product, either once or periodically |
| 5 | Team Member Plans | - Hold launch meeting 5 (script RTL5). - assign the required work to groups of team members - the team member groups make plans to produce the desired products |
| 6 | Report Preparation | - Hold launch meetings 6 (script RTL6). - prepare a report of the launch results to the leadership team |
| 7 | Management Review | - Hold launch meeting 7 (script RTL7). - review the role managers’ goals and plans with the leadership team - answer questions and discuss issues and concerns |
| PM | Launch Postmortem | - Hold the launch postmortem meeting (script RTLPM). - gather launch data and produce a launch report - enter this report in the project notebook - assess the launch process and prepare PIPs |

| # Exit Criteria | - Launch completed with documented team and member plans - Lead role manager selected - Defined team goals, processes, plans, products, risks, and schedules - Management agreement with the team plan - Resolution actions identified and responsibilities assigned - Launch data filed in the project notebook (specification NOTEBOOK). |
| --- | --- |

| TSPm RTL Launch Meeting 1 - Script RTL1 |  |
| --- | --- |
| Purpose | To review the leadership team’s goals and requirements with the role manager team |
| Entry Criteria | - The leadership team and program manager are present and prepared. - All participants are present (TSP coach and team members). - For distributed teams, remote members participate via telephone or videoconference. - Forms: MTG, ITL, PIP |
| General | - Meeting 1 takes from 1 to 2 hours. - Meeting 1 may cover the goals and requirements for several role manager teams at the same time. |

| Step | Activities | Description |
| --- | --- | --- |
| 1 | TSP and Launch Overview Meeting Role Assignments | The TSP coach leads the meeting (script MTG). The TSP coach - describes the RTL launch process and the launch products - reviews the meeting roles and assigns a timekeeper and recorder (specification ROLE) - discusses the work to be done in this meeting |
| 2 | Leadership Team’s Goals and Requirements | The program manager or designee - describes the leadership team’s goals for this role manager team - defines the immediate needs - describes periodic reporting requirements and frequency - discusses the need for early warning of potential problems - outlines the need for managing key project risks - answers the team's questions |
| 3 | Goal Questions | The team members should satisfy themselves that they understand the leadership team’s goals and requirements. - the reasons for each goal and requirement - how the leadership team will determine of their needs are met |
| 4 | Reporting Questions | The team members should satisfy themselves that they understand the reports the leadership team is requesting. - specific content of the reports - and special format needs of constraints - how the reports are to be used - when and how frequently the reports are needed |
| 5 | Launch Meeting Documentation | The recorder completes form MTG. - lists the attendees and the time spent by agenda item - describes decisions made and by whom - documents pending actions: what, when, and by whom - verifies the meeting report with the meeting attendees and saves the completed form MTG to give to the lead role manager |

| Exit Criteria | - Launch meeting 1 activities have been completed. - The role manager team understands the leadership team’s needs and goals. - All of the team's questions have been answered, or actions are planned to get the answers. - All risks and issues have been recorded (form ITL). - All process improvement suggestions have been recorded (form PIP). - The meeting report has been completed (form MTG and attachments). - The lead role manager has copies of all meeting products. |
| --- | --- |

| TSPm RTL Launch Meeting 2 - Script RTL2 |  |
| --- | --- |
| Purpose | To guide the role manage team in setting goals and selecting the lead role manager |
| Entry Criteria | - All participants are present (TSP coach and team members). - For distributed teams, remote members participate via telephone or videoconference. - Forms: GOAL, ITL, MTG, PIP |
| General | Meeting 2 generally takes 1 to 2 hours. |

| Step | Activities | Description |
| --- | --- | --- |
| 1 | Meeting Roles | Select the meeting roles (specification ROLE). - The TSP coach leads the meeting (script MTG). - The timekeeper tracks time and keeps the meeting on schedule. - The recorder notes meeting decisions and actions and writes the meeting report (form MTG). |
| 2 | Meeting Overview | The TSP coach reviews the work to be done in this meeting and the products to be produced. |
| 3 | Review Management's Stated Goals | The TSP coach leads the team in reviewing management's goals to - get agreement on what management stated as the role manager team’s goals - identify one or more measure for the key management goals - recording results on form GOAL. |
| 4 | Implied Goals | The TSP coach leads the team in defining the goals that are implied by management's stated goals. Considerations include team productivity, quality performance, risk analysis, and process improvement (see TSPm Role Manager Team Responsibilities). |
| 5 | Team Goals | The TSP coach leads the team in - establishing team goals to meet management's stated and implied goals - identifying one or more measures for each team goal - recording results on form GOAL |
| 6 | Goal Tracking | The TSP coach leads the team in - assigning team-member tracking responsibility for each goal - recording the assignments on form GOAL - establishing a tracking schedule for each goal |
| 7 | Role Team Leader Selection | - The TSP coach leads the team’s selection of the lead role manager (see TSPm Lead Role Manager Responsibilities). - Each team member first makes whatever comments he or she chooses. - All members then write their selections and give them to the TSP coach. - The TSP coach tallies the votes and announces the selection. |
| 8 | Launch Meeting Documentation | The recorder completes form MTG. - lists the attendees and the time spent by agenda item - describes decisions made and by whom - documents pending actions: what, when, and by whom - verifies the meeting report with the meeting attendees - gives the completed form MTG to the lead role manager. |

| Exit Criteria | - Launch meeting 2 activities have been completed. - The lead role manager has been selected. - Role manager team goals are documented (form GOAL). - All risks and issues have been recorded (form ITL). - All process improvement suggestions have been recorded (form PIP). - The meeting report has been completed (form MTG and attachments). - The lead role manager has copies of all meeting products. |
| --- | --- |

| TSPm RTL Launch Meeting 3 - Script RTL3 |  |
| --- | --- |
| Purpose | To guide the role manager team in defining the products to be produced and the processes to be used |
| Entry Criteria | - All participants are present (TSP coach, team members, lead role manager). - For distributed teams, remote members participate via telephone or videoconference. - The documented team goals are available. - Forms: INV, ITL, MTG, PIP, SUMS |
| General | Meeting 3 generally takes from 1 to 2 hours. |

| Step | Activities | Description |
| --- | --- | --- |
| 1 | Meeting Roles | Select the meeting roles (specification ROLE). - The TSP coach leads the meeting (script MTG). - The timekeeper tracks time and keeps the meeting on schedule. - The recorder notes meeting decisions and actions and writes the meeting report (form MTG). |
| 2 | Meeting Overview | The TSP coach reviews the work to be done in this meeting and the products to be produced. |
| 3 | Products Produced | - The lead role manager leads the team in defining the products the team is to produce either once or periodically. - These products may be processes, analyses, reports, judgments, or anything else the leadership team requested. |
| 4 | Development Process | The lead role manager leads the team in - defining the processes to be used - recording the results on form INV - making a plan to document each process - deciding who will document each process |
| 5 | Launch Meeting Documentation | The recorder completes form MTG. - lists the attendees and the time spent by agenda item - describes decisions made and by whom - documents pending actions: what, when, and by whom - verifies the meeting report with the meeting attendees - gives the completed form MTG to the lead role manager |

| Exit Criteria | - Launch meeting 3 activities have been completed. - List of products to be produced has been recorded (form SUMS). - Overall and detailed development process steps are documented. - Process plan and support plan are documented (form INV). - All risks and issues have been recorded (form ITL). - All process improvement suggestions have been recorded (form PIP). - The meeting report has been completed (form MTG and attachments). - The lead role manager has copies of all meeting products. |
| --- | --- |

| TSPm RTL Launch Meeting 4 - Script RTL4 |  |
| --- | --- |
| Purpose | To guide the role manager team in producing a plan for its work |
| Entry Criteria | - All participants are present (TSP coach, team members, lead role manager). - For distributed teams, remote members participate via telephone or videoconference. - A list of the products to be produced - The defined processes to produce these products. - Forms: ITL, MTG, PIP, SCHED, SUMS, TASK |
| General | Meeting 4 generally takes 1 to 2 hours. |

| Step | Activities | Description |
| --- | --- | --- |
| 1 | Meeting Roles | Select the meeting roles (specification ROLE). - The TSP coach leads the meeting (script MTG). - The timekeeper tracks time and keeps the meeting on schedule. - The recorder notes meeting decisions and actions and writes the meeting report (form MTG). |
| 2 | Meeting Overview | The TSP coach reviews the work to be done in this meeting and the products to be produced. |
| 3 | Size Estimate | The lead role manager leads the team in - estimating the sizes of the products the role manager team will produce - recording these estimates on form SUMS |
| 4 | Determine Project Tasks | The lead role manager leader leads the team in producing a detailed task plan for the required work. - Use the team’s processes defined in meeting 3. - The plan tasks are each 10 hours or less per team member. |
| 5 | Overall Resource Estimate | The lead role manager leads the team in estimating the resources required for each task defined in step 4 (form TASK). |
| 6 | Resource Availability | The lead role manager leads the team in - estimating the team’s task hours to be used for each project week (form SCHED) - determining the work schedule |
| 7 | Launch Meeting Documentation | The recorder completes form MTG. - lists the attendees and the time spent by agenda item - describes decisions made and by whom - documents pending actions: what, when, and by whom - verifies the meeting report with the meeting attendees - gives the completed form MTG to the lead role manager |

| Exit Criteria | - Launch meeting 4 activities have been completed. - The role manager team plan has been documented. - All risks and issues have been recorded (form ITL). - All process improvement suggestions have been recorded (form PIP). - The meeting report has been completed (form MTG and attachments). - The lead role manager has copies of all meeting products. |
| --- | --- |

| TSPm RTL Launch Meeting 5 - Script RTL5 |  |
| --- | --- |
| Purpose | To guide the role manager team in producing a balanced plan |
| Entry Criteria | - All participants are present (TSP coach, team members, lead role manager). - For distributed teams, remote members participate via telephone or videoconference. - Documented process, quality, and support plans are available. - Documented overall plan has been prepared. - Overall and next-phase effort estimates are available. - Forms: SCHED, TASK, INV, ITL, MTG, PIP, SUMS |
| General | Meeting 5 generally takes 1 to 2 hours. |

| Step | Activities | Description |
| --- | --- | --- |
| 1 | Meeting Roles | Select the meeting roles (specification ROLE). - The TSP coach leads the meeting (script MTG). - The timekeeper tracks time and keeps the meeting on schedule. - The recorder notes meeting decisions and actions and writes the meeting report (form MTG). |
| 2 | Meeting Overview | The TSP coach reviews the work to be done in this meeting and the products to be produced. |
| 3 | Allocate Tasks to Team Members | The lead role manager leads the team in - allocating the plan tasks to individual team members - maintaining a balanced workload among the team members |
| 4 | Assess the Plan | - Each role manager team member - determines the impact of the role manager work on his or her other commitments - attempts to resolve any issues with the role manager team |
| 5 | Resolve Plan Issues | - Where issues cannot be resolved with the role manager team, each role manager team member - negotiates the impact with his or her team leader and team - where possible, resolves conflicts with the team leader and lead role manager - takes unresolved conflicts to the leadership team (along with the lead role manager) |
| 6 | Review the Plan | The team leader leads the team in reviewing the plan to ensure that it - produces the required products - meets the established team goals - equitably balances the role manager team’s workload |
| 7 | Launch Meeting Documentation | The recorder completes form MTG. - lists the attendees and the time spent by agenda item - describes decisions made and by whom - documents pending actions: what, when, and by whom - verifies the meeting report with the meeting attendees - gives the completed form MTG to the planning manager |

| Exit Criteria | - Launch meeting 5 activities have been completed. - Detailed next-phase plans for each team member and the team are documented (forms INV, SUMP, SUMQ, TASK, SCHED). - All risks and issues have been recorded (form ITL). - All process improvement suggestions have been recorded (form PIP). - The meeting report has been completed (form MTG and attachments). - The lead role manger has copies of all meeting products. |
| --- | --- |

| TSPm RTL Launch Meeting 6 - Script RTL6 |  |
| --- | --- |
| Purpose | To guide the team in preparing for the leadership team meeting (RTL7) |
| Entry Criteria | - All participants are present (TSP coach, team members, lead role manager). - For distributed teams, remote members participate via telephone or videoconference. - Forms: ITL, MTG, PIP - Specifications: NOTEBOOK and STATUS |
| General | In the leadership team meeting (meeting 7) the role manager team will - review the team’s goals - review the project plan and any questions or issues with this plan Meeting 6 generally takes 1 to 2 hours. |

| Step | Activities | Description |
| --- | --- | --- |
| 1 | Meeting Roles | Select the meeting roles (specification ROLE). - The TSP coach leads the meeting (script MTG). - The timekeeper tracks time and keeps the meeting on schedule. - The recorder notes meeting decisions and actions and writes the meeting report (form MTG). |
| 2 | Meeting Overview | The TSP coach reviews the objectives and procedure for the meeting, and describes the example contents of the management presentation. |
| 3 | Planning for the Leadership Team Meeting | The lead role manager leads the team in - discussing the material to be covered - deciding what to present and who will present it - assigning the preparation work to one or more team members |
| 4 | Meeting Preparation | The lead role manager summarizes - the work to be done - who will produce each item - the times when the items will be completed - who will present each item |
| 5 | Launch Meeting Documentation | The recorder completes form MTG. - lists the attendees and the time spent by agenda item - describes decisions made and by whom - documents pending actions: what, when, and by whom - verifies the meeting report with the meeting attendees - gives the completed form MTG to the planning manager |

| Exit Criteria | - Launch meeting 6 activities have been completed. - The leadership team meeting topics are decided and the preparation work planned. - All risks and issues have been recorded (form ITL). - All process improvement suggestions have been recorded (form PIP). - The meeting report has been completed (form MTG and attachments). - The lead role manger has copies of all meeting products. |
| --- | --- |

| TSPm RTL Launch Meeting 7 - Script RTL7 |  |
| --- | --- |
| Purpose | To guide the team through the final launch leadership team meeting |
| Entry Criteria | - All participants are present (TSP coach, team members, lead role manager, and the leadership team). - For distributed teams, remote members participate via telephone or videoconference. - The management briefing guidelines have been reviewed. - Copies of the team presentation are available. - Forms: ITL, MTG, PIP |
| General | - In the leadership team meeting, the team reviews with management its plan and any questions or issues regarding the plan. - Meeting 7 generally takes 1 to 2 hours. |

| Step | Activities | Description |
| --- | --- | --- |
| 1 | Meeting Roles | Select the meeting roles (specification ROLE). - The TSP coach leads the meeting (script MTG). - The timekeeper tracks time and keeps the meeting on schedule. - The recorder notes meeting decisions and actions and writes the meeting report (form MTG). |
| 2 | Agenda and Objectives | The lead role manager reviews the meeting agenda and objectives. |
| 3 | Team Goal and Plan Comparison | The lead role manager or other team member summarizes the - leadership team’s stated goals - the team's plan and goals - how the team's plan and goals compare with management’s goals - the products the role manager team will produce, their characteristics, and their schedules |
| 4 | Discussion | The lead role manager asks for any questions and closes the meeting. |
| 5 | Launch Meeting Documentation | The recorder completes form MTG. - lists the attendees and the time spent by agenda item - describes decisions made and by whom - documents pending actions: what, when, and by whom - verifies the meeting report with the meeting attendees - gives the completed form MTG to the planning manager |

| Exit Criteria | - The leadership team agrees with the team plan or identifies resolution actions and assigns responsibilities. - All risks and issues have been recorded (form ITL). - All process improvement suggestions have been recorded (form PIP). - The meeting report has been completed (form MTG and attachments). - The lead role manger has copies of all meeting products. |
| --- | --- |

| TSPm RTL Postmortem Meeting - Script RTLPM |  |
| --- | --- |
| Purpose | To guide the role manager team through the launch postmortem |
| Entry Criteria | - All participants are present (TSP coach, team members, lead role manager). - For distributed teams, remote members participate via telephone or videoconference. - All the team members have copies for the role manager team’s plan - Forms: ITL, MTG, PIP - Specification: NOTEBOOK |
| General | Timing - The launch postmortem meeting can be held before or after meeting 7. - The PM meeting generally takes about 1 hour. |

| Step | Activities | Description |
| --- | --- | --- |
| 1 | Meeting Roles | Select the meeting roles (specification ROLE). - The TSP coach leads the meeting (script MTG). - The timekeeper tracks time and keeps the meeting on schedule. - The recorder notes meeting decisions and actions and writes the meeting report (form MTG). |
| 2 | Meeting Overview | The TSP coach reviews the work to be done in this meeting and the products to be produced. |
| 3 | Launch Postmortem | The lead role manager reviews the launch data to ensure that - all required launch data are gathered and recorded - data are properly entered in the appropriate project forms and databases - responsibility is assigned for preparing the launch materials for entry in the project notebook (specification NOTEBOOK) |
| 4 | Prepare PIPs | The TSP coach leads the team through a process evaluation. - identifies launch process problems or inconveniences - suggests process improvements - completes PIPs for these suggestions |
| 5 | Launch Meeting Documentation | The recorder completes form MTG. - lists the attendees and the time spent by agenda item - describes decisions made and by whom - documents pending actions: what, when, and by whom - verifies the meeting report with the meeting attendees - gives the completed form MTG to the planning manager |

| Exit Criteria | - Launch postmortem activities have been completed. - The leadership team presentation has been added to the project notebook. - All risks and issues have been recorded (form ITL). - All process improvement suggestions have been recorded (form PIP). - The meeting report has been completed (form MTG and attachments). - The lead role manger has copies of all meeting products. |
| --- | --- |

| TSP Management and Customer Status Meeting - STATUS |  |
| --- | --- |
| Purpose | - To guide in planning and conducting the periodic management and customer status meetings - The purpose of these meetings is to keep management and the customer informed on project progress, status, and risks. - By being informed, management and/or the customer can help prevent problems and better resolve those problems that cannot be prevented. |
| Entry Criteria | - Management meeting topics agreed to in the weekly team meeting - Customer meeting topics agreed to in the management meeting - Specification: STATUS - Forms: MTG |
| General | - Timing - These meetings are held frequently: weekly, biweekly, or monthly. - The choice should be left to management and the customer. - Meeting preparation - These meetings should follow a standard agenda. - Produce and distribute form MTG to all attendees in advance. - Meeting roles - The team leader typically conducts the meetings (script MTG). - Unless other team members attend to handle them, the team leader also handles the timekeeper and recorder roles. - Customer meeting - The customer meeting can follow the same agenda with changes. - Meeting report - The team leader prepares form MTG (specification STATUS). - Record any risks requiring attention and their likely consequences. - Record any decisions, planned actions, or other key information. - Include a copy of the team’s weekly status data. |

| Step | Activities | Description |
| --- | --- | --- |
| 1 | Meeting Introduction | The team leader opens the meeting by - summarizing the topics and key issues to be covered - stating all of the key issues (no late surprises) - reviewing the meeting purpose and agenda - asking for suggested changes or additions |
| 2 | Project Status | The team leader or planning manager summarizes team status (see STATUS). - actual versus planned team earned value and hours spent - current earned value projection to complete - the planned recovery actions if delays are indicated |
| 3 | Risks and Actions | The team leader - lists previously agreed to actions and their status - reviews the status of project risks - summarizes the status of previously identified risks - requests management help for out-of-control risks - discusses any newly identified risks and likely consequences |
| 4 | Other Agenda Items | Any other agenda items are covered. |
| 5 | Meeting Conclusion | The team leader - restates and verifies each meeting decision - confirms the who, what, and when for each planned action - reviews customer meeting topics and asks for agreement - asks for suggested meeting process improvements |

| Exit Criteria | Meetings held and meeting reports distributed to all attendees and filed in the project NOTEBOOK |
| --- | --- |

| TSP Release Test - Script TEST |  |
| --- | --- |
| Purpose | - To integrate product components into a working system - To identify inter-component and system defects and return defective components to the developers for rework - While occasional defects may be found, integration and system test are not intended to be defect-removal activities. |
| Entry Criteria | - Detailed next-phase or cycle plan and fix prerequisites and co-requisites - A current list of project risks and exposures - All components and fixes inspected, unit tested, and baselined - Development, inspection, and unit test data available - Forms: DEFECT, ITL, LOGT, PIP, SUMP, SUMQ, TestLog |
| General |  |

| Step | Activities | Description |
| --- | --- | --- |
| 1 | Build | - Using script TEST1, produce a detailed build plan. - Review the build plan and make needed corrections. - Review component submissions for quality and completeness. - Return defective products or fixes to development. - Following the plan, build the product. - Check the build for completeness. - Regression test the built product and record data in TestLog. - Release the build to integration and system test. - When defects are found during build, follow script TESTD. - Repeat the build process until system testing is complete. - Build as often as required to ensure that the implementation and test engineers are working with a current-level product. - With many defect fixes or changes, daily builds are required. |
| 2 | Integration | - Using script TEST2, produce a detailed integration plan. - Review the integration plan and make needed corrections. - Review component and fix submissions for quality. - Return defective products or fixes to development. - Following the plan, integrate the product. - Check the integration for completeness. - Regression test the integrated product, record data in TestLog. - Release the integrated product to development and system test. - When defects are found in integration, follow script TESTD. - Continue integration until all components are integrated. |
| 3 | System Test | - Using script TEST3, produce a detailed system test plan. - Review the system test plan and make needed corrections. - Review test submissions for quality and completeness. - Return defective products or fixes to integration. - Following the plan, system test product, record data in TestLog. - Release the tested system for customer acceptance and use. - When defects are found in system test, follow script TESTD. - Continue system testing until the product is fully integrated and meets the quality criteria. |

| Exit Criteria | - All components and fixes pass all integration and system tests. - Forms DEFECT, ITL, LOGT, PIP, SUMP, SUMQ, TestLog - Test plan, actual, and earned-value data recorded and entered in project notebook (specification NOTEBOOK) |
| --- | --- |

| TSP Product Build - Script TEST1 |  |
| --- | --- |
| Purpose | - To integrate components and fixes into a working system - To return defective components or fixes for rework - While occasional defects may be found, product build is not intended as a defect-removal phase. |
| Entry Criteria | - Detailed next-phase or cycle plan which includes activities described below, and a list of project risks and exposures - All submitted components inspected, unit tested, and baselined - Development, inspection, and unit test data available - Forms: DEFECT, ITL, LOGT, SUMP, SUMQ, TestLog |
| General |  |

| Step | Activities | Description |
| --- | --- | --- |
| 1 | Build Development | - Develop required procedures and support facilities. - Produce the initial regression test package. - Using any previous build, integration, and system test cases, update the regression package for subsequent builds. |
| 2 | Build Acceptance | - Review component and fix submissions for quality. - Check all components and fixes for dependency requirements. - Review the process data to verify that all component and fix development followed the team process. - Return unqualified components and fixes for rework. |
| 3 | Product Build | - Check the proposed build for consistency and completeness. - Recompile all accepted new components and fixes. - Link all components and fixes into a completed system. |
| 4 | Build Verify | Review the completed build to ensure that - all planned components and fixes are included - all prerequisites and corequisites are satisfied - the system will perform basic functions |
| 5 | Regression Test | - Run the regression tests and record test data in the TestLog. - If defects are found, determine if they are in the components and fixes, or in the build or testing processes. - If in the testing or build processes, correct, rebuild, and retest. - If in the components or fixes, follow script TESTD. - When the regression tests are satisfactorily completed, release the build for integration, system test, and use by development. |
| 6 | Build Release | - Produce the build release inventory with component, fix, and function content, fix numbers, and change locations. - Update the configuration management system. - complete build release package - component and fix control numbers and file location data - data on all regression test runs and their results |
| 7 | Test Data Summary | Complete DEFECT, SUMP, and SUMQ forms. |

| Exit Criteria | - All components and fixes are incorporated in the system build. - The build correctly runs all regression tests. - The completed build release is under configuration control. - Completed DEFECT, ITL, LOGT, SUMP, SUMQ, TestLog - Test plan, actual, and earned-value data are recorded and entered in project notebook (specification NOTEBOOK). |
| --- | --- |

| TSP Integration - Script TEST2 |  |
| --- | --- |
| Purpose | - To integrate components and fixes into a working system - To ensure that only accepted and high-quality components and fixes are integrated into the system - To identify inter-component defects and return defective components for reinspection and rebuild - While occasional defects may be found, integration is intended to check system interfaces, not to find and fix defects. |
| Entry Criteria | - Detailed next-phase or cycle plan, which includes activities described below, and a list of project risks and exposures - A complete, documented, and regression tested build package - Forms: DEFECT, ITL, LOGT, SUMP, SUMQ, TestLog |

| Step | Activities | Description |
| --- | --- | --- |
| 1 | Integration Acceptance | - Check the build package and return it if incomplete. - Review the testing data against the component and fix criteria. - Return non-complying components and fixes. |
| 2 | Integration Plan | - Determine the interfaces to be tested and a test strategy. - Take advantage of available test materials from all test phases. - Estimate and plan the integration development effort. - The plan should consider the integration process, integration resources, number of integration cycles, and their schedule. |
| 3 | Integration Plan Review | Review the integration plan to ensure that all - interfaces are tested under normal and error conditions - defects found in prior integration cycles are retested |
| 4 | Integration Development | - Produce the integration test package. - Develop required test data, procedures, and support materials. |
| 5 | Test Package Verify | Check the integration test package to ensure that - tests are properly documented and (if possible) self-checking - all new code has been reviewed, inspected, and tested |
| 6 | Integration Testing | - Follow the test plan and record test data in the TestLog. - For every defect, complete a DEFECT form and call for a test defect review (script TESTD). - Suspend integration of the defective components and fixes until the review is completed. |
| 7 | Integration Review | Review the integration process to ensure that - all planned products, features, and fixes are included - any defect fixes have been retested - the test data are complete and properly documented - DEFECT forms are completed for all defects found |
| 8 | Integration Release | - Update the build package release inventory for any changes. - fix numbers and change locations - Update the configuration management system. - complete integration release package - fix control numbers and change locations - data on all integration and regression test runs and results |
| 9 | Test Data Summary | Complete DEFECT, SUMP, and SUMQ forms. |

| Exit Criteria | - All components and fixes incorporated in the system - System correctly runs all integration tests - Completed integration release under configuration control - Completed DEFECT, ITL, LOGT, SUMP, SUMQ, TestLog - Test plan, actual, and earned-value data recorded and entered in project notebook (specification NOTEBOOK) |
| --- | --- |

| TSP System Test - Script TEST3 |  |
| --- | --- |
| Purpose | - To stress test the system, verify that it is usable, and that it works properly under all normal and abnormal conditions - To ensure that high-quality components and fixes are released - To identify and return defective components and fixes - While defects may be found, system test is intended to usability and stress test the system, not to find and fix defects. |
| Entry Criteria | - A built and integrated system released from integration - Forms: DEFECT, ITL, LOGT, SUMP, SUMQ, TestLog |
| General |  |

| Step | Activities | Description |
| --- | --- | --- |
| 1 | System Test Acceptance | - Check the integration package and return it if incomplete. - Review the testing data against the component and fix criteria. - Return non-complying components. |
| 2 | System Test Plan | - Determine the conditions to be tested and a test strategy. - Take advantage of available test materials from all test phases. - Estimate and plan the system test development effort. - The plan should consider the system test process, resources, number of system test cycles, and their schedule. |
| 3 | System Test Plan Review | Review the system test plan to ensure that all - system conditions are tested in normal and stress conditions - installation, conversion, operating, recovery, and performance capabilities are tested for correctness and usability - defects found in prior system test cycles are retested |
| 4 | System Test Development | - Produce the system test package. - Develop required test data, procedures, and support materials. |
| 5 | Test Package Verify | Check the system test package to ensure that - tests are properly documented and (if possible) self checking - all new code has been reviewed, inspected, and tested |
| 6 | System Testing | - Follow the test plan and record test data in the TestLog. - For every defect, complete a DEFECT form and call for a test defect review (script TESTD). - Suspend system test of the defective components and fixes until the review is completed. |
| 7 | System Test Review | Review the system test process to ensure that - all planned products, features, and fixes are included - any prior defect fixes have been retested - the test data are complete and properly documented |
| 8 | System Release | Update the system release inventory for any changes. - fix numbers and change locations Update the configuration management system. - complete system release package - fix control numbers and change locations - data on all system test runs and results |
| 9 | Test Data Summary | Complete DEFECT, SUMP, and SUMQ forms. |

| Exit Criteria | - All components and fixes are incorporated in the tested system. - The system correctly runs all system usability and stress tests. - The completed system release is under configuration control. - Completed DEFECT, ITL, LOGT, SUMP, SUMQ, TestLog - Test plan, actual, and earned-value data are recorded and entered in the project notebook (specification NOTEBOOK). |
| --- | --- |

| TSP Test Defect Handling - Script TESTD |  |
| --- | --- |
| Purpose | - To review every defect found in build, integration, or system test and decide whether - defects are symptoms of quality problems and the defective components or fixes should be returned to development - the defects that are not symptoms of quality problems, should be fixed by development, and test should continue |
| Entry Criteria | - One or more defects have been found during build, integration, or system testing. - Form: MTG - Specification: NOTEBOOK |
| General | - When testing finds defects in a system, they are generally clustered in a relatively small percentage of the code. - Re-inspecting defect-prone components and fixes can save substantial test time and produce high-quality products. |

| Step | Activities | Description |
| --- | --- | --- |
| 1 | Defect Data Analysis | Analyze the defect and process data on each defect to determine - the defective module, component, or fix - when the defect was injected - the phases that missed finding the defect |
| 2 | Product Analysis | - Update the component defect-density map for all test defects. - Analyze the component or fix defect-density map to identify defect-prone modules, components, or fixes. |
| 3 | Address Defects | The project leader - describes the meeting's purpose and the decisions to be made - determines who will fill the meeting roles (script MTG) |
|  |  | The team reviews the available defect data to decide if components or fixes are defective and should be returned to development. - remedial actions to be taken - criteria for resubmitting each component or fix to test |
|  |  | The reporter and timekeeper complete the meeting report, including - defect and product analysis results - who, what, and when of each decision (MTG form) |
| 4 | Product Resubmission | When previously rejected products are resubmitted, the quality and process managers verify that the actions meet the team's criteria. |

| Exit Criteria | - The defective products are reworked and resubmitted to test. - The defect meeting report, including all component defect data, has been entered in MTG form and the project notebook (specification NOTEBOOK). |
| --- | --- |

| TSP Weekly Team Meeting - Script WEEK |  |
| --- | --- |
| Purpose | - To plan and conduct the weekly team meetings - These meetings are held to ensure that all team members understand current project status and know what to do next. |
| Entry Criteria | - All team members have provided the planning manager with - updated task and schedule plan - development, role, and risk status and plans - The planning manager has updated the project plan - Forms: MTG, WEEK - Specifications: NOTEBOOK, ROLE, STATUS |
| General | - The meetings are scheduled at a standard time every week. - All team members should regularly attend. |

| Step | Activities | Description |
| --- | --- | --- |
| 1 | Meeting Roles | - The team leader typically leads the meeting (script MTG). |
| 2 | Meeting Agenda | - Review the meeting purpose and agenda and select the roles. - Check for any changes in the purpose or agenda. |
| 3 | Manager's Report | The team leader opens the meeting with a brief summary of any new developments or issues. |
| 4 | Role Report | The team members review their assigned role responsibilities and the status against each (specification ROLE). |
| 5 | Goal and Risk Reports | At a minimum goals and risks should be discussed biweekly on an alternating basis. Goal reporting: Each responsible team member reports on status against team goals. Risk Reporting: The team members review status and changes in their assigned risks since the last report, and highlight any impending flag dates and required actions. Identifies new risks. |
| 6 | Project Status | - Each team member reviews his or her progress and status. - actual versus planned tasks completed in the prior week - actual versus planned earned value and hours spent - The planning manager summarizes the team progress and status. - actual versus planned team earned value and hours spent - current earned value projection to complete |
| 7 | Next Week Plans | - Each team member summarizes tasks planned for the next week and any special dependencies. - The team leader reviews expected issues or actions. - The team sets task, hour, and EV goals for the next week. |
| 8 | Meeting Wrap-up | The team leader checks that all needed items have been covered. - All team members have reported their project status. - All risks and roles have been reported on. - Any newly identified risks have been evaluated and assigned. - Any other agenda topics are covered. |
| 9 | Meeting Conclusion | The team leader asks if there are any further comments. - confirms the meeting decisions and planned actions - agrees on topics for the management and customer meetings (specification STATUS) - asks for any suggested improvements in the meeting process |
| 10 | Meeting Report | The recorder and team leader produce the meeting report (form MTG). - planned versus actual hours and earned value - risks requiring management attention and why - any decisions, planned actions, or other key information |

| Exit Criteria | The completed WEEK and MTG forms are filed in the project notebook. |
| --- | --- |

| TSPm Weekly Leadership Meeting - Script WEEKL |  |
| --- | --- |
| Purpose | - Use this script to plan and conduct the weekly team leader meetings. - These meetings ensure that the leadership team understands current project status, issues, and plans. - The meetings also provide an informed forum for management decision. |
| Entry Criteria | - Each team leader has suggested agenda items and has data on his or her team’s status. - updated task and schedule plans - WEEK reports - earned versus planned value - weekly planned versus actual hours - milestone status and plans - dependency status and plans - risk and issue status and plans - For distributed teams, remote team leaders participate via telephone or videoconference. |
| General | - The leadership meetings are scheduled at a standard time every week. - They follow the sub-team weekly meetings. - All members of the leadership team regularly attend. |

| Step | Activities | Description |
| --- | --- | --- |
| 1 | Meeting Role Assignments | - Select the meeting roles (specification ROLE). - The TSP coach leads the meeting (script MTG). - The timekeeper tracks time and keeps the meeting on schedule. - The recorder notes meeting decisions and actions and writes the meeting report (form MTG). |
| 2 | Meeting Agenda | - The project manager reviews the agenda and checks for changes. |
| 3 | Project Manager Report | - The project manager opens the meeting with a brief summary of any new developments or issues. |
| 4 | Team Leader Reports | - Each sub-team leader reviews the status of his or her sub-team. - plan versus actual tasks completed in the prior week and to date - plan value versus earned value in the prior week and to date - plan versus actual weekly hours spent for the week and to date - milestone status and plans - dependency status and plans - status of assigned risks and any needed actions - task, hour, and earned-value plans for the next week |
| 5 | Role Manager Team Status | - The team leaders summarize the status of the role manager teams for which they are responsible. |
| 6 | Other Topics | - Any other agenda topics are next covered. |
| 7 | Meeting Conclusion | - The project manager checks that all needed items have been covered. - checks that all team leaders have reported status, risks, and issues - verifies that all new risks have been evaluated and assigned - confirms the meeting decisions and actions (who, what, and when) - schedules any required follow-up meetings - asks for suggested improvements in the meeting process |
| 8 | Meeting Report | - The recorder/project manager produce the meeting report (form MTG). - planned versus actual hours and earned value - risks requiring management attention and why - decisions, planned actions, or other key information |

| # Exit Criteria | Completed WEEK forms, MTG forms, and the team and sub-team status information filed in the project notebook |
| --- | --- |

| TSPm Leadership Meeting with Role Managers - Script WEEKLR |  |
| --- | --- |
| Purpose | - The leadership team should meet with each role manager team about once a month. - This script is used by the leadership team to plan and conduct their meetings with the role manager teams. - These meetings are to ensure that the role manager teams understand and are working on the tasks the leadership team desires. - The meetings provide an informed forum for management decision. |
| Entry Criteria | - All meeting participants have provided suggested agenda items. - The project manager has produced and distributed the meeting agenda. - The role managers are prepared to make role reports. - For distributed teams, remote role managers participate via telephone or videoconference. |
| General | - Prior to the meeting, the leadership team has informed the role managers of - the items to be included in the role manager team report - how often these reports are to be made |

| Step | Activities | Description |
| --- | --- | --- |
| 1 | Meeting Role Assignments | - Select the meeting roles (specification ROLE). - The TSP coach leads the meeting (script MTG). - The timekeeper tracks time and keeps the meeting on schedule. - The recorder notes meeting decisions and actions and writes the meeting report (form MTG). |
| 2 | Meeting Agenda | - The project manager reviews the meeting agenda and checks for changes. |
| 3 | Role Manager Report | - The lead role manager for the reporting team - summarizes the tasks assigned to that team - reviews the status of each task - summarizes any issues or problems - describes where the team needs guidance or assistance - provides estimated dates for when each task will be completed - asks for questions or discussion |
| 4 | Additional Tasks and Assignments | - The project manager - describes any additional assignments for the role manager team - explains when the leadership team would like those tasks completed - asks the role managers to submit a plan for doing the required work |
| 5 | Meeting Wrap-up | - The project manager checks that all needed items have been covered. - all role managers have had an opportunity to comment or ask questions - a follow-up meeting has been scheduled with the role managers |
| 6 | Meeting Conclusion | - The project manager asks for further comments and discussion. - confirms the meeting decisions and actions - asks for suggested improvements in the meeting process |
| 7 | Meeting Report | - The recorder assists the project manager in producing and distributing the meeting report (form MTG). - tasks completed - new tasks assigned - decisions, planned actions, or other key information - risks, issues and mitigations |

| # Exit Criteria | - Completed WEEK forms - Copies of any materials submitted by the role managers are filed in the project notebook - Meeting report produced and distributed to all attendees |
| --- | --- |