Copyright 2018 Carnegie Mellon University.  All rights reserved.

This material is based upon work funded and supported by the Department of Defense under Contract No. FA8721-05-C-0003 with Carnegie Mellon University for the operation of the Software Engineering Institute, a federally funded research and development center.

Any opinions, findings and conclusions or recommendations expressed in this material are those of the author(s) and do not necessarily reflect the views of the United States Department of Defense.

NO WARRANTY. THIS MATERIAL IS FURNISHED ON AN “AS-IS” BASIS WITH NO WARRANTIES OF ANY KIND, EITHER EXPRESSED OR IMPLIED, INCLUDING, BUT NOT LIMITED TO, WARRANTY OF FITNESS FOR PURPOSE OR MERCHANTABILITY, ANY WARRANTY WITH RESPECT TO FREEDOM FROM PATENT, TRADEMARK, OR COPYRIGHT INFRINGEMENT, OR THIRD PARTY INTELLECTUAL PROPERTY RIGHTS.

[Distribution Statement A] This material has been approved for public release and unlimited distribution.  The United States Government has Unlimited Rights in this material as defined by DFARS 252.227-7013.

The text and illustrations in this material are licensed by Carnegie Mellon University under a Creative Commons Attribution 4.0 International License.

The Creative Commons license does not extend to logos, trade marks, or service marks of Carnegie Mellon University.

Workshop Handouts - Meeting 2

| Contents |  |
| --- | --- |
| Page | Element |
| 2 | Meeting Report - Launch Meeting 2 (partially completed) |
| 3 | TSP Launch Meeting 2 - Script LAU2 |
| 4 | TSP Team Role Assignments - Form ROLE (blank) |
| 5 | TSP Team Role Assignments Instructions - Form ROLE |
| 6 | TSP Role Assignment Matrix - Form ROLEMX (blank) |
| 7 | TSP Role Assignment Matrix Instructions - Form ROLEMX |
| 8 | TSP Team Goals - Form GOAL (blank) |
| 9 | TSP Team Goals Instructions - Form GOAL |
| 10 | TSP Issue and Risk Tracking Log - Form ITL (blank) |
| 11 | TSP Process Improvement Proposal - Form PIP (blank) |

Note: for meeting 2, the TSP launch and relaunch processes are the same.

Meeting Report - Launch Meeting 2

| Name |  |  |  |  |  |  |  |  |  | Date |  |  |
| --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- |
| Chairperson |  | TSP Coach |  |  |  | Location |  |  |  |  |  |  |
| Meeting Date |  |  |  |  |  | Time From: |  |  |  |  | To: |  |
| Subject/Purpose |  |  |  | TSP Launch Meeting 2: To assign team roles and establish the project's goals |  |  |  |  |  |  |  |  |
| Attendees |  |  |  |  |  |  |  |  |  |  |  |  |
| Name |  |  |  |  |  |  |  |  |  |  | Role |  |
| Agenda |  |  |  |  |  |  |  |  |  |  |  |  |
| Times (min.) |  |  |  |  | Topics |  |  |  | Discussion Leader |  |  |  |
| Plan | Start |  | Stop |  |  |  |  |  |  |  |  |  |
| 10 |  |  |  |  | Agenda and meeting process |  |  |  | TSP Coach |  |  |  |
| 45 |  |  |  |  | Review management's goals |  |  |  | Team Leader |  |  |  |
| 45 |  |  |  |  | Define implied goals |  |  |  | Team Leader |  |  |  |
| 60 |  |  |  |  | Establish team goals |  |  |  | Team Leader |  |  |  |
| 50 |  |  |  |  | Select team roles |  |  |  | TSP Coach |  |  |  |
| 25 |  |  |  |  | Assign goal tracking responsibility |  |  |  | Team Leader |  |  |  |
| 5 |  |  |  |  | Meeting wrap-up and report |  |  |  | TSP Coach |  |  |  |
| Decisions, Actions, and Key Information |  |  |  |  |  |  |  |  |  |  |  |  |
| What |  |  |  |  |  |  |  | Who |  |  |  | When |
| Attachments: form GOALS and form ROLE |  |  |  |  |  |  |  | Recorder |  |  |  |  |

(Use additional form copies if needed.)

| TSP Launch Meeting 2 - Script LAU2 |  |
| --- | --- |
| Purpose | To guide the team in setting goals and establishing roles |
| Entry Criteria | - All participants are present (TSP coach, team members, team leader). - Forms: GOAL, ITL, MTG, PIP, ROLE, ROLEMX |
| General | Meeting 2 generally takes 3 to 5 hours. |

| Step | Activities | Description |
| --- | --- | --- |
| 1 | Meeting Roles | Select the meeting roles (specification ROLE). - The TSP coach leads the meeting (script MTG). - The timekeeper tracks time and keeps the meeting on schedule. - The recorder notes meeting decisions and actions and writes the meeting report (form MTG). |
| 2 | Meeting Overview | The TSP coach reviews the work to be done in this meeting and the products to be produced. |
| 3 | Review Management's Stated Goals | The team leader leads the team in reviewing management's goals to - get agreement on what management stated as the goals - identify one or more measure for the key management goals - record results on form GOAL |
| 4 | Implied Goals | The team leader leads the team in defining the goals that are implied by management's stated goals. Considerations include customer satisfaction, financial performance, and competitive capability. |
| 5 | Team Goals | The team leader leads the team in - establishing team goals to meet management's stated and implied goals - defining product, process, quality, and project goals - identifying one or more measures for each key team goal - record results on form GOAL |
| 6 | Team Role Selection | The team uses the procedure given with form ROLEMX to - review the team roles - allocate the roles among the team members - identify an alternate for each role - document the role assignments (form ROLE) - Note that the team leader generally is not assigned any of the TSP team roles. |
| 7 | Goal Tracking | The team leader leads the team in - assigning team-member tracking responsibility for each goal - recording the assignments on form GOAL - establishing a tracking schedule for each goal - Note that role assignments may determine goal-tracking responsibility. |
| 8 | Launch Meeting Documentation | The recorder completes form MTG. - lists the attendees and the time spent by agenda item - describes decisions made and by whom - documents pending actions: what, when, and by whom - verifies the meeting report with the meeting attendees and gives the completed form MTG to the planning manager. |

| Exit Criteria | - Launch meeting 2 activities have been completed. - Team roles and alternates are documented (form ROLE). - Project goals are documented (form GOAL). - All issues have been recorded (form ITL). - All process improvement suggestions have been recorded (form PIP). - The meeting report has been completed (form MTG and attachments). - The planning manager has copies of all meeting products. |
| --- | --- |

TSP Team Role Assignments - Form ROLE

| Name |  | Date |  |
| --- | --- | --- | --- |
| Project |  | Launch/Phase |  |

| Team Member Roles |  | Requirements | Design | Implementation | Integration and Test |
| --- | --- | --- | --- | --- | --- |
| Official Team Leader | P |  |  |  |  |
|  | A |  |  |  |  |
| Customer Interface | P |  |  |  |  |
| Manager | A |  |  |  |  |
| Design Manager | P |  |  |  |  |
|  | A |  |  |  |  |
| Implementation | P |  |  |  |  |
| Manager | A |  |  |  |  |
| Planning Manager | P |  |  |  |  |
|  | A |  |  |  |  |
| Process Manager | P |  |  |  |  |
|  | A |  |  |  |  |
| Quality Manager | P |  |  |  |  |
|  | A |  |  |  |  |
| Support Manager | P |  |  |  |  |
|  | A |  |  |  |  |
| Test Manager | P |  |  |  |  |
|  | A |  |  |  |  |
|  | P |  |  |  |  |
|  | A |  |  |  |  |
|  | P |  |  |  |  |
|  | A |  |  |  |  |
|  | P |  |  |  |  |
|  | A |  |  |  |  |
|  | P |  |  |  |  |
|  | A |  |  |  |  |
|  | P |  |  |  |  |
|  | A |  |  |  |  |
|  | P |  |  |  |  |
|  | A |  |  |  |  |
|  | P |  |  |  |  |
|  | A |  |  |  |  |
|  | P |  |  |  |  |
|  | A |  |  |  |  |
|  | P | Principal responsibility for the role |  |  |  |
|  | A | Alternate responsibility for the role |  |  |  |

TSP Team Role Assignments Instructions - Form ROLE

| Purpose | This form holds data on the team role assignments. |
| --- | --- |
| General | - Make team role assignments during launch and relaunch. - Enter the names of those assigned the principal and alternate responsibilities for each role. - Every team member should have at least one principal or alternate team role. - Update the form during relaunch or when roles change. - Use form ROLEMX if necessary to help make role selections. - See ROLE specification for the role responsibilities. - This form is used only when a tool with equivalent functionality, features, or purpose is not available. |
| Header | Enter your name, project name, launch phase, and date. |
| Team Member Roles | List any other role assignments at the bottom of the form. |
| Team Leader | - The team leader - serves as the project and team manager - obtains project staffing, makes job assignments, approves plans, reports status, and arranges for needed support - leads the launch and relaunch meetings - supports and guides the team members in doing their jobs - usually has no other team role. |
| Customer Interface Manager | - The customer interface manager - manages requirements issues and changes - ensures that all requirements assumptions are verified - leads usability, installation, documentation, and training plans |
| Design Manager | - The design manager - leads the design work and controls design changes - sets the design standards and specifications |
| Implementation Manager | - The implementation manager - leads the implementation work - sets the implementation, size, and performance standards |
| Planning Manager | - The planning manager - guides estimating, planning, tracking, and risk management - establishes the standard planning framework used for developing the team and personal plans - consolidates the team members' plans into the overall team plan |
| Process Manager | - The process manager - leads the process and procedure definition work - manages the PIP process - owns and maintains the team processes |
| Quality Manager | - The quality manager - develops and tracks the quality plan and analyzes quality data - moderates team inspections or obtains a moderator - alerts the team and management to likely quality problems |
| Support Manager | - The support manager - establishes the development system - operates the configuration management, change management, and issue tracking systems |
| Test Manager | - The test manager - ensures that testing issues are considered in every phase - leads test planning, measuring, tracking, and management |
| Team Member | All team members do design, implementation, and testing work and support other team members as needed. |

TSP Role Assignment Matrix - Form ROLEMX

| Name |  | Date |  |
| --- | --- | --- | --- |
| Project |  | Launch/Phase |  |

| Team Member Roles Team Members | Customer Interface Manager | Design Manager | Implementation Manager | Planning Manager | Process Manager | Quality Manager | Support Manager | Test Manager |  |  |  |  |  |  |  |  |
| --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- |

TSP Role Assignment Matrix Instructions - Form ROLEMX

| Purpose | This form is used by the team to select team role assignments. |
| --- | --- |
| General | - Make team role assignments during launch and relaunch. - Record the names of those assigned the principal and alternate responsibilities for each role in form ROLE. - Every team member should have at least one principal or alternate team role. - See ROLE specification for the role responsibilities. - This form is used only when a tool with equivalent functionality, features, or purpose is not available. |
| Header | Enter your name, project name, launch phase, and date. |
| Team Member Roles | - The standard TSP role assignments are listed across the top of the form. - List any other role assignments in the blank spaces at the right of the form. |
| Team Leader | - The project leader or team manager is typically designated by management before the project starts. - The team leader usually has no other team role. |
| Team Members | List the team members in the left-hand column of the form. |
| Initial Role Selection | - Have each team member identify the two roles he or she would prefer to have. - Label these roles with 1 or 2 for the first or second choice. - For small teams, make a larger number of initial selections. |
| Initial Role Entry | For each team member, mark a 1 or 2 by the two roles selected by that team member (or 3, etc. for smaller teams). |
| Unique Role Identification | - Where a team member is the only one to select a role, that team member gets that assignment. - Where a team member has two or more unique roles, he or she may choose which one to take. |
| Choice Elimination | - When a team member's role has been selected, cross off all other choices for that team member. Also cross off all selected roles. - Next, note which team members now have unique roles selected and make appropriate assignments. - Continue this process until either all roles have been selected or no unique choices remains. |
| Duplicate Role Choices | - Where two or more team members select the same roles, they decide with the team's assistance which will have the role. - Where they cannot agree, the team leader, with the team's assistance, makes the final selection. |
| Unselected Roles | Similarly, where no roles have been selected, volunteers are requested from those team members with no or the fewest roles. |
| Alternate Roles | - After the roles have been selected, select an alternate for each role. - The role alternate backs up the role manager when needed. - Be guided by the team members' preferences in assigning the alternate roles. |

TSP Team Goals - Form GOAL

| Name |  | Date |  |  |  |  |  |
| --- | --- | --- | --- | --- | --- | --- | --- |
| Project |  | Launch/Phase |  |  |  |  |  |
|  |  |  |  | Measures |  |  | Tracking |
| Goal |  |  |  | Goal |  | Actual | Responsibility |

TSP Team Goals Instructions - Form GOAL

| Purpose | Use this form to record the team's goals. |
| --- | --- |
| General | This form is used only when a tool with equivalent functionality, features, or purpose is not available. |
| Goal-setting Process | In establishing goals, follow these guidelines. - Start with management's and marketing’s or customer’s stated goals. - Identify implied goals. - Define the team goals required to meet stated and implied goals. |
| Implied Goals | Some goals seem too obvious to state. Examples include: - Produce a product that works reliably and consistently. - Provide a product that is safe, does not damage people or property, and is protected against anticipated failures. - Respond to customer requests with sufficient reports and information to keep them satisfied with the team's work. |
| Team Goals | In establishing goals, examine each stated and implied goal and ask what would have to happen for this result to be assured. - What must the team do to assure that this goal is met? - Define team goals that require that these actions be taken. |
| Example Team Goals | - Provide a highly usable and convenient system. - Deliver the product on time and at planned costs. - Produce a defect-free product. - Reduce development cycle time. - Keep management and the customer fully informed of project status. |
| Measures: Goal | Try to define one or more measurements for every goal. - Sometimes, the goal will be readily measurable. - Often, indirect or opinion measures will be needed. - For every goal, specify how to determine if it was met. |
| Example Measures | Possible measures for the above example goals include, - Establish user performance targets and run usability tests to measure the performance and reaction of typical users. - Measure cost and schedule performance against the plan. - Set percent defect free (PDF) targets and track through development, test, acceptance, and use. - Measure how often specific managers must ask about project status rather than being informed in advance. |
| Measures: Actual | At project completion or whenever the data are available, measure and enter actual performance against each goal. |
| Responsibility | - Name the team member or role manager responsible for tracking and reporting on each goal. - In the weekly meeting, report status against all goals as soon as performance measures are available. |

TSP Issue and Risk Tracking Log - Form ITL

| Name |  | Date |  |
| --- | --- | --- | --- |
| Project |  | Launch/Phase |  |

| No. | Date |  | Personal/Team | Risk/Issue | Impact | Likelihood | Source | Owner |
| --- | --- | --- | --- | --- | --- | --- | --- | --- |
| Description |  |  |  |  |  |  |  | Follow-up Date |
|  |  |  |  |  |  |  |  | Resolved Date |
| No. | Date |  | Personal/Team | Risk/Issue | Impact | Likelihood | Source | Owner |
| Description |  |  |  |  |  |  |  | Follow-up Date |
|  |  |  |  |  |  |  |  | Resolved Date |
| No. | Date |  | Personal/Team | Risk/Issue | Impact | Likelihood | Source | Owner |
| Description |  |  |  |  |  |  |  | Follow-up Date |
|  |  |  |  |  |  |  |  | Resolved Date |
| No. | Date |  | Personal/Team | Risk/Issue | Impact | Likelihood | Source | Owner |
| Description |  |  |  |  |  |  |  | Follow-up Date |
|  |  |  |  |  |  |  |  | Resolved Date |
| No. | Date |  | Personal/Team | Risk/Issue | Impact | Likelihood | Source | Owner |
| Description |  |  |  |  |  |  |  | Follow-up Date |
|  |  |  |  |  |  |  |  | Resolved Date |
| No. | Date |  | Personal/Team | Risk/Issue | Impact | Likelihood | Source | Owner |
| Description |  |  |  |  |  |  |  | Follow-up Date |
|  |  |  |  |  |  |  |  | Resolved Date |
| No. | Date |  | Personal/Team | Risk/Issue | Impact | Likelihood | Source | Owner |
| Description |  |  |  |  |  |  |  | Follow-up Date |
|  |  |  |  |  |  |  |  | Resolved Date |

TSP Process Improvement Proposal - Form PIP

| Name |  |  | Date |  |  |
| --- | --- | --- | --- | --- | --- |
| E-mail |  | Organization |  |  |  |
| Project |  | Launch/Phase |  |  |  |

| PIP Number |  |  | Priority |  |  |  |  |
| --- | --- | --- | --- | --- | --- | --- | --- |
| PIP Title |  |  |  |  |  |  |  |
| Improvement Description |  |  |  |  |  |  |  |
| Briefly describe the improvement you suggest. |  |  |  |  |  |  |  |
| Process Elements Impacted |  |  |  |  |  |  |  |
| If you know them, list the process elements that must be added, changed, or deleted. |  |  |  |  |  |  |  |
| Improvement Benefits (check one) |  |  |  |  |  |  |  |
| Improved Quality _______ Reduced Cycle Time ________ Reduced Risk ________ |  |  |  |  |  |  |  |
| Describe the likely benefits of the suggested change. |  |  |  |  |  |  |  |
| When completed and reviewed, submit to the Process Manager and keep a copy. |  |  |  |  |  |  |  |
| Do not write below this line. |  |  |  |  |  |  |  |
| PIP Control No. |  |  |  | Accepted |  |  |  |
| Received |  |  |  | Returned |  |  |  |
| Evaluated |  |  |  | Deferred |  |  |  |
| Effort Involved |  |  |  | Date Done |  |  |  |
| Author Notified |  |  |  |  |  |  |  |
| Reasons |  |  |  |  |  |  |  |