## Slide 1
Implementing Goal-Driven Measurement
Decision Making With Software Measurements
Notes: KEY POINTS
Make yourself an “educated consumer of measurement data”
SUGGESTED SCRIPT
In this module we are going to discuss how to make sure your measurements support effective decision making.

## Slide 2: Module Objectives
Provide some examples of how you can misinterpret graphs and charts
Questions to ask to make sure you have the facts to interpret the plotted results correctly
Make you a more educated consumer of measurement data
At the end of the module, the student will be able to:
  evaluate facts and context to ensure correct interpretation of the plotted results
Notes: INSTRUCTORS NOTES
KEY POINTS
  Make you an “educated consumer of measurement data”
SUGGEST SCRIPT
  To see how others have used graphs and charts based on software measures as indicators to guide management action
  Questions to ask to make sure you have the facts to interpret the plotted results correctly
  Better consumer of measurement data.

## Slide 3: Suppose You Receive This Report…
...
Schedule 90% complete
Total problems reported: 2,135
Current size: 317,300 lines of code
Staff-hours expended: 77,700
...
Integrated Logistics Software:
Development Status Report—August 2003
What questions might you have?
Notes: KEY POINTS
What do these numbers mean? => Nothing since you do not know what was counted, when, etc.
SUGGESTED SCRIPT
This is a part of a typical status report. It addresses schedule, quality, size, and effort expended.
    [Ask the class if they see any problems with the report.]
    [Go down each item and ask what is wrong with what is presented; what additional information is required to fully understand the status of this area?]
      - Schedule: What is the definition of complete? How does this compare to planned value? Etc.
      - Problems: What does “reported” mean? How many are open still, what type, priority; compared to estimate, etc.
      - Size: What is included in this size number? What was counted, new & modified code? Compared to estimated value, etc.
      - Staff-hours: Whose hours were counted? For what time frame? Does it include overtime? Compared to planned value? Etc.
  Need a large amount of additional information to make this report useful.

## Slide 4: Is There a Cause for Concern Here?
Will the budget be overrun? Will the software be late?
SLOC (Added and Modified)
0
10k
20k
30k
40k
50k
60k
70k
80k
90k
Jul
Aug
Sep
Oct
Nov
Dec
Actual
Plan 1
Plan 0
Notes: KEY POINTS
Should you be concerned?
SUGGESTED SCRIPT
This chart has plots of added and modified SLOC over time. The green line is a size estimate for the original plan. This plan was modified based on additional information and the new size estimate is shown in blue. The red line is the actual size.
[Ask the questions to the class:
    Are we in trouble? (Should I start ordering Maalox by the truck load?)
    What action should we take?]
TRANSITION
  [Let the class discuss this for a while.]
  The next slide will provide you some more information

## Slide 5: How About Now?
What went wrong?
0
20k
40k
60k
80k
100k
120k
Jul
Aug
Sep
Oct
Nov
Dec
Actual
Plan 1
Plan 0
SLOC (Added and Modified)
CDR
Integration
& Testing
Notes: KEY POINTS
Should you be really be concerned now?
SUGGESTED SCRIPT
One months of additional data is plotted here
    Ask the question “Should I really panic now?”
    Provide hint: integration and testing start time
  Explanation
    Program written in Fortran. Used COMMON block to communicate between modules.
    During Integration, incorporated completed modules or subroutines.
    As new modules were integrated, any new variables used to communicate between the modules were added at the FRONT of the COMMON block.
    Used a program called DIFF to obtain the new and modified code. Since the new variables were added at the front of the COMMON block, all items after the one that was just added was counted as NEW. Hence the spike was due to how it was counted.
    Lesson learned: to understand what the display is telling you, you need to also know how these numbers were obtained.

## Slide 6: Are We Ready to Ship?
Weeks After System Test Start
Defects Discovered
Would you consider shipping at week 20?
Notes: KEY POINTS
Erroneous plot
SUGGESTED SCRIPT
Boss wants to know when he can ship the product. The boss constructed this chart from your status reports.
  Boss want to ship as soon as possible. Based on the current rate of discovery and being conservative, he wants to ship on week 20.
  [Ask class if OK. If not, ask “why not?”]
  Typical questions:
  Not enough data to make the decision
  How many are still open? Any priority 1’s open?

## Slide 7: But How Many Were Resolved?
Weeks After System Test Start
Defects Resolved
Defects Discovered
Now would you consider releasing at week 20?
Notes: KEY POINTS
Additional information, but still not sufficient.
SUGGESTED SCRIPT
Added curve for “how many were resolved.”
  The number of defects resolved is going up, the defects discovered is going down.
  So why can’t I ship at week 20?
  To ease your discomfort, I’ll give you two extra weeks => let’s ship on week 22
  (Extra information: resolved could be fixed or deferred.)

## Slide 8: If You Don’t Look, You Won’t Find Any
Weeks After System Test Start
Defects Resolved
Defects Discovered
Notes: KEY POINTS
If you don’t look, you won’t find any.
SUGGESTED SCRIPT
  Since they had so many defects, the entire team was allocated to fixing the known defects.
  Hence the steep rise of defects resolved.
  After the team got down to a more reasonable number, they split the team again.
  After splitting the team to test again, new defects are cropping up.
  The bottom line: if you don’t look, you won’t find any.

## Slide 9: Estimated Delivery Time?
Designed
Coded
Integrated
Plan
Actual
Notes: KEY POINTS
Estimate for obtaining the date for start of integration.
SUGGESTED SCRIPT
Your boss is “leaning” on you for a date for the start of integration. Based on the data in the slide, what date can you give him?
  Y-axis has the number of units completed
  X-axis is reporting period, time in months
  Plotted are the planned and actual completions for design, coded, and integration
  [Ask the class for their suggestion.]
  A non-precise way but better then a complete guess.
    Notice the relationship between the planned and actual curves for design. After following behind in completion, the actual curve runs parallel to the planned curve.
    We can mimic the same type of behavior for the actual coded line. Let’s extend the “actual coded” line parallel to the planned line. This provides an estimate for start of integration around month 11.

## Slide 10: Are We On Schedule? Which Schedule?
SDP = Software Development Plan
PDR = Preliminary Design Review
CDR = Critical Design Review
Notes: KEY POINTS
Importance of keeping track of all the replans
SUGGESTED SCRIPT
  Y-axis is the number of units coded and unit tested
  X-axis is time in months
  Plotted are estimates made for the number of units coded and unit tested
    at contract award
    after some additional information was available during the development of the software development plan (SDP)
    Some more information was available at the preliminary design review (PDR)
    And more information was available during the critical design review (CDR)
  The actual completion of units coded and units tested is shown in red
  [Ask the question of the class: why keep all these plans?]
Impact of these changes: The hardware was patched together to meet the completion of the software based on the contract award plan. The software completion was following all these re-plans without communicating these changes to the hardware team. Hence the aircraft sat on the tarmac many months waiting for the completion of the software.
It is important to keep track of all the re-plans.

## Slide 11: What Types of Problems Are My Customers Having?
Documentation defect
Enhancement request
Software failures
Cause unknown
User mistake
Operational mistake
Hardware failure
1
2
3
4
5
6
7
8
9
10
11
12
13
14
15
16
17
18
0
20
40
60
80
100
120
Months After Product Release
Number of Unique Problems
Why collect this type of data?
Notes: KEY POINTS
Use of defect data
SUGGESTED SCRIPT
Plotted here are the number of unique problems, by type, for months after product release.
[Ask the class “why collect this type of data?” and “What use can I make of this type of data?”]
  Notice the large number of user mistakes, enhancements, and unknown causes
  Is there something in the software and/or documentation that causes the user to make all these mistakes? Are the enhancement requests suggestions on correcting these user errors?
  Charts like these would help me to focus my analysis efforts.

## Slide 12: Which Customers Are Having the Most Problems?
1
2
3
4
5
6
7
8
9
10
0
2
4
6
8
10
12
14
16
18
20
0
2
4
6
8
10
12
14
16
18
20
Rolling three
month totals
Customer ID
Number
of Unique
Problems
Notes: KEY POINTS
Use of defect data
SUGGESTED SCRIPT
Background
    The same system was installed at 10 user sites.
    Plotted here is the rolling three month total number of unique problems for the 10 customer sites.
  [Ask the class: if you were the project manager for this deployed system, would this type of chart be of interest? Why or why not?]
  Questions on areas of interest
    Why have sites 4 & 7 experienced so many problems? (Could have large number of users.)
    Why have site 6 & 10 so few problems? (Could have very few users, or got disgusted with the defects experienced initially and quit using the software, etc.)

## Slide 13: Productivity (Example)
Size (KSLOC)
Effort (staff-hours)
completed project
Notes: KEY POINTS
Use of defect data for estimation
SUGGESTED SCRIPT
Plotted here is the effort in staff-hours and size in KSLOC for completed projects. Also the dotted line is a regression line of the data.
[Ask the class: would this be a useful chart to construct? How would I use this information?]
Possible uses
    Estimation: Since this chart plots projects that were completed using the organization’s staff, processes, etc, we can obtain an estimate of the amount of effort required for a project for which we have a size estimate.
    Use of outliers:
      Investigate the completed project whose size was 400K SLOC and used very little effort. Questions to ask: What was unique about this project? Did they modify some standard processes that enabled them to obtain enhanced productivity? Did they do anything (techniques, processes, etc.) that can be transferred to the entire company?
      Investigate the completed project whose size is 100 KSLOC. Questions to ask: why the large amount of effort for so little code?

## Slide 14: Are Our Requirements Under Control?
Number of
Requirements
or
Features
Total
Requirements
Time
Milestones
Baseline
(Weeks, months, quarters, etc.)
Notes: KEY POINTS
Need to understand what is behind these numbers
SUGGESTED SCRIPT
Background
    Plotted here are the total number of requirements over time.
    A number of organizations that we have worked with just keep track of the total requirements.
    Looking at this graph, the total looks relatively constant after the initial changes.
  [Ask class: If you were the project manager of this project, does this chart convince you that your requirements were under control? Why or Why not?]

## Slide 15: Requirements Volatility
New
Mod
Del
New
New
Mod
Mod
Del
Init
Number of
Requirements
or
Features
Total
Requirements
Time
NEW
DEL
Milestones
Baseline
(Weeks, months, quarters, etc.)
MOD
Notes: KEY POINTS
Need to understand what is behind these numbers
SUGGESTED SCRIPT
This chart has plotted some additional information
    The number of new, modified, and deleted requirements that were added.
  Even though the total requirements look relatively stable, having this additional information changes the picture considerably.
  [Ask the class: if the first milestone was the beginning of coding, what could be the impact of adding additional requirements?]
    Increased cost and slipped delivery date due to the ripple effect of the redesign and recode of modules.
    The nice structured code is at risk since we may not have the time to redesign and recode all of the completed modules. The implementation of the new requirements may/will look like a patch.

## Slide 16: Have We Met Our Goal?
Goal: Each successive version should be of a higher quality than the previous version.
Defects
per
KSLOC
0.00
0.40
0.80
1.20
1.60
2.00
Version 1.0
Version 1.1
Version 1.2
Months after Product Release
16
18
14
12
10
8
6
4
2
0
Notes: KEY POINTS
Have we met our goal?
SUGGESTED SCRIPT
Background
    The goal for a specific company was that “each successive version should be of a higher quality than the previous version.”
    The project manager for this project used this chart to try to convince his boss that he had met the companies goal for the defect density as lower than the previous version.
    The defect density (defects per KSLOC) was plotted over time for version 1.0, 1.1, 1.2.
    If you were the BOSS, would you give the manager his bonus? Why or Why not?

## Slide 17: Additional Information
Ver 1.0
Ver 1.1
Ver 1.2
KSLOC
KSLOC
KSLOC
30
2.5
1.5
0
30
32.5
30
32.5
34
New
Old
Total
Defects
per
KSLOC
0.00
0.20
0.40
0.60
0.80
1.00
1.20
1.40
1.60
1.80
2.00
Version 1.0
Version 1.1
Version 1.2
Months after Product Release
16
18
14
12
10
8
6
4
2
0
What is your decision now?
Notes: KEY POINTS
Have we met our goal?
SUGGESTED SCRIPT
Here is some additional information
    Version 1.0 had 30 KSLOC of new code
    Version 1.2 added 2.5 KSLOC of new code to the 30 KSLOC of existing code in version 1.0 for a total size of 32.5 KSLOC
    Version 1.3 added 1.5 KSLOC of new code to the 32.5 KSLOC of version 1.1 for a total size of 34 KSLOC
  Now would you give the project manager his bonus since he has met the company goal of “each successive version should be of a higher quality than the previous version.”
  If not, why not?

## Slide 18: Using New & Modified KSLOC
Have we met our goal of higher quality for each successive version?
How can we be sure we interpret these displays correctly?
0
5
10
15
20
25
Version 1.0
Version 1.1
Version 1.2
Months after Product Release
18
14
12
10
8
6
4
2
0
16
Defects
per
KSLOC
New &
Modified
Code
Notes: KEY POINTS
Just use the new and modified KSLOC for the calculation
SUGGESTED SCRIPT
  Remember, plotted on the Y-axis is defects per KSLOC.
  Using the total code, the denominator is getting bigger and bigger.
    The amount of existing (debugged) code total washes out the amount of new code.
  To find out how “good” the new and modified code is, we will use the amount of new and modified code in the denominator.
    The picture changes entirely.
    The original code was excellent compared to the number of defects in the new and modified code in versions 1.1 and 1.2.
  NO bonus for the project manager!
  To interpret a chart correctly, you really need to understand the details behind the chart.

## Slide 19: What Were Some of the Questions We Just Addressed?
  Are we progressing according to plan?
  Will the budget be overrun?
  Will the software be late?
  When will we be ready to ship?
  Are we on schedule? Which schedule?
  Which customers are having the most problems?
  Have we met our goal?
To interpret each chart, we had to understand the context.
Notes: KEY POINTS
To understand or interpret each chart correctly, we needed to understand the details behind the chart.
SUGGESTED SCRIPT
The preceding charts addressed these questions.
To understand or interpret each chart correctly we needed to understand the details and the context behind the chart!

## Slide 20: Knowledge for Action
Valid Information What’s the source of the data? Has the process for collecting or reporting changed? What’s different this time?
Actionable Choices What’s the significance of the information? Does it represent a risk or problem? Is a decision required?
Follow-Through What will you monitor after the action? How often? Can you get the monitoring data you need? Who is responsible?
Notes: KEY POINTS
For each chart, think about the validity of the information, what the actionable choices are, and what the follow-through is based on this information.
SUGGESTED SCRIPT
Here is some advice to take home with you. Whenever you get presented with a chart, indicator, or graph, think about these issues:
  Is this chart based on valid Information?
    Type of questions to ask:
      What’s the source of the data?
      Has the process for collecting or reporting changed?
      What’s different this time?
  What are the actionable choices?
    Type of questions to ask:
      What is the significance of the information?
      Does it represent a risk or problem?
      Is a decision required?
  Follow-Through
    Type of questions to ask:
      What will you monitor after the action? How often?
      Can you get the monitoring data you need?
      Who is responsible?

## Slide 21: Summary
Make sure you have the facts to interpret the plotted results correctly.
Formalize your measurement definitions, so that they can be employed consistently.
Tailor your indicators to your measurement goals, questions, and software process.
Define the information you need before you collect the data.
Notes: KEY POINTS
Take-home suggestions
SUGGESTED SCRIPT
Some take home suggestion on indicators:
  Tailor your indicators to your measurement goals, questions, and software processes.
  Define the information you need before you collect the data.
  Make sure you have the facts to interpret the plotted results correctly.
  Formalize your measurement definitions so they can be employed consistently.