## Slide 1: Personal Software ProcessSM for Engineers: Part II
Workshop: Assignment 9F

## Slide 2: Document Markings
Copyright 2020 Carnegie Mellon University. All rights reserved. This material is based upon work funded and supported by the Department of Defense under Contract No. FA8721-05-C-0003 with Carnegie Mellon University for the operation of the Software Engineering Institute, a federally funded research and development center. Any opinions, findings and conclusions or recommendations expressed in this material are those of the author(s) and do not necessarily reflect the views of the United States Department of Defense. NO WARRANTY. THIS MATERIAL IS FURNISHED ON AN “AS-IS” BASIS WITH NO WARRANTIES OF ANY KIND, EITHER EXPRESSED OR IMPLIED, INCLUDING, BUT NOT LIMITED TO, WARRANTY OF FITNESS FOR PURPOSE OR MERCHANTABILITY, ANY WARRANTY WITH RESPECT TO FREEDOM FROM PATENT, TRADEMARK, OR COPYRIGHT INFRINGEMENT, OR THIRD PARTY INTELLECTUAL PROPERTY RIGHTS. [Distribution Statement A] This material has been approved for public release and unlimited distribution. The United States Government has Unlimited Rights in this material as defined by DFARS 252.227-7013.
The text and illustrations in this material are licensed by Carnegie Mellon University under a Creative Commons Attribution 4.0 International License.
The Creative Commons license does not extend to logos, trade marks, or service marks of Carnegie Mellon University.

## Slide 3: Workshop Objectives
After this workshop, you will
  understand Program 9F requirements
  have completed Program 9F planning
    conceptual design
    size estimate
    resource estimate
    defect estimate

## Slide 4: Program 9F Requirements -1
Use PSP2.1 to extend Program 6F to
  complete the Actual portion of the task and schedule planning templates
  estimate the project completion day
Your program should use the following as input:
  plan hours per day (assume the same number of hours are available each day)
  a task list (assume that tasks are provided in the order in which they are planned to be completed)
  the actual hours worked per day through the current day
  a list of completed tasks, including the day each task was completed
Thoroughly test the program. At a minimum, test your program with the following three test cases.

## Slide 5: Test Case 1
Use the data below as input for Test Case 1.
On-task hours per day = 3.5

## Slide 6: Test Case 1 – Expected Results
For Test Case 1, your program should produce the results below in a similar format.
Estimated day of project completion = Day 7

## Slide 7: Test Case 2
Use the data below as input for Test Case 2.
On-task hours per day = 4

## Slide 8: Test Case 2 – Expected Results
For Test Case 2, your program should produce the results below in a similar format.
Estimated day of project completion = Day 8

## Slide 9: Test Case 3
Use the data below as input for Test Case 3.
On-task hours per day = 5

## Slide 10: Test Case 3 – Expected Results
For Test Case 3, your program should produce the results below in a similar format.
Estimated day of project completion = Day 14

## Slide 11: Tracking the Plan
As each task is completed, it earns the planned value. On the task template,
  enter the earned value (EV) for that task
  enter the day of task completion
  add the EV to date in the Cumulative EV column
In the schedule template, enter the cumulative EV for each day as it is completed.
Track earned value versus planned value by day.

## Slide 12: Projecting Project Completion
Assume that the project will continue to earn value at the rate it has in the past.
Calculate Average EV per day = Cumulative EV/Number of Elapsed Days (where the number of elapsed days is the number of days for which actual time data has been provided)
Extrapolate to project completion by linearly extending the EV line until it reaches 100%.
Remaining EV = 100 – Cumulative EV
Days to project completion = Remaining EV/Average EV per day (rounded up to the next day)

## Slide 13: Assignment Instructions -1
Using the PSP2.1 process, complete the planning phase for Assignment 9F.
When you have finished planning, review your work with the instructor.
After your plan has been reviewed, complete the assignment using PSP2.1.

## Slide 14: Assignment Instructions
  PSP2.1 project plan summary
  test report
  design review checklist
  code review checklist
  PIP form
  size estimating template
  PROBE worksheet
  operational scenario template
  functional specification template
  state specification template
  logic specification template
  time recording log
  defect recording log
  source program listing
  test results
  LOC report
When you have completed the postmortem phase, submit your assignment package, source code, and test results to the instructor in the following order (NO STAPLES):

## Slide 15: PSP2.1 Evaluation Criteria
Your process report must be
  complete
  legible
  in the specified order
Your process data, including size calculations, must be
  accurate
  precise
  self-consistent

## Slide 16: General Guidelines -1
Keep your programs simple. You will learn as much from small programs as from large ones.
Keep your reports and standards simple and short.
Do not hesitate to copy or build on the PSP materials.
Do it right the first time. If you are not sure, find out.

## Slide 17: General Guidelines -2
Software is not a solo business, so you do not have to work alone. However, you must produce your own estimates, designs, and code.
You may have others review your work, and you may change it as a result.
You should note any help in your process report. Include the review time that you and your associates spent, and log the defects found.