Analysis 1, Cost Schedule Case

Baseline Exercise

Instructions, from lecture slides

In groups of 4  (15 min)

  - Create your plan for baselining the data.

  - List specific charts and analyses. (Ask for help if you need it.)

Individually  (30 min)

  - Create your charts and statistics.

Return to your group  (30 min)

  - What are your interpretations, conclusions?

    - Where is the priority for your attention? What would you do next?

Debrief (30 min)

  - Each group reports results (5 min/group)

    - Use questions listed on next slide.

  - Class discussion

  - Does this case study situation reflect any of your organization’s reality?

    - Record actionable ideas on your “real life project” form.

Data Files:

  - A1C3E1-2_Baseline-Explore-MonthlyData.MTW

  - A1C3E1_Baseline-CompletedProjects.MTW

Additional guidance

(information about data files and corresponding analysis tips are on the following pages)

When developing your plan for baselining the data, consider these questions

- What is your strategy? What are your tasks?

- What roadmap questions are relevant?

- What statistics and charts will you create?

- Do you need to manipulate the data to create the desired charts? Or, does the file contain the data in the format that you need?

- Who will create which charts?

- Who will be the group spokesperson?

The specification for cost and schedule is +/- 20%

Note: There can be overlap between baselining and exploratory analysis. If the data segmentations are obvious and the purpose is to snapshot the performance, it’s more like baselining. If you’re on an educated fishing expedition, that’s more like exploratory analysis.

Monthly Data:   A1C3E1-2_Baseline-Explore-MonthlyData.MTW

This data set is a portion of the overall data set used in this case study.

The fieldnames in bold are the primary focus for the exercise.     Consider the following analyses:

- Descriptive statistics

- Trends over time

  - Don’t forget to sort the data by time first!

- Distributions

- Boxplots

- SPC charts (in “diagnostic mode”)

  - If you look at SPC charts, would you use x-mr or xbar-r?   If you use x-mr, how will you order the projects within each given month?

If time

- For extreme values, check whether they are all from the same project(s) or not.  What would you need to know before you removed them from the data set.

- Replot your data without the extreme values.  How much affect did they have on your results?

| Fieldname | Additional Explanation | Comments |
| --- | --- | --- |
| month# - date | Date, prefixed by sequential month number (1=october, 2=november, etc) | Prefix allows charting in time sequence. (How would you create this column from the raw data, which contained only date) |
| date |  |  |
| Org unit | Identifies which organizational unit the project is from |  |
| project id |  |  |
| Size (BAC) | The total staff hours budgeted to accomplish a work package or cost account. |  |
| BCWS | The percentage of a cost account’s Budget at Completion (BAC) that was scheduled to be completed on a particular date. BCWS cannot be calculated until after BAC has been determined and all work packages have been scheduled. | “budgeted cost for work scheduled” |
| BCWP | The amount of the Budget at Completion (BAC) that has been accomplished to date, based on the completion criteria and earned value (EV) method selected for the work package. (When a work package is completed, no matter how long it took to meet the completion criteria, BCWP=BAC.) | “budgeted cost for work performed” |
| ACWP | The actual manhours expended while working on a cost account. | “actual cost of work performed” |
| %sch var | ((BCWP – BCWS) / BCWS) * 100 |  |
| % cost var | ((BCWP – ACWP) / BCWP) * 100 |  |

Complete Project Data:  A1C3E1_Baseline-CompletedProjects.MTW

This data set is a portion of the overall data set used in this case study.

The fieldnames in bold are the primary focus for the exercise.     Consider the following analyses:

- Descriptive statistics for both the absolute and percent data  (why should you look at both?)

- Trends over time

- Distributions

| Fieldname | Additional Explanation | comments |
| --- | --- | --- |
| org unit | Identifies which organizational unit the project is from |  |
| project ID | Project index, 1 to 42 |  |
| domain | Type of projects 1 & 2 are mostly development 3 is mostly maintenance |  |
| resources | Organic = no contracting Hybrid = some work contracted |  |
| priority |  |  |
| size | Project size based on estimate |  |
| initial effort hrs |  |  |
| initial cost |  |  |
| planned finish date |  |  |
| planned start date |  |  |
| actual effort |  |  |
| actual cost |  |  |
| actual finish date |  |  |
| actual start date |  |  |
| start date - pre/post assessment | Did the project start prior to the last assessment? | This was flagged because there were process changes resulting from the last assessment that might affect performance |
| effort variance | Initial estimated effort – actual final effort |  |
| cost variance | Initial estimated cost – actual final cost, including hardware other purchases | For projects with no capital expenditures, cost tracks effort |
| sched variance | Planned finish date – actual finish date, in days |  |
| total rebaselines | Number of times the project re-estimated effort or schedule |  |
| % effort var | Effort variance / initial effort estimate |  |
| % cost var | Cost variance / initial cost estimate |  |
| % sched variance | Schedule variance / actual duration | Used actual rather than planned duration because many of the planned start dates were not available via this “data archaeology” exercise |