Analysis 1, Cost Schedule Case

Baseline Exercise, Key

Following are a selection of statistics and charts that may be part of a baseline summary.  This is not intended to be exhaustive.

The bottom line:  the cost and schedule performance is highly variable and numerous points are outside of spec

Data File:  A1C3E1-2_Baseline-Explore-MonthlyData.MTW

Distributions and descriptive statistics

Schedule and Cost Variance Boxplots, with Cost Boxplot repeated using adjusted y scale

Trend Charts

- data sorted by month then by project name, charted by “index”

- cost chart repeated using adjusted y scale

These trends by project id are pretty messy, yet in just a few moments they show that some projects are running high and some are running low (i.e., those consistently “way out of whack” points are probably from a few specific projects)

One-way ANOVA: %sch var versus org unit

  With this analysis, we see that org unit 5’s mean is statistically different than the other means.  However, the the large standard deviation and the low r-squared contribute (in combination with the median-based boxplots) contribute to a practical interpretation that all the groups are “running in the same pack” in terms of having variability issues that need to be addressed as a top priority.

Source     DF      SS    MS      F      P

org unit    2   15757  7878  21.12  0.000

Error     696  259657   373

Total     698  275414

S = 19.32   R-Sq = 5.72%   R-Sq(adj) = 5.45%

Individual 95% CIs For Mean Based on

Pooled StDev

Level    N    Mean  StDev  ------+---------+---------+---------+---

1      344   -5.02  11.90                        (---*---)

5      189  -15.00  31.69  (-----*-----)

6      166   -3.22  11.62                          (-----*----)

------+---------+---------+---------+---

-15.0     -10.0      -5.0       0.0

Pooled StDev = 19.32

Tukey 95% Simultaneous Confidence Intervals

All Pairwise Comparisons among Levels of org unit

Individual confidence level = 98.05%

org unit = 1 subtracted from:

org

unit   Lower  Center  Upper  -------+---------+---------+---------+--

5     -14.07   -9.98  -5.89     (---*---)

6      -2.47    1.80   6.07                 (---*---)

-------+---------+---------+---------+--

-10         0        10        20

org unit = 5 subtracted from:

org

unit  Lower  Center  Upper  -------+---------+---------+---------+--

6      6.97   11.78  16.59                          (----*----)

-------+---------+---------+---------+--

-10         0        10        20

One-way ANOVA: %sch var versus month id - date

Source            DF      SS   MS     F      P

month id - date    8    3294  412  1.04  0.401

Error            690  272120  394

Total            698  275414

S = 19.86   R-Sq = 1.20%   R-Sq(adj) = 0.05%

Individual 95% CIs For Mean Based on Pooled

StDev

Level       N    Mean  StDev     -+---------+---------+---------+--------

1: Oct 01  83   -4.60  19.21                  (--------*-------)

2: Nov 01  79   -7.30  18.63             (-------*--------)

3: Dec 01  78   -7.63  18.24            (--------*--------)

4: Jan 02  77   -9.26  21.45         (-------*--------)

5: Feb 02  79  -10.87  23.33     (--------*--------)

6: Mar 02  78   -8.78  23.35          (-------*--------)

7: Apr 02  77   -6.26  23.78               (-------*--------)

8: May 02  73   -7.51  16.02            (--------*--------)

9: Jun 02  75   -3.43  10.62                    (--------*--------)

-+---------+---------+---------+--------

-15.0     -10.0      -5.0       0.0

Pooled StDev = 19.86

Tukey 95% Simultaneous Confidence Intervals

All Pairwise Comparisons among Levels of month id - date

Individual confidence level = 99.80%

month id - date = 1: Oct 01 subtracted from:

month id

- date      Lower  Center  Upper  -------+---------+---------+---------+--

2: Nov 01  -12.39   -2.70   6.99       (--------*---------)

3: Dec 01  -12.75   -3.03   6.69      (---------*---------)

4: Jan 02  -14.41   -4.66   5.09     (--------*---------)

5: Feb 02  -15.96   -6.27   3.42   (---------*--------)

6: Mar 02  -13.90   -4.18   5.54     (---------*---------)

7: Apr 02  -11.42   -1.66   8.09        (--------*---------)

8: May 02  -12.80   -2.91   6.98      (---------*---------)

9: Jun 02   -8.65    1.17  10.99          (---------*---------)

-------+---------+---------+---------+--

-10         0        10        20

month id - date = 2: Nov 01 subtracted from:

month id

- date      Lower  Center  Upper  -------+---------+---------+---------+--

3: Dec 01  -10.17   -0.33   9.51         (---------*---------)

4: Jan 02  -11.83   -1.96   7.91       (---------*---------)

5: Feb 02  -13.38   -3.57   6.24      (--------*---------)

6: Mar 02  -11.32   -1.48   8.36        (---------*--------)

7: Apr 02   -8.84    1.03  10.91          (---------*---------)

8: May 02  -10.22   -0.21   9.80         (---------*---------)

9: Jun 02   -6.07    3.87  13.81             (---------*---------)

-------+---------+---------+---------+--

-10         0        10        20

month id - date = 3: Dec 01 subtracted from:

month id

- date      Lower  Center  Upper  -------+---------+---------+---------+--

4: Jan 02  -11.54   -1.63   8.27       (---------*---------)

5: Feb 02  -13.08   -3.24   6.60      (---------*---------)

6: Mar 02  -11.02   -1.15   8.72        (---------*---------)

7: Apr 02   -8.54    1.36  11.27          (---------*---------)

8: May 02   -9.92    0.12  10.16         (---------*---------)

9: Jun 02   -5.77    4.20  14.17             (---------*---------)

-------+---------+---------+---------+--

-10         0        10        20

month id - date = 4: Jan 02 subtracted from:

month id

- date      Lower  Center  Upper  -------+---------+---------+---------+--

5: Feb 02  -11.48   -1.61   8.26        (--------*---------)

6: Mar 02   -9.42    0.48  10.39          (--------*---------)

7: Apr 02   -6.94    3.00  12.93            (---------*---------)

8: May 02   -8.32    1.75  11.82           (---------*---------)

9: Jun 02   -4.17    5.83  15.83               (---------*---------)

-------+---------+---------+---------+--

-10         0        10        20

month id - date = 5: Feb 02 subtracted from:

month id

- date     Lower  Center  Upper  -------+---------+---------+---------+--

6: Mar 02  -7.75    2.09  11.93           (---------*---------)

7: Apr 02  -5.27    4.60  14.48              (---------*--------)

8: May 02  -6.65    3.36  13.37            (---------*---------)

9: Jun 02  -2.50    7.44  17.38                (---------*---------)

-------+---------+---------+---------+--

-10         0        10        20

month id - date = 6: Mar 02 subtracted from:

month id

- date     Lower  Center  Upper  -------+---------+---------+---------+--

7: Apr 02  -7.39    2.51  12.42            (---------*--------)

8: May 02  -8.77    1.27  11.31          (---------*---------)

9: Jun 02  -4.62    5.35  15.32              (---------*---------)

-------+---------+---------+---------+--

-10         0        10        20

month id - date = 7: Apr 02 subtracted from:

month id

- date      Lower  Center  Upper  -------+---------+---------+---------+--

8: May 02  -11.31   -1.24   8.83        (---------*---------)

9: Jun 02   -7.17    2.83  12.84            (---------*---------)

-------+---------+---------+---------+--

-10         0        10        20

month id - date = 8: May 02 subtracted from:

month id

- date     Lower  Center  Upper  -------+---------+---------+---------+--

9: Jun 02  -6.06    4.08  14.21             (---------*---------)

-------+---------+---------+---------+--

-10         0        10        20

Data File:  A1C3E1_Baseline-CompletedProjects.MTW

Following are a selection of statistics and charts that may be part of a baseline summary.  This is not intended to be exhaustive.

Distributions

- note that variances are in decimal format, not yet multiplied by 100   (whereas monthly data is multiplied out)

Trend charts, sorted by finish date

- repeated with adjusted y scale

- note that variances are in decimal format, not yet multiplied by 100

Trend charts, sorted by start date

- repeated with adjusted y scale

- ???what different conclusions do you draw from this view;  can you make a distinction between projects that started before vs. after the last assessment?