## Data Collection Spreadsheet
Closed Projects
Project:
PSM:
Domain:
Category
|  | Initial Plan | Last Approved Rebaselined Plan | Actual Results | Variance from Initial Plan | Variance from Last Approved Baseline
Total Effort (# hours) |  | 59286 |  | 77618 | -18332 hours over | in hours
Schedule Start (date) |  | 2001-10-01 |  | 2001-10-01 | 0 days under
Schedule Completion (date) |  | 2002-09-30 |  | 2002-09-30 | 0 days under | in days
[5 empty] | Effort Hour Variance | Schedule Variance | # Rebaselines
Reason for Variance from Initial Plan |  |  |  |  | -18332 hours over | 0 days under
- Internal to Project
-- Missed requirements
-- Overestimated or underestimated task
-- Over commitment of personnel
-- Understaffed or inadequate funding
-- Unexpected departure of personnel
-- Skills mismatch
-- Tools unavailable
-- EV issues
-- Under planned rework
-- Planned work not performed
-- Other |  | Baseline plan called for 135 software changes to be worked. Actual was 209 |  |  | 100%
- External to Project but within Organization
-- Who
-- Why
- External to Organization
-- Who
-- Why
-- Technical /Functional Requirements Change
-- Waiting for user test
-- Assets not available
-- Reprioritization of workload
-- Other
|  |  |  | Total | 1 | 0
* Noting that there may not be a one-to-one relationship between the number of rebaselines identified in column H
and the reason for the rebaseline, what is the total number of rebaselines that occurred on the project?
Please identify the following information for each category of the completed project.
PROJECT PHASE CATEGORY |  |  |  | Initial Planned Effort (# hrs) | Actual Effort (# hrs) | Initial Planned Schedule Start (date) | Actual Schedule Start (date) | Initial Planned Schedule Completion (date) | Actual Schedule Completion (date)
Project Administration/Support
- Project Management
- Configuration Management
- Quality Assurance
Proposal
Project Planning (including prelim rqmts analysis)
Execution
- Design (including detailed rqmts analysis)
- Implement
- Formal Test
- Release
Other | The software maintenance process used has all phases in work simultaneously |  |  | 59286 | 77618 | 2001-10-01 | 2001-10-01 | 2002-09-30 | 2002-09-30
Note on B56: If a phase is used that does not fit in one of the categories above, enter the description here.
Note on C7: Input the number of effort hours originally planned for the project.
Note on C8: Input the original planned start date of the project. Use MM/DD/YY format.
Note on C9: Input the original planned completion date of the project. Use MM/DD/YY format.
Note on C14: Requirements (usually technical) that could (or should) have been derived during the planning phase that resulted in additional tasks or work that was not expected. Missed requirements are not new requirements levied by the customer or user.
Note on C15: The effort to accomplish a task (or multiple tasks) was simply overestimated or underestimated.
Note on C16: Existing personnel were assigned more workload than they were capable of accomplishing. This could be caused by adding new assignments or by reassiging a person to another project.
Note on C17: A project does not have anticipated people or funding to accomplish the work as planned.
Note on C18: A person unexpectedly left the project's office and is no longer available to work the project as planned. This may occur due to: - promotion - resigning from the government - significant illness This does not include reassignment of personnel by MAS management to work higher priority projects.
Note on C19: Personnel are available but don't have the skills to meet the estimates as planned. Examples are: - Not trained in specific programming languages - Not trained on a tester - Inexperience on a specific system (even if trained)
Note on C20: Tools are items purchased by MAS to support equipment. Examples are: - ISSs - oscilloscopes - analyzers - compilers - PCs - other support equipment Assets are not included in this category.
Note on C21: A problem with the method of calculating EV is causing the project to appear more behind or ahead of estimates than the project really is. Examples include: - wrong EV method was chosen for tasks - EV methods available do not adequately represent the way work is accomplished - planning was accomplished at too high a level
Note on C22: Rework was under planned or not planned at all and accomplishing rework is increasing the variance.
Note on C23: Planned tasks were not accomplished.
Note on C24: Input any variance cause not specifically listed. Please describe thoroughly.
Note on C26: Input the group, Section, or Branch who was responsible for the variance.
Note on C27: Input the reason for the variance.
Note on C29: List the organizations that caused the externally caused variances.
Note on C31: Requirements were added, deleted, or modified.
Note on C32: Waiting for the user to perform testing.
Note on C33: Assets are operationally used items that are capable of use by fielded organizations. Examples include: - LRUs - SRUs - Aircraft - Flightline testers
Note on C34: Decision by the customer or user to reprioritize the workload.
Note on C35: Input any variance cause not specifically listed. Please describe thoroughly.
Note on D7: If rebaselining occurred, input the last approved plan in effort hours.
Note on D9: If rebaselining occurred, input the last approved completion date.
Note on E7: Input the actual number of effort hours used to complete the project.
Note on E8: Input the actual start date of the project. Use MM/DD/YY format.
Note on E9: Input the actual completion date of the project. Use MM/DD/YY format.
Note on F15: Input the estimated % of effort hour variance due to overestimated or underestimated tasks.
Note on F16: Input the estimated % of effort hour variance due to over commitment of personnel.
Note on F17: Input the estimated % of effort hour variance due to understaffed or inadequate funding.
Note on F18: Input the estimated % of effort hour variance due to unexpected departure of personnel.
Note on F19: Input the estimated % of effort hour variance due to skills mismatch.
Note on F20: Input the estimated % of effort hour variance due to unavailability of tools.
Note on F21: Input the estimated % of effort hour variance due to Earned Value issues.
Note on F22: Input the estimated % of effort hour variance due to under planned rework.
Note on F23: Input the estimated % of effort hour variance due to planned work not performed.
Note on F24: Input the estimated % of effort hour variance due to missed requirements.
Note on F27: Input the estimated % of effort hour variance.
Note on F31: Input the estimated % of effort hour variance due to requirements changes.
Note on F32: Input the estimated % of effort hour variance due to waiting on user test.
Note on F33: Input the estimated % of effort hour variance due unavailability of assets.
Note on F34: Input the estimated % of effort hour variance due to reprioritization of workload.
Note on F35: Input the estimated % of effort hour variance.
Note on G14: Input the estimated % of schedule variance due to missed requirements.
Note on G15: Input the estimated % of schedule variance due to overestimated or underestimated tasks.
Note on G16: Input the estimated % of schedule variance due to over commitment of personnel.
Note on G17: Input the estimated % of schedule variance due to understaffed or inadequate funding.
Note on G18: Input the estimated % of schedule variance due to unexpected departure of personnel.
Note on G19: Input the estimated % of schedule variance due to skills mismatch.
Note on G20: Input the estimated % of schedule variance due to unavailability of tools.
Note on G21: Input the estimated % of schedule variance due to Earned Value issues.
Note on G22: Input the estimated % of schedule variance due to under planned rework.
Note on G23: Input the estimated % of schedule variance due to planned work not performed.
Note on G24: Input the estimated % of schedule variance.
Note on G27: Input the estimated % of schedule variance.
Note on G31: Input the estimated % of schedule variance due requirements changes.
Note on G32: Input the estimated % of schedule variance due waiting on user test.
Note on G33: Input the estimated % of schedule variance due unavailability of assets.
Note on G34: Input the estimated % of schedule variance due reprioritization of workload.
Note on G35: Input the estimated % of schedule variance.
Note on H14: Input # rebaselines due to missed requirements.
Note on H15: Input # rebaselines due to overestimated or underestimated tasks.
Note on H16: Input # rebaselines due to over commitment of personnel.
Note on H17: Input # rebaselines due to understaffed or inadequate funding.
Note on H18: Input # rebaselines due to unexpected departure of personnel.
Note on H19: Input # rebaselines due to skills mismatch.
Note on H20: Input # rebaselines due to unavailability of tools.
Note on H21: Input # rebaselines due to Earned Value issues.
Note on H22: Input # rebaselines due to under planned rework.
Note on H23: Input # rebaselines due to planned work not performed.
Note on H24: Input # rebaselines due to other reasons
Note on H27: Input # rebaselines due to an MAS organization outside the project.
Note on H31: Input # rebaselines due to requirements changes.
Note on H32: Input # rebaselines due to waiting on user test.
Note on H33: Input # rebaselines due to unavailability of assets.
Note on H34: Input # rebaselines due to reprioritization of workload.
Note on H35: Input # rebaselines due to planned work not performed.
Note on H39: Enter total number of rebaselines.
Data from the cells to the left and below was collected and transferred to the "completed project data by category" tab

## compl proj data by category
[137 empty] | % cost variance = (bcwp - acwp) / bcwp or (plan-actual)/plan | [5 empty] | negative = overrun
%schedule variance = (bcwp - bcws)/bcws or (actual - plan)/plan
[21 empty] | variance due to internal, project causes |  |  |  | % due to internal, project causes |  |  |  | variance (based on total) due to internal, project causes |  |  | # due to internal org but outside project |  |  |  | %due to internal org but outside project |  |  |  | # due to external, tech requirements |  |  |  | % due to external, tech requirements |  |  |  | # due to external, schedule/cost delays |  |  |  | % due to external, schedule/cost delays |  |  |  | total variance accounted for |  |  |  | Project Administration/Support | [5 empty] | - Project Management | [10 empty] | - Configuration Management | [10 empty] | - Quality Assurance | [10 empty] | Proposal | [13 empty] | Project Planning (including prelim rqmts analysis) | [13 empty] | Execution | [5 empty] | - Design (including detailed rqmts analysis) | [13 empty] | - Implement | [13 empty] | - Formal Test | [13 empty] | - Release
org unit | project | domain | type | priority | size | initial effort hrs | initial cost | planned finish date | planned start date | actual effort | actual cost | actual finish date | actual start date | effort variance | cost variance | sched variance | total rebaselines | % effort var | % cost var | % sched variance | hrs | cost | sched | #rebaselines | hrs | cost | sched | rebaselines | hrs | cost | sched | hrs - reqts | cost - reqts | sched - reqts | rebaselines - reqts | hrs - reqts | cost - reqts | sched - reqts | rebaselines - reqts | hrs - reqts | cost - reqts | sched - reqts | rebaselines - reqts | hrs - reqts | cost - reqts | sched - reqts | rebaselines - reqts | hrs - ext sched | cost - ext sched | sched - ext sched | rebaselines - ext sched | hrs - ext sched | cost - ext sched | sched - ext sched | rebaselines - ext sched | hrs - ext sched | cost - ext sched | sched - ext sched | rebaselines - ext sched | Planned Effort (# hrs) | Actual Effort (# hrs) | Planned Schedule Start (date) | Actual Schedule Start (date) | Planned Schedule Completion (date) | Actual Schedule Completion (date) | Planned Effort (# hrs) | Actual Effort (# hrs) | hrs deviation | within phase - atual/planned | within phase variance | phase % of budget | phase % of variance | Planned Schedule Start (date) | Actual Schedule Start (date) | Planned Schedule Completion (date) | Actual Schedule Completion (date) | Planned Effort (# hrs) | Actual Effort (# hrs) | hrs deviation | within phase - actual/plan | within phase variance | phase % of budget | phase % of variance | Planned Schedule Start (date) | Actual Schedule Start (date) | Planned Schedule Completion (date) | Actual Schedule Completion (date) | Planned Effort (# hrs) | Actual Effort (# hrs) | hrs deviation | within phase - actual/plan | within phase variance | phase % of budget | phase % of variance | Planned Schedule Start (date) | Actual Schedule Start (date) | Planned Schedule Completion (date) | Actual Schedule Completion (date) | Planned Effort (# hrs) | Actual Effort (# hrs) | hrs deviation | within phase - actual/plan | within phase variance | phase % of budget | phase % of variance | Planned Schedule Start (date) | Actual Schedule Start (date) | Planned Schedule Completion (date) | Actual Schedule Completion (date) | within phase deviation - days | within phase variance - % | within phase % of total variance | Planned Effort (# hrs) | Actual Effort (# hrs) | hrs deviation | within phase - actual/plan | within phase variance | phase % of budget | phase % of variance | Planned Schedule Start (date) | Actual Schedule Start (date) | Planned Schedule Completion (date) | Actual Schedule Completion (date) | within phase deviation - days | within phase variance - % | within phase % of total variance | Planned Effort (# hrs) | Actual Effort (# hrs) | Planned Schedule Start (date) | Actual Schedule Start (date) | Planned Schedule Completion (date) | Actual Schedule Completion (date) | Planned Effort (# hrs) | Actual Effort (# hrs) | hrs deviation | within phase - actual/plan | within phase variance | phase % of budget | phase % of variance | Planned Schedule Start (date) | Actual Schedule Start (date) | Planned Schedule Completion (date) | Actual Schedule Completion (date) | within phase deviation - days | within phase variance - % | within phase % of total variance | Planned Effort (# hrs) | Actual Effort (# hrs) | hrs deviation | within phase - actual/plan | within phase variance | phase % of budget | phase % of variance | Planned Schedule Start (date) | Actual Schedule Start (date) | Planned Schedule Completion (date) | Actual Schedule Completion (date) | within phase deviation - days | within phase variance - % | within phase % of total variance | Planned Effort (# hrs) | Actual Effort (# hrs) | hrs deviation | within phase - actual/plan | within phase variance | phase % of budget | phase % of variance | Planned Schedule Start (date) | Actual Schedule Start (date) | Planned Schedule Completion (date) | Actual Schedule Completion (date) | within phase deviation - days | within phase variance - % | within phase % of total variance | Planned Effort (# hrs) | Actual Effort (# hrs) | hrs deviation | within phase - actual/plan | within phase variance | phase % of budget | phase % of variance | Planned Schedule Start (date) | Actual Schedule Start (date) | Planned Schedule Completion (date) | Actual Schedule Completion (date) | within phase deviation - days | within phase variance - % | within phase % of total variance |  | sum of phase effort % of variance | sum of phase schedule % of variance
7 | 21 | 3 |  |  |  | 6025 | 425110 | 2001-09-28 |  | 6307 | 441490 | 2001-10-05 | 2001-04-01 | -282 | -16380 | 7 | 0 | -4.68% | -3.853% | 3.743% | [19 empty] | 282 | 19740 | 7 |  | -100% | -120.5% | 100% | [9 empty] | -100% | -120.5% | 100% | 0% | [130 empty] | 0% | 0%
3 | 37 | 1 |  |  |  | 9139 | 685425 | 2000-12-29 | 2000-01-03 | 13846 | 990450 | 2002-08-15 | 2000-01-03 | -4707 | -305025 | 594 | 4 | -51.5% | -44.5% | 62.2% | 707 | 53025 | 60 | 0 | -15.02% | -17.38% | 10.1% | 0% | 0.077361 | 0.077361 | 0.062827 | [8 empty] | 4000 | 300000 | 240 | 4 | -84.98% | -98.35% | 40.4% | 100% | 0 | 0 | 360 | 0 | -0% | -0% | 60.61% | 0% | -100% | -115.7% | 111.1% | 100% | 250 | 750 | 2000-01-03 | 2000-01-03 | 2000-12-29 | 2001-11-14 | [47 empty] | 504 | 2566 | -2062 | 509.1% | -409.1% | 5.515% | 43.81% | 2000-01-03 | 2000-01-03 | 2000-01-31 | 2000-03-01 | -30 | -51.72% | -5.051% | [6 empty] | 4783 | 6211 | -1428 | 129.9% | -29.86% | 52.34% | 30.34% | 2000-01-03 | 2000-01-14 | 2000-09-18 | 2002-02-06 | -506 | -67.11% | -85.19% | 2429 | 2709 | -280 | 111.5% | -11.53% | 26.58% | 5.949% | 2000-02-15 | 2000-01-17 | 2000-09-20 | 2002-03-07 | -533 | -68.33% | -89.73% | 584 | 1089 | -505 | 186.5% | -86.47% | 6.39% | 10.73% | 2000-09-18 | 2001-04-12 | 2000-10-20 | 2001-07-31 | -284 | -258.2% | -47.81% | 590 | 521 | 69 | 88.31% | 11.69% | 6.456% | -1.466% | 2000-01-03 | 2001-06-11 | 2000-11-01 | 2002-08-15 | -652 | -151.6% | -109.8% |  | 89.36% | -337.5%
3 | 10 | 1 |  |  |  | 16483 | 1104361 | 2001-04-30 | 2000-01-03 | 13672 | 916024 | 2001-05-18 | 2000-01-03 | 2811 | 188337 | 18 | 1 | 17.05% | 17.05% | 3.593% | [29 empty] | 18 | 1 | 0% | 0% | 100% | 100% | 0% | 0% | 100% | 100% | 3892 | 4090 | 2000-01-31 | 2000-01-31 | 2001-04-30 | 2001-05-18 | 3892 | 1990 | 1902 | 51.13% | 48.87% | 23.61% | 67.66% | 2000-01-31 | 2000-01-31 | 2001-04-30 | 2001-05-18 | 1812 | 1972 | -160 | 108.8% | -8.83% | 10.99% | -5.692% | 2000-01-31 | 2000-01-31 | 2001-04-30 | 2001-05-18 | [45 empty] | 5592 | 4124 | 1468 | 73.75% | 26.25% | 33.93% | 52.22% | 2000-01-31 | 2000-01-31 | 2000-09-01 | 2001-01-08 | -129 | -37.61% | -716.7% | 3970 | 2606 | 1364 | 65.64% | 34.36% | 24.09% | 48.52% | 2000-06-12 | 2000-05-01 | 2000-12-11 | 2001-01-18 | -38 | -14.5% | -211.1% | 1724 | 1026 | 698 | 59.51% | 40.49% | 10.46% | 24.83% | 2000-04-13 | 2000-04-10 | 2001-03-30 | 2001-03-09 | 21 | 6.306% | 116.7% | 1209 | 1361 | -152 | 112.6% | -12.57% | 7.335% | -5.407% | 2000-03-30 | 2000-04-17 | 2001-04-27 | 2001-05-18 | -21 | -5.303% | -116.7% |  | 182.1% | -927.8%
3 | 5 | 1 |  |  |  | 22725 |  | 2000-08-31 |  | 21751 |  | 2000-11-07 | 1998-10-01 | 974 |  | 68 |  | 4.286% |  | 8.854% | [35 empty] | 0% | 0% | 0% | 0% | [130 empty] | 0% | 0%
3 | 31 | 1 |  |  |  | 5475 |  | 2001-12-31 | 2001-09-01 | 6504 |  | 2002-04-11 | 2001-09-25 | -1029 |  | 101 |  | -18.79% |  | 51.01% | [35 empty] | 0% | 0% | 0% | 0% | [6 empty] | 400 | 232 | 168 | 58% | 42% | 7.306% | -16.33% | 2001-09-01 | 2001-09-25 | 2001-12-31 | 2002-04-11 | 400 | 537 | -137 | 134.2% | -34.25% | 7.306% | 13.31% | 2001-09-01 | 2001-09-24 | 2001-12-31 | 2002-04-11 | [59 empty] | 1646 | 2802 | -1156 | 170.2% | -70.23% | 30.06% | 112.3% | 2001-09-03 | 2001-07-27 | 2002-01-11 | 2002-04-11 | -90 | -34.88% | -89.11% | 425 | 345 | 80 | 81.18% | 18.82% | 7.763% | -7.775% | 2001-11-13 | 2001-11-26 | 2001-12-14 | 2002-01-11 | -28 | -60.87% | -27.72% | 20 | 9 | 11 | 45% | 55% | 0.3653% | -1.069% | 2001-12-17 | 2002-01-25 | 2001-12-18 | 2002-02-28 | -72 | -211.8% | -71.29% |  | 100.5% | -188.1%
3 | 14 | 1 |  |  |  | 10423 |  | 2001-06-30 |  | 11045 |  | 2001-07-10 | 2000-12-01 | -622 |  | 10 |  | -5.968% |  | 4.525% | [35 empty] | 0% | 0% | 0% | 0% | [6 empty] | 1008 | 1013 | -5 | 100.5% | -0.496% | 9.671% | 0.8039% | 2000-12-01 | 2000-12-01 | 2001-06-30 | 2001-06-30 | 504 | 781 | -277 | 155% | -54.96% | 4.835% | 44.53% | 2000-12-01 | 2000-12-29 | 2001-05-31 | 2001-06-30 | [59 empty] | 4541 | 5193 | -652 | 114.4% | -14.36% | 43.57% | 104.8% | 2000-12-01 | 2000-12-01 | 2001-06-30 | 2001-07-31 | -31 | -12.81% | -310% | 440 | 203 | 237 | 46.14% | 53.86% | 4.221% | -38.1% | 2001-03-05 | 2001-04-28 | 2001-04-20 | 2001-05-25 | -35 | -129.6% | -350% | 50 | 244 | -194 | 488% | -388% | 0.4797% | 31.19% | 2001-04-20 | **** | 2001-04-24 | **** |  |  |  |  | 143.2% | -660%
3 | 38 | 1 |  |  |  | 12628 | 912625 | 2001-12-30 |  | 12628 | 912625 | 2002-08-30 | 2001-06-01 | 0 | 0 | 243 | 5 | 0% | 0% | 53.41% | [21 empty] | 230 | 5 |  |  | 94.65% | 100% | [8 empty] | 0% | 0% | 94.65% | 100% | [130 empty] | 0% | 0%
4 | 11 | 1 |  |  |  | 3040 | 279600 | 2001-03-31 | 2000-07-03 | 3060.35 | 277585 | 2001-05-31 | 2000-07-03 | -20.35 | 2015 | 61 | 0 | -0.6694% | 0.7207% | 18.37% | 20.35 | 2015 |  |  | -100% | 100% |  |  | 0.0066941 | 0.0072067 |  | 0 | 0 | 45 | 0 | -0% | 0% | 73.77% | [17 empty] | -100% | 100% | 73.77% | 0% | [6 empty] | 380 | 505.75 | -125.75 | 133.1% | -33.09% | 12.5% | 617.9% |  |  |  |  | 210 | 61 | 149 | 29.05% | 70.95% | 6.908% | -732.2% |  |  |  |  | 0 | 0 | 0 |  |  | 0% | -0% |  |  |  |  | 0 | 0 | 0 |  |  | 0% | -0% | [7 empty] | 450 | 497 | -47 | 110.4% | -10.44% | 14.8% | 231% | 2000-07-03 | 2000-07-03 | 2000-10-06 | 2000-10-06 | 0 | 0% | 0% | [6 empty] | 700 | 851.25 | -151.25 | 121.6% | -21.61% | 23.03% | 743.2% | 2000-09-18 | 2000-12-18 | 2000-11-03 | 2001-03-01 | -118 | -161.6% | -193.4% | 350 | 477.625 | -127.625 | 136.5% | -36.46% | 11.51% | 627.1% | 2000-11-07 | 2001-03-04 | 2000-12-01 | 2001-04-01 | -121 | -432.1% | -198.4% | 350 | 477.625 | -127.625 | 136.5% | -36.46% | 11.51% | 627.1% | 2000-12-04 | 2001-04-02 | 2000-12-22 | 2001-04-30 | -129 | -460.7% | -211.5% | 0 | 0 | 0 |  |  | 0% | -0% | 2000-03-31 |  | 2001-05-15 | [5 empty] | 2114% | -603.3%
4 | 23 | 1 |  |  |  | 2951 | 206570 | 2001-05-11 | 1998-01-20 | 2334 | 163380 | 2001-10-18 | 1998-01-20 | 617 | 43190 | 160 | 4 | 20.91% | 20.91% | 11.7% | [29 empty] | 274 | 4 |  |  |  | 100% | 0% | 0% | 0% | 100% | [6 empty] | 337 | 302 | 35 | 89.61% | 10.39% | 11.42% | 5.673% |  |  |  |  | 1046 | 848 | 198 | 81.07% | 18.93% | 35.45% | 32.09% |  |  |  |  | 220 | 192 | 28 | 87.27% | 12.73% | 7.455% | 4.538% | [18 empty] | 119 | 103 | 16 | 86.55% | 13.45% | 4.033% | 2.593% | 1998-01-20 | 1998-01-20 | 1998-03-11 | 2001-05-23 | -1169 | -95.9% | -730.6% | [6 empty] | 1353 | 1179 | 174 | 87.14% | 12.86% | 45.85% | 28.2% | 1998-04-03 | 1998-04-22 | 1999-08-03 | 1999-08-03 | 0 | 0% | 0% | [21 empty] | 1999-03-12 | 1999-10-29 | 2001-04-30 | 2001-07-30 | -91 | -14.22% | -56.88% | [7 empty] | 2001-04-11 | 2001-09-18 | 2001-05-11 | 2001-10-18 | -160 | -533.3% | -100% |  | 73.1% | -887.5%
4 | 24 | 1 |  |  |  | 1463 | 102410 | 2001-05-11 | 1998-01-20 | 1095 | 76650 | 2001-10-18 | 1998-01-20 | 368 | 25760 | 160 | 5 | 25.15% | 25.15% | 11.7% | [29 empty] | 152 | 5 |  |  | 95% | 100% | 0% | 0% | 95% | 100% | [6 empty] | 329 | 240 | 89 | 72.95% | 27.05% | 22.49% | 24.18% |  |  |  |  | 180 | 293 | -113 | 162.8% | -62.78% | 12.3% | -30.71% |  |  |  |  | 220 | 192 | 28 | 87.27% | 12.73% | 15.04% | 7.609% | [18 empty] | 65 | 86 | -21 | 132.3% | -32.31% | 4.443% | -5.707% | 1998-01-20 | 1998-01-20 | 1998-03-06 | 2001-06-12 | -1194 | -96.37% | -746.2% | [6 empty] | 1091 | 549 | 542 | 50.32% | 49.68% | 74.57% | 147.3% | 1998-04-03 | 1998-05-04 | 1998-11-09 | 1999-03-19 | -130 | -40.75% | -81.25% | [21 empty] | 1998-11-09 | 1999-10-04 | 2001-04-30 | 2001-08-29 | -121 | -17.41% | -75.62% | [7 empty] | 2000-03-20 | 2000-03-20 | 2001-10-11 | 2001-10-11 | 0 | 0% | 0% |  | 142.7% | -903.1%
4 | 28 | 1 |  |  |  | 19772 | 1601532 | 2001-02-02 | 1998-01-01 | 31640 | 2562840 | 2002-01-10 | 1998-01-01 | -11868 | -961308 | 342 | 6 | -60.02% | -60.02% | 23.27% | 5131 | 415611 |  | 2 | -43.23% | -43.23% |  | 33.33% | 0.25951 | 0.25951 |  | 297 | 24057 |  |  | -2.503% | -2.503% |  |  | 500 | 40500 |  |  | -4.213% | -4.213% | 0% | 0% | 5940 | 481140 | 365 | 3 | -50.05% | -50.05% | 106.7% | 50% | -100% | -100% | 106.7% | 83.33% | [6 empty] | 4600 | 1472 | 3128 | 32% | 68% | 23.27% | -26.36% |  |  |  |  | 2299 | 3962 | -1663 | 172.3% | -72.34% | 11.63% | 14.01% | [29 empty] | 320 | 767 | -447 | 239.7% | -139.7% | 1.618% | 3.766% | 1998-01-01 | 1998-01-01 | 1998-02-28 | 1999-02-01 | -338 | -85.35% | -98.83% | [6 empty] | 5568 | 11400 | -5832 | 204.7% | -104.7% | 28.16% | 49.14% | 1998-02-01 | 1998-03-01 | 1999-03-01 | 1999-07-01 | -122 | -25.05% | -35.67% | 3459 | 6360 | -2901 | 183.9% | -83.87% | 17.49% | 24.44% | 1998-02-01 | 1998-03-01 | 1999-07-01 | 2001-08-09 | -770 | -61.26% | -225.1% | 3526 | 7631 | -4105 | 216.4% | -116.4% | 17.83% | 34.59% | 2001-08-10 | 2001-08-10 | 2001-10-10 | 2001-10-04 | 6 | 10.91% | 1.754% | 80 | 48 | 32 | 60% | 40% | 0.4046% | -0.2696% | 2001-07-07 | 2001-07-11 | 2002-01-07 | 2002-01-10 | -3 | -1.639% | -0.8772% |  | 99.33% | -358.8%
4 | 27 | 1 |  |  |  | 15600 | 1263600 | 2000-12-01 | 1997-12-01 | 25655 | 2078055 | 2001-12-01 | 1997-12-01 | -10055 | -814455 | 365 | 7 | -64.46% | -64.46% | 24.98% | 3100 | 251100 |  |  | -30.83% | -30.83% |  | 0% | 0.19872 | 0.19872 | [9 empty] | 2900 | 234900 |  | 1 | -28.84% | -28.84% | 0% | 14.29% | 4011 | 324881 | 365 | 3 | -39.89% | -39.89% | 100% | 42.86% | -99.56% | -99.56% | 100% | 57.14% | [6 empty] | 5356 | 5095 | 261 | 95.13% | 4.873% | 34.33% | -2.596% |  |  |  |  | 1664 | 4495 | -2831 | 270.1% | -170.1% | 10.67% | 28.16% | [29 empty] | 240 | 500 | -260 | 208.3% | -108.3% | 1.538% | 2.586% | 1997-12-01 | 1997-12-01 | 1998-02-01 | 1998-04-01 | -59 | -48.76% | -16.16% | [6 empty] | 240 | 500 | -260 | 208.3% | -108.3% | 1.538% | 2.586% | 1997-12-01 | 1997-12-01 | 1998-02-01 | 1998-04-01 | -59 | -48.76% | -16.16% | 4170 | 7488 | -3318 | 179.6% | -79.57% | 26.73% | 33% | 1998-01-01 | 1998-03-01 | 1999-06-01 | 2001-10-01 | -853 | -65.11% | -233.7% | 1068 | 3345 | -2277 | 313.2% | -213.2% | 6.846% | 22.65% | 1998-01-01 | 1998-03-01 | 1999-08-01 | 2001-11-01 | -823 | -61.37% | -225.5% | [15 empty] | 86.37% | -491.5%
4 | 25 | 1 |  |  |  | 8622 |  | 2001-05-01 |  | 7422 |  | 2001-10-31 | 1998-05-04 | 1200 |  | 183 | 0 | 13.92% |  | 14.34% | [29 empty] | 180 |  |  |  | 98.36% |  | 0% | 0% | 98.36% | 0% | [6 empty] | 3216 | 1773 | 1443 | 55.13% | 44.87% | 37.3% | 120.2% | [60 empty] | 1802 | 1883 | -81 | 104.5% | -4.495% | 20.9% | -6.75% | 1998-04-27 | 1998-04-27 | 1998-10-16 | 1998-10-06 | 10 | 6.173% | 5.464% | 2703 | 2824 | -121 | 104.5% | -4.477% | 31.35% | -10.08% | 1998-08-12 | 1998-09-02 | 1999-04-07 | 1999-04-29 | -22 | -9.205% | -12.02% | 901 | 941 | -40 | 104.4% | -4.44% | 10.45% | -3.333% | 2000-07-10 | 2000-07-10 | 2001-04-26 | 2001-10-31 | -188 | -39.33% | -102.7% | [7 empty] | 2001-05-01 | 2001-05-01 | 2001-10-31 | 2001-10-31 | 0 | 0% | 0% |  | 100.1% | -109.3%
4 | 7 | 1 |  |  |  | 802 |  | 2001-01-16 |  | 531 |  | 2001-01-22 | 2000-10-09 | 271 |  | 6 | 0 | 33.79% |  | 5.714% | [35 empty] | 0% | 0% | 0% | 0% | [6 empty] | 175 | 90 | 85 | 51.43% | 48.57% | 21.82% | 31.37% | [60 empty] | 167 | 53 | 114 | 31.74% | 68.26% | 20.82% | 42.07% | 2000-10-09 | 2000-10-09 | 2000-12-12 | 2000-12-14 | -2 | -3.03% | -33.33% | 423 | 363.5 | 59.5 | 85.93% | 14.07% | 52.74% | 21.96% | 2000-12-06 | 2000-12-04 | 2001-01-03 | 2001-01-08 | -5 | -14.29% | -83.33% | 37 | 25 | 12 | 67.57% | 32.43% | 4.613% | 4.428% | 2001-01-09 | 2001-01-12 | 2001-01-16 | 2001-01-22 | -6 | -60% | -100% | [7 empty] | 2001-01-16 | 2001-01-16 | 2001-01-22 | 2001-01-22 | 0 | 0% | 0% |  | 99.82% | -216.7%
4 | 22 | 1 |  |  |  | 4709 |  | 2001-12-01 |  | 9178 |  | 2001-10-10 | 1998-01-20 | -4469 |  | -52 | 1 | -94.9% |  | -3.826% | [19 empty] | 4000 |  |  |  | -89.51% | [11 empty] | -89.51% | 0% | 0% | 0% | [6 empty] | 1426 | 3436 | -2010 | 241% | -141% | 30.28% | 44.98% | [60 empty] | 1094 | 1914 | -820 | 175% | -74.95% | 23.23% | 18.35% | 1998-01-20 | 1998-01-20 | 1999-02-05 | 1999-02-18 | -13 | -3.299% | 25% | 1641 | 2871 | -1230 | 175% | -74.95% | 34.85% | 27.52% | 1999-02-06 | 1999-02-19 | 1999-11-30 | 1999-11-30 | 0 | 0% | -0% | 547 | 957 | -410 | 175% | -74.95% | 11.62% | 9.174% | 1999-12-01 | 1999-12-01 | 2001-10-15 | 2001-08-30 | 46 | 7.21% | -88.46% | [7 empty] | 2001-12-01 | 2001-12-01 | 2001-10-10 | 2001-10-10 | 0 | -0% | -0% |  | 100% | -63.46%
4 | 26 | 1 |  |  |  | 6684 |  | 2001-05-01 |  | 6369 |  | 2001-10-31 | 1998-01-20 | 315 |  | 183 | 0 | 4.713% |  | 13.26% | [29 empty] | 180 |  | 0% |  | 98.36% |  | 0% | 0% | 98.36% | 0% | [6 empty] | 1421 | 1462 | -41 | 102.9% | -2.885% | 21.26% | -13.02% | [60 empty] | 1754 | 1635 | 119 | 93.22% | 6.784% | 26.24% | 37.78% | 1998-06-10 | 1998-02-10 | 1999-08-04 | 1999-12-01 | -119 | -18.06% | -65.03% | 2631 | 2453 | 178 | 93.23% | 6.765% | 39.36% | 56.51% | 1999-08-05 | 1999-12-02 | 2000-02-03 | 2001-05-31 | -483 | -88.46% | -263.9% | 877 | 817 | 60 | 93.16% | 6.842% | 13.12% | 19.05% | 1999-12-15 | 1999-12-01 | 2001-05-18 | 2001-10-31 | -166 | -23.71% | -90.71% | [7 empty] | 2001-05-01 | 2001-05-01 | 2001-10-31 | 2001-10-31 | 0 | 0% | 0% |  | 100.3% | -419.7%
1 | 9 | 1 | Organic | Routine | Small | 39.5 |  | 2001-04-16 | 2001-04-09 | 48.75 |  | 2001-05-03 | 2001-04-09 | -9.25 |  | 17 |  | -23.42% |  | 70.83% | [29 empty] | 17 |  | -0% |  | 100% |  | 0% | 0% | 100% | 0% | [6 empty] | 2 | 3 | -1 | 150% | -50% | 5.063% | 10.81% | 2001-04-09 | 2001-04-09 | 2001-04-16 | 2001-05-03 | [24 empty] | 0 | [11 empty] | 2.5 | 3 | -0.5 | 120% | -20% | 6.329% | 5.405% | 2001-04-09 | 2001-04-09 | 2001-04-10 | 2001-04-10 | 0 | 0% | 0% | [20 empty] | 8 | 10.75 | -2.75 | 134.4% | -34.38% | 20.25% | 29.73% | 2001-04-10 | 2001-04-10 | 2001-04-12 | 2001-04-11 | 1 | 100% | 5.882% | 24 | 29 | -5 | 120.8% | -20.83% | 60.76% | 54.05% | 2001-04-10 | 2001-04-10 | 2001-04-13 | 2001-04-17 | -4 | -57.14% | -23.53% | 3 | 3 | 0 | 100% | 0% | 7.595% | -0% | 2001-04-16 | 2001-04-16 | 2001-05-03 | 2001-05-03 | 0 | 0% | 0% |  | 100% | -17.65%
1 | 20 | 1 | Organic | Emergency | Small | 93 |  | 2001-10-09 | 2001-09-24 | 101 |  | 2001-10-03 | 2001-09-24 | -8 |  | -6 |  | -8.602% |  | -66.67% | [35 empty] | 0% | 0% | 0% | 0% | [6 empty] | 7 | 4 | 3 | 57.14% | 42.86% | 7.527% | -37.5% | [28 empty] | 0 | [11 empty] | 7 | 6 | 1 | 85.71% | 14.29% | 7.527% | -12.5% | [27 empty] | 14 | 15 | -1 | 107.1% | -7.143% | 15.05% | 12.5% | 2001-09-24 | 2001-09-24 | 2001-09-28 | 2001-09-29 | -1 | -20% | 16.67% | 61 | 72 | -11 | 118% | -18.03% | 65.59% | 137.5% | 2001-09-28 | 2001-09-28 | 2001-10-03 | 2001-10-03 | 0 | 0% | -0% | 4 | 4 | 0 | 100% | 0% | 4.301% | -0% | 2001-10-09 | 2001-10-09 | 2001-10-02 | 2001-10-03 | -1 | 16.67% | 16.67% |  | 100% | 33.33%
1 | 40 | 1 | Hybrid | Routine | Standard | 6962 |  | 2001-05-31 | 2000-03-01 | 6560 |  | 2002-09-30 | 2000-03-07 | 402 |  | 487 | 1 | 5.774% |  | 51.97% | [29 empty] | 240 |  | 0% |  | 49.28% | 0% | 0% | 0% | 49.28% | 0% | [6 empty] | 684 | 735 | -51 | 107.5% | -7.456% | 9.825% | -12.69% | [26 empty] | 1562 | 1448 | 114 | 92.7% | 7.298% | 22.44% | 28.36% | 2000-03-01 | 2000-03-07 | 2001-05-01 | 2002-04-30 | -364 | -46.43% | -74.74% | 438 | 456 | -18 | 104.1% | -4.11% | 6.291% | -4.478% | 2000-04-15 | 2000-04-27 | 2000-08-31 | 2000-08-30 | 1 | 0.8% | 0.2053% | [20 empty] | 1747 | 1434 | 313 | 82.08% | 17.92% | 25.09% | 77.86% | 2000-06-01 | 2000-06-01 | 2000-12-01 | 2002-04-30 | -515 | -73.78% | -105.7% | 2431 | 2463 | -32 | 101.3% | -1.316% | 34.92% | -7.96% | 2000-06-01 | 2000-06-01 | 1/631/01 | 2002-09-25 |  |  |  | 100 | 24 | 76 | 24% | 76% | 1.436% | 18.91% | 2001-05-01 | 2001-05-15 | 2002-06-01 | 2002-06-30 | -29 | -7.056% | -5.955% |  | 100% | -186.2%
1 | 17 | 1 | Organic | Urgent | Small | 481.25 | 34085.94 | 2001-08-31 | 2001-06-14 | 443.5 | 31641.63 | 2001-09-04 | 2001-06-14 | 37.75 | 2444.31 | 4 |  | 7.844% | 7.171% | 4.878% | [35 empty] | 0% | 0% | 0% | 0% | [6 empty] | 25 | 17 | 8 | 68% | 32% | 5.195% | 21.19% |  |  |  |  | 13 | 5.5 | 7.5 | 42.31% | 57.69% | 2.701% | 19.87% |  |  |  |  | 10 | 8 | 2 | 80% | 20% | 2.078% | 5.298% |  |  |  |  | N/A | N/A | [5 empty] | N/A | N/A | N/A | N/A |  |  |  | 9 | 8 | 1 | 88.89% | 11.11% | 1.87% | 2.649% | 2001-06-12 | 2001-06-12 | 2001-08-30 | 2001-08-30 | 0 | 0% | 0% | [6 empty] | 28 | 23.5 | 4.5 | 83.93% | 16.07% | 5.818% | 11.92% | 2001-05-31 | 2001-05-31 | 2001-08-24 | 2001-08-24 | 0 | 0% | 0% | 21 | 28 | -7 | 133.3% | -33.33% | 4.364% | -18.54% | 2001-06-01 | 2001-06-01 | 2001-06-01 | 2001-08-24 | -84 | -100% | -2100% | 118 | 105.75 | 12.25 | 89.62% | 10.38% | 24.52% | 32.45% | 2001-08-23 | 2001-08-24 | 2001-08-30 | 2001-08-30 | 0 | 0% | 0% | 9 | 5.5 | 3.5 | 61.11% | 38.89% | 1.87% | 9.272% | 2001-08-31 | 2001-08-31 | 2001-09-04 | 2001-09-04 | 0 | 0% | 0% |  | 84.11% | -2100%
1 | 36 | 1 | Organic | Urgent | Small | 81 | 5670 | 2000-02-24 | 2000-02-22 | 2259 | 272013.88 | 2002-07-24 | 2000-02-22 | -2178 | -266343.88 | 881 | 28 | -2689% | -4697% | 99.77% | [19 empty] | 2178 | 266344 | 870 | 20 | -100% | -100% | 98.75% | 71.43% |  |  |  | 8 | -0% | -0% | 0% | 28.57% | -100% | -100% | 98.75% | 100% | [6 empty] | 5 | 184 | -179 | 3680% | -3580% | 6.173% | 8.219% |  |  |  |  | 5 | 120 | -115 | 2400% | -2300% | 6.173% | 5.28% |  |  |  |  | 2 | 43 | -41 | 2150% | -2050% | 2.469% | 1.882% |  |  |  |  | N/A | N/A | [5 empty] | N/A | N/A | N/A | N/A |  |  |  | 2 | 75 | -73 | 3750% | -3650% | 2.469% | 3.352% | 2000-02-18 | 2000-02-18 | 2000-02-18 | 2002-04-23 | -795 | -100% | -90.24% | [6 empty] | 2 | 1139 | -1137 | 56950% | -56850% | 2.469% | 52.2% | 2000-02-18 | 2000-02-18 | 2000-02-18 | 2001-08-10 | -539 | -100% | -61.18% | 2 | 1388 | -1386 | 69400% | -69300% | 2.469% | 63.64% | 2000-02-18 | 2001-02-12 | 2000-02-18 | 2001-09-18 | -578 | -265.1% | -65.61% | 58 | 899 | -841 | 1550% | -1450% | 71.6% | 38.61% | 2000-02-18 | 2001-08-17 | 2000-02-23 | 2002-04-12 | -779 | -327.3% | -88.42% | 5 | 9 | -4 | 180% | -80% | 6.173% | 0.1837% | 2000-02-24 | 2000-02-24 | 2002-07-16 | 2002-07-16 | 0 | 0% | 0% |  | 173.4% | -305.4%
1 | 8 | 1 | Organic | Routine | Small | 2095 | 146650 | 2000-12-29 | 1999-11-24 | 2041 | 142870 | 2001-01-31 | 1999-11-24 | 54 | 3780 | 21 | 0 | 2.578% | 2.578% | 4.839% | [31 empty] | 0% | 0% |  |  | 0% | 0% | 0% | 0% | [6 empty] | 196 | 140 | 56 | 71.43% | 28.57% | 9.356% | 103.7% |  |  |  |  | 39 | 69 | -30 | 176.9% | -76.92% | 1.862% | -55.56% |  |  |  |  | 276 | 157 | 119 | 56.88% | 43.12% | 13.17% | 220.4% |  |  |  |  | 37 | 37 | 0 | 100% | 0% | 1.766% | 0% | 1999-11-24 | 1999-11-24 | 1999-11-24 | 1999-11-24 | 0 |  | 0% | 646 | 620 | 26 | 95.98% | 4.025% | 30.84% | 48.15% | 1999-12-06 | 1999-12-06 | 2000-03-21 | 2000-03-16 | 5 | 4.95% | 23.81% | 901 | 1018 | 2000-04-20 | 2000-03-17 | 2000-12-29 | 2001-01-31 | 32 | 26 | 6 | 81.25% | 18.75% | 1.527% | 11.11% | 2000-04-20 | 2000-03-17 | 2000-04-27 | 2000-03-24 | 34 | 485.7% | 161.9% | 829 | 969 | -140 | 116.9% | -16.89% | 39.57% | -259.3% | 2000-04-28 | 2000-03-17 | 2000-12-29 | 2001-01-31 | -33 | -10.31% | -157.1% | 40 | 23 | 17 | 57.5% | 42.5% | 1.909% | 31.48% | 2000-09-25 | 2000-09-18 | 2000-11-30 | 2001-01-03 | -34 | -31.78% | -161.9% | Included in CM Management | [14 empty] | 100% | -133.3%
1 | 29 | 1 | Hybrid | Routine | Standard | 73103 | 10118000 | 2001-09-01 | 1997-08-01 | 74010 | 10480000 | 2002-02-02 | 1997-08-01 | -907 | -362000 | 154 | 0 | -1.241% | -3.578% | 9.356% | [29 empty] | 180 | 0 | -0% | -0% | 116.9% |  | 0% | 0% | 116.9% | 0% | [6 empty] | 2792 | 2680 | 112 | 95.99% | 4.011% | 3.819% | -12.35% |  |  |  |  | 724 | 495 | 229 | 68.37% | 31.63% | 0.9904% | -25.25% | [29 empty] | 1040 | 978 | 62 | 94.04% | 5.962% | 1.423% | -6.836% | 1997-08-01 | 1997-08-01 | 1998-05-15 | 1998-05-01 | 14 | 5.128% | 9.091% | [6 empty] | 8508 | 8700 | -192 | 102.3% | -2.257% | 11.64% | 21.17% | 1997-08-01 | 1997-08-01 | 1999-08-01 | 1999-08-01 | 0 | 0% | 0% | 3190 | 3680 | -490 | 115.4% | -15.36% | 4.364% | 54.02% | 1998-08-01 | 1998-08-01 | 1999-08-01 | 1999-12-01 | -122 | -25.05% | -79.22% | 15560 | 13004 | 2556 | 83.57% | 16.43% | 21.29% | -281.8% | 1998-10-01 | 1998-10-01 | 2001-05-01 | 2001-12-01 | -214 | -18.5% | -139% | 1214 | 692 | 522 | 57% | 43% | 1.661% | -57.55% | 1998-10-01 | 2001-12-01 | 2001-09-01 | [5 empty] | -308.6% | -209.1%
1 | 4 | 1 | Hybrid | Routine | Small | 2610 | 245000 | 1999-10-29 | 1998-09-18 | 2003 | 199000 | 2000-10-30 | 1998-09-18 | 607 | 46000 | 367 | 2 | 23.26% | 18.78% | 47.48% | [27 empty] | 0 | 0 | 365 | 2 | 0% | 0% | 99.46% | 100% | 0% | 0% | 99.46% | 100% | [6 empty] | 60 | 90.5 | -30.5 | 150.8% | -50.83% | 2.299% | -5.025% |  |  |  |  | 90 | 15.75 | 74.25 | 17.5% | 82.5% | 3.448% | 12.23% | [29 empty] | 315 | 285 | 30 | 90.48% | 9.524% | 12.07% | 4.942% | 1998-09-18 | 1998-09-18 | 1998-11-12 | 1998-11-12 | 0 | 0% | 0% | [6 empty] | 300 | 271 | 29 | 90.33% | 9.667% | 11.49% | 4.778% | 1998-11-18 | 1998-11-22 | 1999-01-06 | 1999-01-31 | -25 | -35.71% | -6.812% | 150 | 102 | 48 | 68% | 32% | 5.747% | 7.908% | 1998-11-18 | 1998-11-22 | 1999-01-06 | 1999-02-28 | -53 | -54.08% | -14.44% | 495 | 327 | 168 | 66.06% | 33.94% | 18.97% | 27.68% | 1998-11-18 | 1999-01-01 | 1999-08-27 | 2000-09-01 | -371 | -60.92% | -101.1% | 30 | 163.5 | -133.5 | 545% | -445% | 1.149% | -21.99% | 1999-09-06 | 1999-10-19 | 2000-09-01 | 2000-09-30 | -29 | -8.357% | -7.902% |  | 30.52% | -130.2%
1 | 12 | 1 | Organic | Routine | Small | 2227 | 162571 | 2001-06-30 |  | 1638 | 119574 | 2001-06-30 | 2000-03-03 | 589 | 42997 | 0 | 0 | 26.45% | 26.45% | 0% | [35 empty] | 0% | 0% | 0% | 0% | [6 empty] | 359 | 168 | 191 | 46.8% | 53.2% | 16.12% | 32.43% |  |  |  |  | 36 | 36 | 0 | 100% | 0% | 1.617% | 0% |  |  |  |  | 24 | 24 | 0 | 100% | 0% | 1.078% | 0% |  |  |  |  | 12 | 12 | 0 | 100% | 0% | 0.5388% | 0% | 2000-03-01 | 2000-03-01 | 2000-03-30 | 2000-03-30 | 0 | 0% |  | 184 | 184 | 0 | 100% | 0% | 8.262% | 0% | 2000-03-01 | 2000-03-01 | 2000-03-30 | 2000-03-30 | 0 | 0% | [7 empty] | 60 | 40 | 20 | 66.67% | 33.33% | 2.694% | 3.396% | 2000-04-01 | 2000-04-01 | 2000-05-01 | 2000-05-01 | 0 | 0% |  | 520 | 453 | 67 | 87.12% | 12.88% | 23.35% | 11.38% | 2000-05-01 | 2000-05-01 | 2000-09-30 | 2000-09-20 | 10 | 7.042% |  | 120 | 154 | -34 | 128.3% | -28.33% | 5.388% | -5.772% | 2000-10-01 | 2000-11-01 | 2000-12-30 | 2001-02-10 | -42 | -41.58% |  | 32 | 26 | 6 | 81.25% | 18.75% | 1.437% | 1.019% | 2001-06-15 | 2001-06-15 | 2001-06-20 | 2001-06-20 | 0 | 0% |  |  | 42.44% | 0%
1 | 15 | 1 | Hybrid | Urgent | Small | 735 | 76500 | 2001-07-27 | 2001-05-08 | 735 | 76500 | 2001-07-27 | 2001-05-08 | 0 | 0 | 0 | 0 | 0% | 0% | 0% | [35 empty] | 0% | 0% | 0% | 0% | [6 empty] | 4 | 4 | 0 | 100% | 0% | 0.5442% | [41 empty] | 4 | 4 | 0 | 100% | 0% | 0.5442% |  | 2001-05-08 | 2001-05-08 | 2001-05-08 | 2001-05-08 | 0 | [8 empty] | 8 | 8 | 0 | 100% | 0% | 1.088% |  | 2001-05-08 | 2001-05-08 | 2001-05-17 | 2001-05-17 | 0 | 0% |  | 4 | 4 | 0 | 100% | 0% | 0.5442% |  | 2001-05-08 | 2001-05-08 | 2001-05-17 | 2001-05-17 | 0 | 0% |  | 0 | 0 | 0 |  |  |  |  | 2001-06-14 | 2001-07-15 | 2001-05-21 | 2001-07-02 | -42 | 323.1% |  | 4 | 4 | 0 | 100% | 0% | 0.5442% |  | 2001-07-31 | 2001-07-27 | 2001-07-31 | 2001-07-27 | 4 |  |  |  | 0% | 0%
1 | 41 | 1 | Organic | Urgent | Small | 886 |  | 2002-01-17 |  | 442 |  | 2002-09-30 | 2001-08-30 | 444 |  | 256 | 0 | 50.11% |  | 64.65% | 58 |  |  | 0 | 13.06% |  |  |  | 0.065463 | [10 empty] | 286 |  | 252 | 0 | 64.41% |  | 98.44% |  |  |  | 30 | 0 | 0% |  | 11.72% |  | 77.48% | 0% | 110.2% | 0% | [53 empty] | 64 |  |  | 0% | 100% | 7.223% | 14.41% | 2001-08-30 | 2001-08-30 | 2001-09-07 | 2001-09-14 | -7 | -46.67% | -2.734% | [13 empty] | 2001-08-30 | 2001-08-30 | [14 empty] | 2001-09-19 | 2001-10-31 | -42 | -0.1129% | -16.41% | 216 |  |  |  |  | 24.38% |  | 2001-09-10 | 2001-09-10 | 2002-01-15 | 2002-06-17 | -153 | -54.64% | -59.77% | 366 |  |  | 0% | 100% | 41.31% | 82.43% | 2001-11-05 | 2001-12-10 | 2002-01-17 | 2002-09-30 | -256 | -87.07% | -100% |  | 96.85% | -178.9%
1 | 18 | 1 | Organic | Urgent | Small | 538 |  | 2001-09-21 |  | 538 |  | 2001-09-21 | 2001-05-07 | 0 |  | 0 |  | 0% |  | 0% | [35 empty] | 0% | 0% | 0% | 0% | [53 empty] | 64 |  |  | 0% | 100% | 11.9% |  | 2001-05-07 | 2001-05-07 | 2001-07-31 | 2001-08-10 | -10 | -10.53% | [14 empty] | 2001-05-07 | 2001-05-07 | [19 empty] | 216 |  |  |  |  | 40.15% |  | 2001-05-21 | 2001-05-21 | 2001-08-31 | 2001-08-28 | 3 | 3.03% |  | 122 |  |  | 0% | 100% | 22.68% |  | 2001-08-31 | 2001-08-31 | 2001-09-21 | 2001-09-21 | 0 | 0% |  |  | 0% | 0%
1 | 32 | 1 | Organic | Routine | Standard | 8978 | 589010 | 2000-10-15 |  | 11370 | 739910 | 2002-04-23 | 1998-08-01 | -2392 | -150900 | 555 | 0 | -26.64% | -25.62% | 40.78% | 2062 | 134030 | 308 | 0 | -86.2% | -88.82% | 55.5% |  | 0.22967 | 0.22755 | 0.2263 | [16 empty] | 330 | 21450 | 270 | 0 | -13.8% | -14.21% | 48.65% |  | -100% | -103% | 104.1% | 0% | [6 empty] | 252 | 511 | -259 | 202.8% | -102.8% | 2.807% | 10.83% |  |  |  |  | 170 | 67 | 103 | 39.41% | 60.59% | 1.894% | -4.306% |  |  |  |  | n/a | n/a | [9 empty] | n/a | n/a | [5 empty] | n/a | n/a | n/a | n/a |  |  |  | 1228 | 1134 | 94 | 92.35% | 7.655% | 13.68% | -3.93% | 1998-09-01 | 1998-09-01 | 1999-06-15 | 1999-06-15 | 0 | 0% | 0% | [6 empty] | 1212 | 1727 | -515 | 142.5% | -42.49% | 13.5% | 21.53% | 1999-01-01 | 1999-01-01 | 2000-02-28 | 2000-03-10 | -11 | -2.535% | -1.982% | 2384 | 3168 | -784 | 132.9% | -32.89% | 26.55% | 32.78% | 1999-08-01 | 1999-08-01 | 2000-05-31 | 2000-10-31 | -153 | -33.48% | -27.57% | 672 | 1544 | -872 | 229.8% | -129.8% | 7.485% | 36.45% | 2000-06-01 | 2000-11-01 | 2000-08-10 | 2001-06-01 | -295 | -139.2% | -53.15% | 32 | 60 | -28 | 187.5% | -87.5% | 0.3564% | 1.171% | 2000-10-28 | 2000-10-31 | 2002-04-23 | 2002-04-26 | -3 | -0.5535% | -0.5405% |  | 94.52% | -83.24%
1 | 1 | 1 | Hybrid | Routine | Small | 2313 | 178101 | 2000-02-28 |  | 4198 | 426906 | 2000-05-31 | 1999-11-22 | -1885 | -248805 | 93 | 1 | -81.5% | -139.7% | 48.69% | 465 | 35000 | 120 | 1 | -24.67% | -14.07% |  | 100% | 0.20104 | 0.19652 | 0.62827 | 1420 | 213000 | 120 |  | -75.33% | -85.61% | [18 empty] | -100% | -99.68% | 0% | 100% | [6 empty] | 331 | 504 | -173 | 152.3% | -52.27% | 14.31% | 9.178% | [15 empty] | 120 | 120 | 0 | 100% | 0% | 5.188% | -0% | [18 empty] | 281 | 289 | -8 | 102.8% | -2.847% | 12.15% | 0.4244% | 1999-11-11 | 1999-11-11 | 2001-02-28 | 2001-05-31 | -92 | -16.23% | -98.92% | [6 empty] | 600 | 600 | 0 | 100% | 0% | 25.94% | -0% | 2000-02-18 | 2000-02-18 | 2000-02-18 | 2000-02-18 | 0 |  | 0% | 681 | 681 | 0 | 100% | 0% | 29.44% | -0% | 2000-09-15 | 2000-09-15 | 2001-01-16 | 2001-01-16 | 0 | 0% | 0% | 180 | 1884 | -1704 | 1047% | -946.7% | 7.782% | 90.4% | 2001-01-16 | 2001-01-16 | 2001-04-16 | 2001-04-16 | 0 | 0% | 0% | 120 | 120 | 0 | 100% | 0% | 5.188% | -0% | 2001-04-16 | 2001-04-16 | 2001-05-28 | 2001-05-28 | 0 | 0% | 0% |  | 100% | -98.92%
2 | 19 | 1 |  |  |  | 35314 | 2335751.5628 | 37165 |  | 34713 | 2296000 | 2001-10-01 |  | 601 | 39751.5628 | 0 |  | 1.702% | 1.702% | 0% | [35 empty] | 0% | 0% | 0% | 0% | [130 empty] | 0% | 0%
2 | 6 | 1 |  |  |  | 17428 | 1235993 | 2000-12-01 |  | 10614 | 752745 | 2000-12-01 |  | 6814 | 483248 | 0 |  | 39.1% | 39.1% | 0% | [35 empty] | 0% | 0% | 0% | 0% | [130 empty] | 0% | 0%
2 | 3 | 1 |  |  |  | 11535 | 818159 | 2000-07-01 |  | 11138 | 790000 | 2000-07-01 |  | 397 | 28159 | 0 |  | 3.442% | 3.442% | 0% | [35 empty] | 0% | 0% | 0% | 0% | [130 empty] | 0% | 0%
2 | 2 | 1 |  |  |  | 7783 | 551970 | 2000-06-01 |  | 7145 | 506723 | 2000-06-01 |  | 638 | 45247 | 0 |  | 8.197% | 8.197% | 0% | [35 empty] | 0% | 0% | 0% | 0% | [130 empty] | 0% | 0%
6 | 35 | 1 |  |  |  | 13378 | 829436 | 2002-03-15 |  | 19443 | 1205466 | 2002-05-15 | 1999-05-01 | -6065 | -376030 | 61 |  | -45.34% | -45.34% | 5.495% | [35 empty] | 0% | 0% | 0% | 0% | [130 empty] | 0% | 0%
6 | 33 | 1 |  |  |  | 18278 | 1133236 | 2002-06-01 |  | 11942 | 740404 | 2002-05-01 | 2001-06-01 | 6336 | 392832 | -31 |  | 34.66% | 34.66% | -9.281% | [35 empty] | 0% | 0% | 0% | 0% | [130 empty] | 0% | 0%
6 | 34 | 1 |  |  |  | 671 | 45809.17 | 2001-12-02 |  | 368 | 25123.36 | 2002-05-12 | 2001-09-02 | 303 | 20685.81 | 161 | 0 | 45.16% | 45.16% | 63.89% | na | na |  | 0 | [7 empty] | 0 | 0 | 0 | 0 | 0% | 0% | 0% |  | 0 | 0 | 0 | 0 | 0% | 0% | 0% |  | 0 | 0 | 0 | 0 | 0% | 0% | 0% |  | 0% | 0% | 0% | 0% | [6 empty] | 0 | 8 | -8 |  |  | 0% | -2.64% |  |  |  |  | 0 | 5 | -5 |  |  | 0% | -1.65% |  |  |  |  | 0 | 4 | -4 |  |  | 0% | -1.32% |  |  |  |  | 0 | 0 | 0 |  |  |  |  | NA | NA | NA | NA |  |  |  | 40 | 10 | 30 | 25% | 75% | 5.961% | 9.901% | 2001-09-02 | 2001-09-02 | 2001-09-07 | 2001-09-06 | 1 | 25% | 0.6211% | [6 empty] | 30 | 28 | 2 | 93.33% | 6.667% | 4.471% | 0.6601% | 2001-09-10 | 2001-09-10 | 2001-09-14 | 2001-09-18 | -4 | -50% | -2.484% | 30 | 54 | -24 | 180% | -80% | 4.471% | -7.921% | 2001-09-17 | 2001-09-24 | 2001-09-21 | 2001-10-05 | -14 | -127.3% | -8.696% | 340 | 150 | 190 | 44.12% | 55.88% | 50.67% | 62.71% | 2001-09-24 | 2001-10-08 | 2001-11-19 | 2001-12-10 | -21 | -33.33% | -13.04% | 0 | 8 | -8 |  |  | 0% | -2.64% | 2001-11-29 | 2002-05-05 | 2001-12-02 | 2002-05-12 | -161 | -2300% | -100% |  | 57.1% | -123.6%
6 | 16 | 1 |  |  |  | 8000 | 560000 | 2001-07-31 |  | 8931 | 625170 | 2001-08-09 | 2000-12-11 | -931 | -65170 | 9 |  | -11.64% | -11.64% | 3.734% | [19 empty] | 150 | 10500 |  |  | -16.11% | -16.11% | 0% | [9 empty] | -16.11% | -16.11% | 0% | 0% | [6 empty] | 1061 | 763 | 298 | 71.91% | 28.09% | 13.26% | -32.01% |  |  |  |  | 457 | 452 | 5 | 98.91% | 1.094% | 5.713% | -0.5371% | [29 empty] | 2367 | 2910 | -543 | 122.9% | -22.94% | 29.59% | 58.32% | [14 empty] | 26 | -26 |  |  | 0% | 2.793% | [7 empty] | 1190 | 638 | 552 | 53.61% | 46.39% | 14.88% | -59.29% | 2001-01-16 |  | 2001-04-02 |  |  |  |  | 1701 | 3224 | -1523 | 189.5% | -89.54% | 21.26% | 163.6% | 2001-04-11 |  | 2001-07-12 |  |  |  |  | 1225 | 918 | 307 | 74.94% | 25.06% | 15.31% | -32.98% |  |  | 2001-07-31 | 2001-08-09 | -9 | -0.02425% | -100% |  | 99.89% | -100%
6 | 42 | 1 |  |  |  | 6495 | 519600 | 2002-08-31 |  | 6665 | 533200 | 2002-09-30 | 2001-08-20 | -170 | -13600 | 30 |  | -2.617% | -2.617% | 7.389% | [35 empty] | 0% | 0% | 0% | 0% | [6 empty] | 2201 | 952 | 1249 | 43.25% | 56.75% | 33.89% | -734.7% |  |  |  |  | 366 | 356 | 10 | 97.27% | 2.732% | 5.635% | -5.882% | [49 empty] | 221 | 142 | 79 | 64.25% | 35.75% | 3.403% | -46.47% | [7 empty] | 1263 | 1468 |  | 116.2% | -16.23% | 19.45% | 120.6% | [7 empty] | 2444 | 3747 | -1303 | 153.3% | -53.31% | 37.63% | 766.5% | [22 empty] | 100% | 0%
5 | 39 | 3 |  |  |  | 1484 |  | 2003-05-16 | 2002-02-25 | 843 |  | 2002-09-20 | 2002-03-18 | 641 |  | -238 |  | 43.19% |  | -128% | [35 empty] | 0% | 0% | 0% | 0% | [130 empty] | 0% | 0%
5 | 30 | 3 |  |  |  | 1632 |  | 2002-08-20 | 2001-06-27 | 1433 |  | 2002-04-09 | 2001-06-27 | 199 |  | -133 |  | 12.19% |  | -46.5% | [35 empty] | 0% | 0% | 0% | 0% | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  | 0% | 0% | [15 empty] | 0 | 0 | 0 |  |  | 0% | 0% | [32 empty] | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  | 0% | 0% | [7 empty] | 0 | 0 | 0 |  |  | 0% | 0% | [7 empty] | 16 | 13 | 3 | 81.25% | 18.75% | 0.9804% | 1.508% | [22 empty] | 1.508% | 0%
5 | 13 | 2 |  |  |  | 254590 | 21702886 | 1997-09-30 |  | 274020 | 21778295 | 2001-06-30 | 1993-10-01 | -19430 | -75409 | 1369 | 5 | -7.632% | -0.3475% | 48.39% |  | 997371 | 180 | 2 |  | -1323% | 13.15% | 40% |  | 0.045956 | 0.063627 | [9 empty] | -921962 |  | 3 | -0% | 1223% | 0% | 60% |  |  | 1275 | 3 | -0% | -0% | 93.13% | 60% | 0% | -100% | 106.3% | 160% | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  | 0% | -0% | [15 empty] | 0 | 0 | 0 |  |  | 0% | -0% | [32 empty] | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  | 0% | -0% | [7 empty] | 0 | 0 | 0 |  |  | 0% | -0% | [7 empty] | 8 | 13 | -5 | 162.5% | -62.5% | 0.003142% | 0.02573% | [22 empty] | 0.02573% | 0%
[18 empty] | % effort var | % cost var | % sched variance | [118 empty] | -170
[15 empty] | avg | 154.9048 |  | -66.07% | -173.1% | 14.97% |  |  |  | avg | -40.98% | -202.4% | 26.25% | 34.67% | 14.84% | 14.47% | 24.53% |  |  |  | avg | -19.46% | -22.03% | 36.89% | #DIV/0! |  |  |  | avg | -35.92% | 106.8% | 43.22% | 57.62% |  |  |  | avg | -6.916% | -9.469% | 73.64% | 58.14% | -19.71% | -17.97% | 41.97% | 26.2% | [7 empty] | avg |  | 2.3387 | -133.9% | 13.29% | 7.643% | [5 empty] | avg |  | 244.4% | -144.4% | 7.229% | -38.46% | [5 empty] | avg |  | 380.2% | -280.2% | 4.225% | 21.67% | [5 empty] | avg |  | 97.57% | 2.433% | 6.185% | 7.09% |  |  |  | avg | -121.3333 | -23.21% | -37.37% |  | avg |  | 284.5% | -184.5% | 8.639% | 19.89% |  |  |  | avg | -183.65 | -27.14% | -103.2% | [7 empty] | avg |  | 2689% | -2589% | 17.39% | 51.15% |  |  |  | avg | -82.5238 | -5.084% | -58.25% |  | avg |  | 2783% | -2683% | 20.5% | 41.39% |  |  |  | avg | -181.2 | -56.13% | -185.6% |  | avg |  | 211.2% | -111.2% | 20.69% | 68.55% |  |  |  | avg | -138.8889 | -57.01% | -79.1% |  | avg |  | 126.6% | -26.56% | 6.002% | 1.095% |  |  |  | avg | -58 | -143% | -33.16% | avg | 104.8% | -233.3%
[15 empty] | std dev | 284.9478 |  | 415.9% | 887.5% | 38.29% |  |  |  | std dev | 39.79% | 497.3% | 25.37% | 40.93% | 9.683% | 9.903% | 26.67% |  |  |  | std dev | 37.27% | 42.4% | 52.16% | #DIV/0! |  |  |  | std dev | 55.36% | 453.4% | 48.7% | 42.39% |  |  |  | std dev | 15.97% | 18.2% | 39.87% | 40.75% | 43.58% | 45.55% | 50.01% | 46.06% | [7 empty] | std dev |  | 7.0468 | 704.7% | 11.15% | 188.5% | [5 empty] | std dev |  | 559.3% | 559.3% | 8.021% | 174.7% | [5 empty] | std dev |  | 780.5% | 780.5% | 5.453% | 65.96% | [5 empty] | std dev |  | 4.214% | 4.214% | 10.86% | 14.18% |  |  |  | std dev | 210.1555 | 32.83% | 52.85% |  | std dev |  | 780.7% | 780.7% | 8.167% | 53.18% |  |  |  | std dev | 389.1378 | 40.86% | 242.1% | [7 empty] | std dev |  | 12119% | 12119% | 18.96% | 151.5% |  |  |  | std dev | 155.8405 | 122.7% | 172.9% |  | std dev |  | 13587% | 13587% | 14.47% | 135.9% |  |  |  | std dev | 265.6222 | 101.6% | 428.7% |  | std dev |  | 327.2% | 327.2% | 20.08% | 196.5% |  |  |  | std dev | 219.2746 | 134% | 93.44% |  | std dev |  | 146.1% | 146.1% | 9.869% | 26.99% |  |  |  | std dev | 142.775 | 485.2% | 49% | std dev | 327.2% | 395.9%
[15 empty] | median | 45.5 |  | 0.8509% | 0.3603% | 8.122% |  |  |  | median | -30.83% | -30.83% | 13.15% | 33.33% | 19.87% | 19.65% | 14.5% |  |  |  | median | -1.251% | -1.251% | 36.89% | #VALUE! |  |  |  | median | -22.48% | -22.48% | 20.2% | 65.71% |  |  |  | median | -0% | 0% | 96.68% | 55% | 0% | 0% | 0% | 0% | [7 empty] | median |  | 0.92371 | 7.629% | 9.825% | 3.238% | [5 empty] | median |  | 100% | 0% | 5.674% | -0.2685% | [5 empty] | median |  | 87.27% | 12.73% | 2.078% | -0% | [5 empty] | median |  | 100% | 0% | 1.152% | 0% |  |  |  | median | 0 | -23.21% | -37.37% |  | median |  | 100% | 0% | 6.31% | 3% |  |  |  | median | 0 | 0% | 0% | [7 empty] | median |  | 96.67% | 3.333% | 11.64% | 15.13% |  |  |  | median | -11 | -10.68% | -6.812% |  | median |  | 114.9% | -14.86% | 21.8% | 24.44% |  |  |  | median | -42 | -25.05% | -83.33% |  | median |  | 118% | -18.03% | 11.62% | 24.83% |  |  |  | median | -42 | -33.33% | -67.7% |  | median |  | 88.31% | 11.69% | 1.661% | -0% |  |  |  | median | -0.5 | 0% | -0.5405% | median | 87.87% | -99.46%
[15 empty] | min | -238 |  | -2689% | -4697% | -128% |  |  |  | min | -100% | -1323% | 10.1% | 0% | 0.6694% | 0.7207% | 6.283% |  |  |  | min | -75.33% | -85.61% | 0% | 0% |  |  |  | min | -100% | -120.5% | 0% | 0% |  |  |  | min | -50.05% | -50.05% | 0% | 0% | -100% | -120.5% | 0% | 0% | [7 empty] | min |  | 0.32 | -3580% | 0% | -734.7% | [5 empty] | min |  | 17.5% | -2300% | 0% | -732.2% | [5 empty] | min |  | 56.88% | -2050% | 0% | -1.32% | [5 empty] | min |  | 92.7% | 0% | 0% | -0% |  |  |  | min | -364 | -46.43% | -74.74% |  | min |  | 0% | -3650% | 0.5442% | -12.5% |  |  |  | min | -1194 | -100% | -746.2% | [7 empty] | min |  | 31.74% | -56850% | 0% | -46.47% |  |  |  | min | -539 | -161.6% | -716.7% |  | min |  | 53.61% | -69300% | 0% | -259.3% |  |  |  | min | -853 | -432.1% | -2100% |  | min |  | 44.12% | -1450% | 0.003142% | -281.8% |  |  |  | min | -823 | -460.7% | -350% |  | min |  | 0% | -445% | 0% | -57.55% |  |  |  | min | -652 | -2300% | -116.7% | min | -308.6% | -2100%
[15 empty] | max | 1369 |  | 50.11% | 45.16% | 99.77% |  |  |  | max | 13.06% | 100% | 55.5% | 100% | 25.95% | 25.95% | 62.83% |  |  |  | max | -0% | 0% | 73.77% | 0% |  |  |  | max | 64.41% | 1223% | 100% | 100% |  |  |  | max | -0% | -0% | 116.9% | 100% | 77.48% | 100% | 116.9% | 160% | [7 empty] | max |  | 36.8 | 68% | 37.3% | 617.9% | [5 empty] | max |  | 2400% | 82.5% | 35.45% | 44.53% | [5 empty] | max |  | 2150% | 43.12% | 15.04% | 220.4% | [5 empty] | max |  | 100% | 7.298% | 22.44% | 28.36% |  |  |  | max | 0 | 0% | 0% |  | max |  | 3750% | 100% | 30.84% | 231% |  |  |  | max | 14 | 25% | 23.81% | [7 empty] | max |  | 56950% | 68.26% | 74.57% | 743.2% |  |  |  | max | 34 | 485.7% | 161.9% |  | max |  | 69400% | 46.39% | 52.74% | 627.1% |  |  |  | max | 10 | 100% | 16.67% |  | max |  | 1550% | 55.88% | 71.6% | 766.5% |  |  |  | max | 46 | 323.1% | 116.7% |  | max |  | 545% | 100% | 41.31% | 82.43% |  |  |  | max | 4 | 16.67% | 16.67% | max | 2114% | 33.33%
[15 empty] | n | 42 |  | 42 | 28 | 42 |  |  |  | n | 7 | 7 | 3 | 5 | 7 | 7 | 4 |  |  |  | n | 4 | 4 | 2 | 0 |  |  |  | n | 10 | 8 | 10 | 6 |  |  |  | n | 15 | 11 | 16 | 10 | 42 | 42 | 42 | 42 | [7 empty] | n |  | 26 | 26 | 29 | 28 | [5 empty] | n |  | 17 | 17 | 18 | 18 | [5 empty] | n |  | 7 | 7 | 11 | 11 | [5 empty] | n |  | 3 | 3 | 4 | 4 |  |  |  | n | 3 | 2 | 2 |  | n |  | 22 | 22 | 22 | 20 |  |  |  | n | 20 | 19 | 17 | [7 empty] | n |  | 22 | 22 | 25 | 24 |  |  |  | n | 21 | 20 | 19 |  | n |  | 26 | 26 | 28 | 27 |  |  |  | n | 25 | 25 | 23 |  | n |  | 27 | 27 | 29 | 27 |  |  |  | n | 27 | 27 | 24 |  | n |  | 19 | 19 | 21 | 19 |  |  |  | n | 24 | 23 | 21 | n | 42 | 42
excluding project on row 27
[15 empty] | avg |  |  | -2.101% | -5.578% | 12.9%
[15 empty] | std dev |  |  | 32.91% | 38.54% | 36.31%
[15 empty] | median |  |  | 1.702% | 0.7207% | 7.389%
[15 empty] | min |  |  | -94.9% | -139.7% | -128%
[15 empty] | max |  |  | 50.11% | 45.16% | 70.83%
Note on H37: Jeannine M. Siviy: this was back calculated
Note on O6: Jeannine M. Siviy:( initial - actual)
Note on Q28: Jeannine M. Siviy: typed in <3 wks
Note on S6: Jeannine M. Siviy: initial - actual)/ initial
Note on S49: Jeannine M. Siviy: initial - actual)/ initial
Note on U6: Jeannine M. Siviy: % of actual duration (because planned duration not available for all projects)
Note on U49: Jeannine M. Siviy: % of actual duration (because planned duration not available for all projects)
Note on V5: Jeannine M. Siviy: missing data implied no contribution to variance if another category is present; if all categories missing, then data is not available also note… review raw data -- things don't always sum up to 100%
Note on V7: Jeannine M. Siviy: implied: no contribution to variance (see 'eternal' contributions)
Note on W7: Jeannine M. Siviy: implied: no contribution to variance (see 'eternal' contributions)
Note on X7: Jeannine M. Siviy: implied: no contribution to variance (see 'eternal' contributions)
Note on Y7: Jeannine M. Siviy: no rebaselines done
Note on AY25: Jeannine M. Siviy: 8 mos = 8*30??
Note on BO47: Paul.Beard: The project and configuration management tasks hrs were collected under our normal sustainment project
Note on BO48: Paul.Beard: The project and configuration management tasks hrs were collected under our normal sustainment project
Note on BP43: Jeannine M. Siviy: see comments
Note on BP47: Paul.Beard: The project and configuration management tasks hrs were collected under our normal sustainment project
Note on BP48: Paul.Beard: The project and configuration management tasks hrs were collected under our normal sustainment project
Note on ER45: Chandra Emanuel: Includes Code and integration, Documentation and training
Note on ES45: Chandra Emanuel: Includes code and integration, documentation and training
Note on FF45: Chandra Emanuel: Includes procedures, baseline testing rehost, unique testing, regression testing
Note on FG45: Chandra Emanuel: Includes procedures, baseline test rehosting, unique testing and regression testing
Note on FO25: Jeannine M. Siviy: this was typed into original spreadsheet; not sure whether 1/6/01 or 6/31/01 (or something else) is correct
Note on GB16: Jeannine M. Siviy: swapped 2 fields - appears that planned completion date was typed in actual start field and that actual start was typed in planned completion
Note on GB17: Jeannine M. Siviy: swapped 2 fields - appears that planned completion date was typed in actual start field and that actual start was typed in planned completion
Note on GB19: Jeannine M. Siviy: swapped 2 fields - appears that planned completion date was typed in actual start field and that actual start was typed in planned completion
Note on GB20: Jeannine M. Siviy: swapped 2 fields - appears that planned completion date was typed in actual start field and that actual start was typed in planned completion
Note on GB21: Jeannine M. Siviy: swapped 2 fields - appears that planned completion date was typed in actual start field and that actual start was typed in planned completion
Note on GB22: Jeannine M. Siviy: swapped 2 fields - appears that planned completion date was typed in actual start field and that actual start was typed in planned completion
Note on GB23: Jeannine M. Siviy: swapped 2 fields - appears that planned completion date was typed in actual start field and that actual start was typed in planned completion
Note on GB24: Jeannine M. Siviy: swapped 2 fields - appears that planned completion date was typed in actual start field and that actual start was typed in planned completion
Note on GB25: Jeannine M. Siviy: swapped 2 fields - appears that planned completion date was typed in actual start field and that actual start was typed in planned completion
Note on GB26: Jeannine M. Siviy: swapped 2 fields - appears that planned completion date was typed in actual start field and that actual start was typed in planned completion
Note on GB27: Jeannine M. Siviy: swapped 2 fields - appears that planned completion date was typed in actual start field and that actual start was typed in planned completion
Note on GB29: Jeannine M. Siviy: swapped 2 fields - appears that planned completion date was typed in actual start field and that actual start was typed in planned completion
Note on GB30: Jeannine M. Siviy: swapped 2 fields - appears that planned completion date was typed in actual start field and that actual start was typed in planned completion
Note on GB31: Jeannine M. Siviy: swapped 2 fields - appears that planned completion date was typed in actual start field and that actual start was typed in planned completion
Note on GB32: Jeannine M. Siviy: swapped 2 fields - appears that planned completion date was typed in actual start field and that actual start was typed in planned completion
Note on GB35: Jeannine M. Siviy: swapped 2 fields - appears that planned completion date was typed in actual start field and that actual start was typed in planned completion
Note on GC16: Jeannine M. Siviy: swapped 2 fields - appears that planned completion date was typed in actual start field and that actual start was typed in planned completion
Note on GC17: Jeannine M. Siviy: swapped 2 fields - appears that planned completion date was typed in actual start field and that actual start was typed in planned completion
Note on GC19: Jeannine M. Siviy: swapped 2 fields - appears that planned completion date was typed in actual start field and that actual start was typed in planned completion
Note on GC20: Jeannine M. Siviy: swapped 2 fields - appears that planned completion date was typed in actual start field and that actual start was typed in planned completion
Note on GC21: Jeannine M. Siviy: swapped 2 fields - appears that planned completion date was typed in actual start field and that actual start was typed in planned completion
Note on GC22: Jeannine M. Siviy: swapped 2 fields - appears that planned completion date was typed in actual start field and that actual start was typed in planned completion
Note on GC23: Jeannine M. Siviy: swapped 2 fields - appears that planned completion date was typed in actual start field and that actual start was typed in planned completion
Note on GC24: Jeannine M. Siviy: swapped 2 fields - appears that planned completion date was typed in actual start field and that actual start was typed in planned completion
Note on GC25: Jeannine M. Siviy: swapped 2 fields - appears that planned completion date was typed in actual start field and that actual start was typed in planned completion
Note on GC26: Jeannine M. Siviy: swapped 2 fields - appears that planned completion date was typed in actual start field and that actual start was typed in planned completion
Note on GC27: Jeannine M. Siviy: swapped 2 fields - appears that planned completion date was typed in actual start field and that actual start was typed in planned completion
Note on GC29: Jeannine M. Siviy: swapped 2 fields - appears that planned completion date was typed in actual start field and that actual start was typed in planned completion
Note on GC30: Jeannine M. Siviy: swapped 2 fields - appears that planned completion date was typed in actual start field and that actual start was typed in planned completion
Note on GC31: Jeannine M. Siviy: swapped 2 fields - appears that planned completion date was typed in actual start field and that actual start was typed in planned completion
Note on GC32: Jeannine M. Siviy: swapped 2 fields - appears that planned completion date was typed in actual start field and that actual start was typed in planned completion
Note on GC35: Jeannine M. Siviy: swapped 2 fields - appears that planned completion date was typed in actual start field and that actual start was typed in planned completion
blank cell = missing data (crosscheck for any n/a's that were typed in)
pink=calculated on data collection spreadsheet and copied here;
light gray = intended as "no data entry" field in data collection spreadsheet, but some folks typed in information
dark gray= intended as a rollup in data collection spreadsheet, but some folks typed numbers in directly....
blue=calculated in this spreadsheet (your assignment is to evaluate/summarize info in the blue zones)
if calculation not possible due to missing value or divide by zero, you will need to blank it out to do the summary stats
Data by internal/external
categories begins here
Data by life cycle phase
categories begins here

## compl proj - coded
[138 empty] | % cost variance = (bcwp - acwp) / bcwp or (plan-actual)/plan | [5 empty] | negative = overrun
%schedule variance = (bcwp - bcws)/bcws or (actual - plan)/plan
[21 empty] | variance due to internal, project causes |  |  |  | % due to internal, project causes |  |  |  | variance (based on total) due to internal, project causes |  |  | # due to internal org but outside project |  |  |  | %due to internal org but outside project |  |  |  | # due to external, tech requirements |  |  |  | % due to external, tech requirements |  |  |  | # due to external, schedule/cost delays |  |  |  | % due to external, schedule/cost delays |  |  |  | total variance accounted for |  |  |  |  | Project Administration/Support | [5 empty] | - Project Management | [10 empty] | - Configuration Management | [10 empty] | - Quality Assurance | [10 empty] | Proposal | [13 empty] | Project Planning (including prelim rqmts analysis) | [13 empty] | Execution | [5 empty] | - Design (including detailed rqmts analysis) | [13 empty] | - Implement | [13 empty] | - Formal Test | [13 empty] | - Release
org unit | project | domain | type | priority | size | initial effort hrs | initial cost | planned finish date | planned start date | actual effort | actual cost | actual finish date | actual start date | effort variance | cost variance | sched variance | total rebaselines | % effort var | % cost var | % sched variance | hrs | cost | sched | #rebaselines | hrs | cost | sched | rebaselines | hrs | cost | sched | hrs - reqts | cost - reqts | sched - reqts | rebaselines - reqts | hrs - reqts | cost - reqts | sched - reqts | rebaselines - reqts | hrs - reqts | cost - reqts | sched - reqts | rebaselines - reqts | hrs - reqts | cost - reqts | sched - reqts | rebaselines - reqts | hrs - ext sched | cost - ext sched | sched - ext sched | rebaselines - ext sched | hrs - ext sched | cost - ext sched | sched - ext sched | rebaselines - ext sched | hrs - ext sched | cost - ext sched | sched - ext sched | rebaselines - ext sched | comments | Planned Effort (# hrs) | Actual Effort (# hrs) | Planned Schedule Start (date) | Actual Schedule Start (date) | Planned Schedule Completion (date) | Actual Schedule Completion (date) | Planned Effort (# hrs) | Actual Effort (# hrs) | hrs deviation | within phase - atual/planned | within phase variance | phase % of budget | phase % of variance | Planned Schedule Start (date) | Actual Schedule Start (date) | Planned Schedule Completion (date) | Actual Schedule Completion (date) | Planned Effort (# hrs) | Actual Effort (# hrs) | hrs deviation | within phase - actual/plan | within phase variance | phase % of budget | phase % of variance | Planned Schedule Start (date) | Actual Schedule Start (date) | Planned Schedule Completion (date) | Actual Schedule Completion (date) | Planned Effort (# hrs) | Actual Effort (# hrs) | hrs deviation | within phase - actual/plan | within phase variance | phase % of budget | phase % of variance | Planned Schedule Start (date) | Actual Schedule Start (date) | Planned Schedule Completion (date) | Actual Schedule Completion (date) | Planned Effort (# hrs) | Actual Effort (# hrs) | hrs deviation | within phase - actual/plan | within phase variance | phase % of budget | phase % of variance | Planned Schedule Start (date) | Actual Schedule Start (date) | Planned Schedule Completion (date) | Actual Schedule Completion (date) | within phase deviation - days | within phase variance - % | within phase % of total variance | Planned Effort (# hrs) | Actual Effort (# hrs) | hrs deviation | within phase - actual/plan | within phase variance | phase % of budget | phase % of variance | Planned Schedule Start (date) | Actual Schedule Start (date) | Planned Schedule Completion (date) | Actual Schedule Completion (date) | within phase deviation - days | within phase variance - % | within phase % of total variance | Planned Effort (# hrs) | Actual Effort (# hrs) | Planned Schedule Start (date) | Actual Schedule Start (date) | Planned Schedule Completion (date) | Actual Schedule Completion (date) | Planned Effort (# hrs) | Actual Effort (# hrs) | hrs deviation | within phase - actual/plan | within phase variance | phase % of budget | phase % of variance | Planned Schedule Start (date) | Actual Schedule Start (date) | Planned Schedule Completion (date) | Actual Schedule Completion (date) | within phase deviation - days | within phase variance - % | within phase % of total variance | Planned Effort (# hrs) | Actual Effort (# hrs) | hrs deviation | within phase - actual/plan | within phase variance | phase % of budget | phase % of variance | Planned Schedule Start (date) | Actual Schedule Start (date) | Planned Schedule Completion (date) | Actual Schedule Completion (date) | within phase deviation - days | within phase variance - % | within phase % of total variance | Planned Effort (# hrs) | Actual Effort (# hrs) | hrs deviation | within phase - actual/plan | within phase variance | phase % of budget | phase % of variance | Planned Schedule Start (date) | Actual Schedule Start (date) | Planned Schedule Completion (date) | Actual Schedule Completion (date) | within phase deviation - days | within phase variance - % | within phase % of total variance | Planned Effort (# hrs) | Actual Effort (# hrs) | hrs deviation | within phase - actual/plan | within phase variance | phase % of budget | phase % of variance | Planned Schedule Start (date) | Actual Schedule Start (date) | Planned Schedule Completion (date) | Actual Schedule Completion (date) | within phase deviation - days | within phase variance - % | within phase % of total variance |  | sum of phase effort % of variance | sum of phase schedule % of variance
7 | 21 | 3 |  |  |  | 6025 | 425110 | 2001-09-28 |  | 6307 | 441490 | 2001-10-05 | 2001-04-01 | -282 | -16380 | 7 | 0 | -4.68% | -3.853% | 3.743% | [19 empty] | 282 | 19740 | 7 |  | -100% | -120.5% | 100% | [9 empty] | -100% | -120.5% | 100% | 0% | cost variance due to tech reqts > actual variance; no data by development phase | [130 empty] | 0% | 0%
3 | 37 | 1 |  |  |  | 9139 | 685425 | 2000-12-29 | 2000-01-03 | 13846 | 990450 | 2002-08-15 | 2000-01-03 | -4707 | -305025 | 594 | 4 | -51.5% | -44.5% | 62.2% | 707 | 53025 | 60 | 0 | -15.02% | -17.38% | 10.1% | 0% | 0.077361 | 0.077361 | 0.062827 | [8 empty] | 4000 | 300000 | 240 | 4 | -84.98% | -98.35% | 40.4% | 100% | 0 | 0 | 360 | 0 | -0% | -0% | 60.61% | 0% | -100% | -115.7% | 111.1% | 100% |  | 250 | 750 | 2000-01-03 | 2000-01-03 | 2000-12-29 | 2001-11-14 | [47 empty] | 504 | 2566 | -2062 | 509.1% | -409.1% | 5.515% | 43.81% | 2000-01-03 | 2000-01-03 | 2000-01-31 | 2000-03-01 | -30 | -51.72% | -5.051% | [6 empty] | 4783 | 6211 | -1428 | 129.9% | -29.86% | 52.34% | 30.34% | 2000-01-03 | 2000-01-14 | 2000-09-18 | 2002-02-06 | -506 | -67.11% | -85.19% | 2429 | 2709 | -280 | 111.5% | -11.53% | 26.58% | 5.949% | 2000-02-15 | 2000-01-17 | 2000-09-20 | 2002-03-07 | -533 | -68.33% | -89.73% | 584 | 1089 | -505 | 186.5% | -86.47% | 6.39% | 10.73% | 2000-09-18 | 2001-04-12 | 2000-10-20 | 2001-07-31 | -284 | -258.2% | -47.81% | 590 | 521 | 69 | 88.31% | 11.69% | 6.456% | -1.466% | 2000-01-03 | 2001-06-11 | 2000-11-01 | 2002-08-15 | -652 | -151.6% | -109.8% |  | 89.36% | -337.5%
3 | 10 | 1 |  |  |  | 16483 | 1104361 | 2001-04-30 | 2000-01-03 | 13672 | 916024 | 2001-05-18 | 2000-01-03 | 2811 | 188337 | 18 | 1 | 17.05% | 17.05% | 3.593% | [29 empty] | 18 | 1 | 0% | 0% | 100% | 100% | 0% | 0% | 100% | 100% |  | 3892 | 4090 | 2000-01-31 | 2000-01-31 | 2001-04-30 | 2001-05-18 | 3892 | 1990 | 1902 | 51.13% | 48.87% | 23.61% | 67.66% | 2000-01-31 | 2000-01-31 | 2001-04-30 | 2001-05-18 | 1812 | 1972 | -160 | 108.8% | -8.83% | 10.99% | -5.692% | 2000-01-31 | 2000-01-31 | 2001-04-30 | 2001-05-18 | [45 empty] | 5592 | 4124 | 1468 | 73.75% | 26.25% | 33.93% | 52.22% | 2000-01-31 | 2000-01-31 | 2000-09-01 | 2001-01-08 | -129 | -37.61% | -716.7% | 3970 | 2606 | 1364 | 65.64% | 34.36% | 24.09% | 48.52% | 2000-06-12 | 2000-05-01 | 2000-12-11 | 2001-01-18 | -38 | -14.5% | -211.1% | 1724 | 1026 | 698 | 59.51% | 40.49% | 10.46% | 24.83% | 2000-04-13 | 2000-04-10 | 2001-03-30 | 2001-03-09 | 21 | 6.306% | 116.7% | 1209 | 1361 | -152 | 112.6% | -12.57% | 7.335% | -5.407% | 2000-03-30 | 2000-04-17 | 2001-04-27 | 2001-05-18 | -21 | -5.303% | -116.7% |  | 182.1% | -927.8%
3 | 5 | 1 |  |  |  | 22725 |  | 2000-08-31 |  | 21751 |  | 2000-11-07 | 1998-10-01 | 974 |  | 68 |  | 4.286% |  | 8.854% | [35 empty] | 0% | 0% | 0% | 0% | [131 empty] | 0% | 0%
3 | 31 | 1 |  |  |  | 5475 |  | 2001-12-31 | 2001-09-01 | 6504 |  | 2002-04-11 | 2001-09-25 | -1029 |  | 101 |  | -18.79% |  | 51.01% | [35 empty] | 0% | 0% | 0% | 0% | [7 empty] | 400 | 232 | 168 | 58% | 42% | 7.306% | -16.33% | 2001-09-01 | 2001-09-25 | 2001-12-31 | 2002-04-11 | 400 | 537 | -137 | 134.2% | -34.25% | 7.306% | 13.31% | 2001-09-01 | 2001-09-24 | 2001-12-31 | 2002-04-11 | [59 empty] | 1646 | 2802 | -1156 | 170.2% | -70.23% | 30.06% | 112.3% | 2001-09-03 | 2001-07-27 | 2002-01-11 | 2002-04-11 | -90 | -34.88% | -89.11% | 425 | 345 | 80 | 81.18% | 18.82% | 7.763% | -7.775% | 2001-11-13 | 2001-11-26 | 2001-12-14 | 2002-01-11 | -28 | -60.87% | -27.72% | 20 | 9 | 11 | 45% | 55% | 0.3653% | -1.069% | 2001-12-17 | 2002-01-25 | 2001-12-18 | 2002-02-28 | -72 | -211.8% | -71.29% |  | 100.5% | -188.1%
3 | 14 | 1 |  |  |  | 10423 |  | 2001-06-30 |  | 11045 |  | 2001-07-10 | 2000-12-01 | -622 |  | 10 |  | -5.968% |  | 4.525% | [35 empty] | 0% | 0% | 0% | 0% | **** Due to Technical order delays in LUTD the OFPs essetially sat on the shelf until 31 Mar 02. | [6 empty] | 1008 | 1013 | -5 | 100.5% | -0.496% | 9.671% | 0.8039% | 2000-12-01 | 2000-12-01 | 2001-06-30 | 2001-06-30 | 504 | 781 | -277 | 155% | -54.96% | 4.835% | 44.53% | 2000-12-01 | 2000-12-29 | 2001-05-31 | 2001-06-30 | [59 empty] | 4541 | 5193 | -652 | 114.4% | -14.36% | 43.57% | 104.8% | 2000-12-01 | 2000-12-01 | 2001-06-30 | 2001-07-31 | -31 | -12.81% | -310% | 440 | 203 | 237 | 46.14% | 53.86% | 4.221% | -38.1% | 2001-03-05 | 2001-04-28 | 2001-04-20 | 2001-05-25 | -35 | -129.6% | -350% | 50 | 244 | -194 | 488% | -388% | 0.4797% | 31.19% | 2001-04-20 | **** | 2001-04-24 | **** |  |  |  |  | 143.2% | -660%
3 | 38 | 1 |  |  |  | 12628 | 912625 | 2001-12-30 |  | 12628 | 912625 | 2002-08-30 | 2001-06-01 | 0 | 0 | 243 | 5 | 0% | 0% | 53.41% | [21 empty] | 230 | 5 |  |  | 94.65% | 100% | [8 empty] | 0% | 0% | 94.65% | 100% | [131 empty] | 0% | 0%
4 | 11 | 1 |  |  |  | 3040 | 279600 | 2001-03-31 | 2000-07-03 | 3060.35 | 277585 | 2001-05-31 | 2000-07-03 | -20.35 | 2015 | 61 | 0 | -0.6694% | 0.7207% | 18.37% | 20.35 | 2015 |  |  | -100% | 100% |  |  | 0.0066941 | 0.0072067 |  | 0 | 0 | 45 | 0 | -0% | 0% | 73.77% | [17 empty] | -100% | 100% | 73.77% | 0% | [7 empty] | 380 | 505.75 | -125.75 | 133.1% | -33.09% | 12.5% | 617.9% |  |  |  |  | 210 | 61 | 149 | 29.05% | 70.95% | 6.908% | -732.2% |  |  |  |  | 0 | 0 | 0 |  |  | 0% | -0% |  |  |  |  | 0 | 0 | 0 |  |  | 0% | -0% | [7 empty] | 450 | 497 | -47 | 110.4% | -10.44% | 14.8% | 231% | 2000-07-03 | 2000-07-03 | 2000-10-06 | 2000-10-06 | 0 | 0% | 0% | [6 empty] | 700 | 851.25 | -151.25 | 121.6% | -21.61% | 23.03% | 743.2% | 2000-09-18 | 2000-12-18 | 2000-11-03 | 2001-03-01 | -118 | -161.6% | -193.4% | 350 | 477.625 | -127.625 | 136.5% | -36.46% | 11.51% | 627.1% | 2000-11-07 | 2001-03-04 | 2000-12-01 | 2001-04-01 | -121 | -432.1% | -198.4% | 350 | 477.625 | -127.625 | 136.5% | -36.46% | 11.51% | 627.1% | 2000-12-04 | 2001-04-02 | 2000-12-22 | 2001-04-30 | -129 | -460.7% | -211.5% | 0 | 0 | 0 |  |  | 0% | -0% | 2000-03-31 |  | 2001-05-15 | [5 empty] | 2114% | -603.3%
4 | 23 | 1 |  |  |  | 2951 | 206570 | 2001-05-11 | 1998-01-20 | 2334 | 163380 | 2001-10-18 | 1998-01-20 | 617 | 43190 | 160 | 4 | 20.91% | 20.91% | 11.7% | [29 empty] | 274 | 4 |  |  |  | 100% | 0% | 0% | 0% | 100% | Notes: 1) Effort hours include all Execution phases 2) Design phase and Implement phase are combined | [6 empty] | 337 | 302 | 35 | 89.61% | 10.39% | 11.42% | 5.673% |  |  |  |  | 1046 | 848 | 198 | 81.07% | 18.93% | 35.45% | 32.09% |  |  |  |  | 220 | 192 | 28 | 87.27% | 12.73% | 7.455% | 4.538% | [18 empty] | 119 | 103 | 16 | 86.55% | 13.45% | 4.033% | 2.593% | 1998-01-20 | 1998-01-20 | 1998-03-11 | 2001-05-23 | -1169 | -95.9% | -730.6% | [6 empty] | 1353 | 1179 | 174 | 87.14% | 12.86% | 45.85% | 28.2% | 1998-04-03 | 1998-04-22 | 1999-08-03 | 1999-08-03 | 0 | 0% | 0% | [21 empty] | 1999-03-12 | 1999-10-29 | 2001-04-30 | 2001-07-30 | -91 | -14.22% | -56.88% | [7 empty] | 2001-04-11 | 2001-09-18 | 2001-05-11 | 2001-10-18 | -160 | -533.3% | -100% |  | 73.1% | -887.5%
4 | 24 | 1 |  |  |  | 1463 | 102410 | 2001-05-11 | 1998-01-20 | 1095 | 76650 | 2001-10-18 | 1998-01-20 | 368 | 25760 | 160 | 5 | 25.15% | 25.15% | 11.7% | [29 empty] | 152 | 5 |  |  | 95% | 100% | 0% | 0% | 95% | 100% | Notes: 1) Effort hours include all Execution phases 2) Design phase and Implement phase are combined | [6 empty] | 329 | 240 | 89 | 72.95% | 27.05% | 22.49% | 24.18% |  |  |  |  | 180 | 293 | -113 | 162.8% | -62.78% | 12.3% | -30.71% |  |  |  |  | 220 | 192 | 28 | 87.27% | 12.73% | 15.04% | 7.609% | [18 empty] | 65 | 86 | -21 | 132.3% | -32.31% | 4.443% | -5.707% | 1998-01-20 | 1998-01-20 | 1998-03-06 | 2001-06-12 | -1194 | -96.37% | -746.2% | [6 empty] | 1091 | 549 | 542 | 50.32% | 49.68% | 74.57% | 147.3% | 1998-04-03 | 1998-05-04 | 1998-11-09 | 1999-03-19 | -130 | -40.75% | -81.25% | [21 empty] | 1998-11-09 | 1999-10-04 | 2001-04-30 | 2001-08-29 | -121 | -17.41% | -75.62% | [7 empty] | 2000-03-20 | 2000-03-20 | 2001-10-11 | 2001-10-11 | 0 | 0% | 0% |  | 142.7% | -903.1%
4 | 28 | 1 |  |  |  | 19772 | 1601532 | 2001-02-02 | 1998-01-01 | 31640 | 2562840 | 2002-01-10 | 1998-01-01 | -11868 | -961308 | 342 | 6 | -60.02% | -60.02% | 23.27% | 5131 | 415611 |  | 2 | -43.23% | -43.23% |  | 33.33% | 0.25951 | 0.25951 |  | 297 | 24057 |  |  | -2.503% | -2.503% |  |  | 500 | 40500 |  |  | -4.213% | -4.213% | 0% | 0% | 5940 | 481140 | 365 | 3 | -50.05% | -50.05% | 106.7% | 50% | -100% | -100% | 106.7% | 83.33% | [7 empty] | 4600 | 1472 | 3128 | 32% | 68% | 23.27% | -26.36% |  |  |  |  | 2299 | 3962 | -1663 | 172.3% | -72.34% | 11.63% | 14.01% | [29 empty] | 320 | 767 | -447 | 239.7% | -139.7% | 1.618% | 3.766% | 1998-01-01 | 1998-01-01 | 1998-02-28 | 1999-02-01 | -338 | -85.35% | -98.83% | [6 empty] | 5568 | 11400 | -5832 | 204.7% | -104.7% | 28.16% | 49.14% | 1998-02-01 | 1998-03-01 | 1999-03-01 | 1999-07-01 | -122 | -25.05% | -35.67% | 3459 | 6360 | -2901 | 183.9% | -83.87% | 17.49% | 24.44% | 1998-02-01 | 1998-03-01 | 1999-07-01 | 2001-08-09 | -770 | -61.26% | -225.1% | 3526 | 7631 | -4105 | 216.4% | -116.4% | 17.83% | 34.59% | 2001-08-10 | 2001-08-10 | 2001-10-10 | 2001-10-04 | 6 | 10.91% | 1.754% | 80 | 48 | 32 | 60% | 40% | 0.4046% | -0.2696% | 2001-07-07 | 2001-07-11 | 2002-01-07 | 2002-01-10 | -3 | -1.639% | -0.8772% |  | 99.33% | -358.8%
4 | 27 | 1 |  |  |  | 15600 | 1263600 | 2000-12-01 | 1997-12-01 | 25655 | 2078055 | 2001-12-01 | 1997-12-01 | -10055 | -814455 | 365 | 7 | -64.46% | -64.46% | 24.98% | 3100 | 251100 |  |  | -30.83% | -30.83% |  | 0% | 0.19872 | 0.19872 | [9 empty] | 2900 | 234900 |  | 1 | -28.84% | -28.84% | 0% | 14.29% | 4011 | 324881 | 365 | 3 | -39.89% | -39.89% | 100% | 42.86% | -99.56% | -99.56% | 100% | 57.14% | [7 empty] | 5356 | 5095 | 261 | 95.13% | 4.873% | 34.33% | -2.596% |  |  |  |  | 1664 | 4495 | -2831 | 270.1% | -170.1% | 10.67% | 28.16% | [29 empty] | 240 | 500 | -260 | 208.3% | -108.3% | 1.538% | 2.586% | 1997-12-01 | 1997-12-01 | 1998-02-01 | 1998-04-01 | -59 | -48.76% | -16.16% | [6 empty] | 240 | 500 | -260 | 208.3% | -108.3% | 1.538% | 2.586% | 1997-12-01 | 1997-12-01 | 1998-02-01 | 1998-04-01 | -59 | -48.76% | -16.16% | 4170 | 7488 | -3318 | 179.6% | -79.57% | 26.73% | 33% | 1998-01-01 | 1998-03-01 | 1999-06-01 | 2001-10-01 | -853 | -65.11% | -233.7% | 1068 | 3345 | -2277 | 313.2% | -213.2% | 6.846% | 22.65% | 1998-01-01 | 1998-03-01 | 1999-08-01 | 2001-11-01 | -823 | -61.37% | -225.5% | [15 empty] | 86.37% | -491.5%
4 | 25 | 1 |  |  |  | 8622 |  | 2001-05-01 |  | 7422 |  | 2001-10-31 | 1998-05-04 | 1200 |  | 183 | 0 | 13.92% |  | 14.34% | [29 empty] | 180 |  |  |  | 98.36% |  | 0% | 0% | 98.36% | 0% | [7 empty] | 3216 | 1773 | 1443 | 55.13% | 44.87% | 37.3% | 120.2% | [60 empty] | 1802 | 1883 | -81 | 104.5% | -4.495% | 20.9% | -6.75% | 1998-04-27 | 1998-04-27 | 1998-10-16 | 1998-10-06 | 10 | 6.173% | 5.464% | 2703 | 2824 | -121 | 104.5% | -4.477% | 31.35% | -10.08% | 1998-08-12 | 1998-09-02 | 1999-04-07 | 1999-04-29 | -22 | -9.205% | -12.02% | 901 | 941 | -40 | 104.4% | -4.44% | 10.45% | -3.333% | 2000-07-10 | 2000-07-10 | 2001-04-26 | 2001-10-31 | -188 | -39.33% | -102.7% | [7 empty] | 2001-05-01 | 2001-05-01 | 2001-10-31 | 2001-10-31 | 0 | 0% | 0% |  | 100.1% | -109.3%
4 | 7 | 1 |  |  |  | 802 |  | 2001-01-16 |  | 531 |  | 2001-01-22 | 2000-10-09 | 271 |  | 6 | 0 | 33.79% |  | 5.714% | [35 empty] | 0% | 0% | 0% | 0% | [7 empty] | 175 | 90 | 85 | 51.43% | 48.57% | 21.82% | 31.37% | [60 empty] | 167 | 53 | 114 | 31.74% | 68.26% | 20.82% | 42.07% | 2000-10-09 | 2000-10-09 | 2000-12-12 | 2000-12-14 | -2 | -3.03% | -33.33% | 423 | 363.5 | 59.5 | 85.93% | 14.07% | 52.74% | 21.96% | 2000-12-06 | 2000-12-04 | 2001-01-03 | 2001-01-08 | -5 | -14.29% | -83.33% | 37 | 25 | 12 | 67.57% | 32.43% | 4.613% | 4.428% | 2001-01-09 | 2001-01-12 | 2001-01-16 | 2001-01-22 | -6 | -60% | -100% | [7 empty] | 2001-01-16 | 2001-01-16 | 2001-01-22 | 2001-01-22 | 0 | 0% | 0% |  | 99.82% | -216.7%
4 | 22 | 1 |  |  |  | 4709 |  | 2001-12-01 |  | 9178 |  | 2001-10-10 | 1998-01-20 | -4469 |  | -52 | 1 | -94.9% |  | -3.826% | [19 empty] | 4000 |  |  |  | -89.51% | [11 empty] | -89.51% | 0% | 0% | 0% | [7 empty] | 1426 | 3436 | -2010 | 241% | -141% | 30.28% | 44.98% | [60 empty] | 1094 | 1914 | -820 | 175% | -74.95% | 23.23% | 18.35% | 1998-01-20 | 1998-01-20 | 1999-02-05 | 1999-02-18 | -13 | -3.299% | 25% | 1641 | 2871 | -1230 | 175% | -74.95% | 34.85% | 27.52% | 1999-02-06 | 1999-02-19 | 1999-11-30 | 1999-11-30 | 0 | 0% | -0% | 547 | 957 | -410 | 175% | -74.95% | 11.62% | 9.174% | 1999-12-01 | 1999-12-01 | 2001-10-15 | 2001-08-30 | 46 | 7.21% | -88.46% | [7 empty] | 2001-12-01 | 2001-12-01 | 2001-10-10 | 2001-10-10 | 0 | -0% | -0% |  | 100% | -63.46%
4 | 26 | 1 |  |  |  | 6684 |  | 2001-05-01 |  | 6369 |  | 2001-10-31 | 1998-01-20 | 315 |  | 183 | 0 | 4.713% |  | 13.26% | [29 empty] | 180 |  | 0% |  | 98.36% |  | 0% | 0% | 98.36% | 0% | [7 empty] | 1421 | 1462 | -41 | 102.9% | -2.885% | 21.26% | -13.02% | [60 empty] | 1754 | 1635 | 119 | 93.22% | 6.784% | 26.24% | 37.78% | 1998-06-10 | 1998-02-10 | 1999-08-04 | 1999-12-01 | -119 | -18.06% | -65.03% | 2631 | 2453 | 178 | 93.23% | 6.765% | 39.36% | 56.51% | 1999-08-05 | 1999-12-02 | 2000-02-03 | 2001-05-31 | -483 | -88.46% | -263.9% | 877 | 817 | 60 | 93.16% | 6.842% | 13.12% | 19.05% | 1999-12-15 | 1999-12-01 | 2001-05-18 | 2001-10-31 | -166 | -23.71% | -90.71% | [7 empty] | 2001-05-01 | 2001-05-01 | 2001-10-31 | 2001-10-31 | 0 | 0% | 0% |  | 100.3% | -419.7%
1 | 9 | 1 | Organic | Routine | Small | 39.5 |  | 2001-04-16 | 2001-04-09 | 48.75 |  | 2001-05-03 | 2001-04-09 | -9.25 |  | 17 |  | -23.42% |  | 70.83% | [29 empty] | 17 |  | -0% |  | 100% |  | 0% | 0% | 100% | 0% | 17 day delay due to 36th {cust org} delay | [6 empty] | 2 | 3 | -1 | 150% | -50% | 5.063% | 10.81% | 2001-04-09 | 2001-04-09 | 2001-04-16 | 2001-05-03 | [24 empty] | 0 | [11 empty] | 2.5 | 3 | -0.5 | 120% | -20% | 6.329% | 5.405% | 2001-04-09 | 2001-04-09 | 2001-04-10 | 2001-04-10 | 0 | 0% | 0% | [20 empty] | 8 | 10.75 | -2.75 | 134.4% | -34.38% | 20.25% | 29.73% | 2001-04-10 | 2001-04-10 | 2001-04-12 | 2001-04-11 | 1 | 100% | 5.882% | 24 | 29 | -5 | 120.8% | -20.83% | 60.76% | 54.05% | 2001-04-10 | 2001-04-10 | 2001-04-13 | 2001-04-17 | -4 | -57.14% | -23.53% | 3 | 3 | 0 | 100% | 0% | 7.595% | -0% | 2001-04-16 | 2001-04-16 | 2001-05-03 | 2001-05-03 | 0 | 0% | 0% |  | 100% | -17.65%
1 | 20 | 1 | Organic | Emergency | Small | 93 |  | 2001-10-09 | 2001-09-24 | 101 |  | 2001-10-03 | 2001-09-24 | -8 |  | -6 |  | -8.602% |  | -66.67% | [35 empty] | 0% | 0% | 0% | 0% | [7 empty] | 7 | 4 | 3 | 57.14% | 42.86% | 7.527% | -37.5% | [28 empty] | 0 | [11 empty] | 7 | 6 | 1 | 85.71% | 14.29% | 7.527% | -12.5% | [27 empty] | 14 | 15 | -1 | 107.1% | -7.143% | 15.05% | 12.5% | 2001-09-24 | 2001-09-24 | 2001-09-28 | 2001-09-29 | -1 | -20% | 16.67% | 61 | 72 | -11 | 118% | -18.03% | 65.59% | 137.5% | 2001-09-28 | 2001-09-28 | 2001-10-03 | 2001-10-03 | 0 | 0% | -0% | 4 | 4 | 0 | 100% | 0% | 4.301% | -0% | 2001-10-09 | 2001-10-09 | 2001-10-02 | 2001-10-03 | -1 | 16.67% | 16.67% |  | 100% | 33.33%
1 | 40 | 1 | Hybrid | Routine | Standard | 6962 |  | 2001-05-31 | 2000-03-01 | 6560 |  | 2002-09-30 | 2000-03-07 | 402 |  | 487 | 1 | 5.774% |  | 51.97% | [29 empty] | 240 |  | 0% |  | 49.28% | 0% | 0% | 0% | 49.28% | 0% | 8 month schedule slip includes 3 mos for a reqts change | [6 empty] | 684 | 735 | -51 | 107.5% | -7.456% | 9.825% | -12.69% | [26 empty] | 1562 | 1448 | 114 | 92.7% | 7.298% | 22.44% | 28.36% | 2000-03-01 | 2000-03-07 | 2001-05-01 | 2002-04-30 | -364 | -46.43% | -74.74% | 438 | 456 | -18 | 104.1% | -4.11% | 6.291% | -4.478% | 2000-04-15 | 2000-04-27 | 2000-08-31 | 2000-08-30 | 1 | 0.8% | 0.2053% | [20 empty] | 1747 | 1434 | 313 | 82.08% | 17.92% | 25.09% | 77.86% | 2000-06-01 | 2000-06-01 | 2000-12-01 | 2002-04-30 | -515 | -73.78% | -105.7% | 2431 | 2463 | -32 | 101.3% | -1.316% | 34.92% | -7.96% | 2000-06-01 | 2000-06-01 | 1/631/01 | 2002-09-25 |  |  |  | 100 | 24 | 76 | 24% | 76% | 1.436% | 18.91% | 2001-05-01 | 2001-05-15 | 2002-06-01 | 2002-06-30 | -29 | -7.056% | -5.955% |  | 100% | -186.2%
1 | 17 | 1 | Organic | Urgent | Small | 481.25 | 34085.94 | 2001-08-31 | 2001-06-14 | 443.5 | 31641.63 | 2001-09-04 | 2001-06-14 | 37.75 | 2444.31 | 4 |  | 7.844% | 7.171% | 4.878% | [35 empty] | 0% | 0% | 0% | 0% | [7 empty] | 25 | 17 | 8 | 68% | 32% | 5.195% | 21.19% |  |  |  |  | 13 | 5.5 | 7.5 | 42.31% | 57.69% | 2.701% | 19.87% |  |  |  |  | 10 | 8 | 2 | 80% | 20% | 2.078% | 5.298% |  |  |  |  | N/A | N/A | [5 empty] | N/A | N/A | N/A | N/A |  |  |  | 9 | 8 | 1 | 88.89% | 11.11% | 1.87% | 2.649% | 2001-06-12 | 2001-06-12 | 2001-08-30 | 2001-08-30 | 0 | 0% | 0% | [6 empty] | 28 | 23.5 | 4.5 | 83.93% | 16.07% | 5.818% | 11.92% | 2001-05-31 | 2001-05-31 | 2001-08-24 | 2001-08-24 | 0 | 0% | 0% | 21 | 28 | -7 | 133.3% | -33.33% | 4.364% | -18.54% | 2001-06-01 | 2001-06-01 | 2001-06-01 | 2001-08-24 | -84 | -100% | -2100% | 118 | 105.75 | 12.25 | 89.62% | 10.38% | 24.52% | 32.45% | 2001-08-23 | 2001-08-24 | 2001-08-30 | 2001-08-30 | 0 | 0% | 0% | 9 | 5.5 | 3.5 | 61.11% | 38.89% | 1.87% | 9.272% | 2001-08-31 | 2001-08-31 | 2001-09-04 | 2001-09-04 | 0 | 0% | 0% |  | 84.11% | -2100%
1 | 36 | 1 | Organic | Urgent | Small | 81 | 5670 | 2000-02-24 | 2000-02-22 | 2259 | 272013.88 | 2002-07-24 | 2000-02-22 | -2178 | -266343.88 | 881 | 28 | -2689% | -4697% | 99.77% | [19 empty] | 2178 | 266344 | 870 | 20 | -100% | -100% | 98.75% | 71.43% |  |  |  | 8 | -0% | -0% | 0% | 28.57% | -100% | -100% | 98.75% | 100% | sched delays due to test system delays; also, this project started out as a very small effort and unfolded into a major project due to customer priority changes. | [6 empty] | 5 | 184 | -179 | 3680% | -3580% | 6.173% | 8.219% |  |  |  |  | 5 | 120 | -115 | 2400% | -2300% | 6.173% | 5.28% |  |  |  |  | 2 | 43 | -41 | 2150% | -2050% | 2.469% | 1.882% |  |  |  |  | N/A | N/A | [5 empty] | N/A | N/A | N/A | N/A |  |  |  | 2 | 75 | -73 | 3750% | -3650% | 2.469% | 3.352% | 2000-02-18 | 2000-02-18 | 2000-02-18 | 2002-04-23 | -795 | -100% | -90.24% | [6 empty] | 2 | 1139 | -1137 | 56950% | -56850% | 2.469% | 52.2% | 2000-02-18 | 2000-02-18 | 2000-02-18 | 2001-08-10 | -539 | -100% | -61.18% | 2 | 1388 | -1386 | 69400% | -69300% | 2.469% | 63.64% | 2000-02-18 | 2001-02-12 | 2000-02-18 | 2001-09-18 | -578 | -265.1% | -65.61% | 58 | 899 | -841 | 1550% | -1450% | 71.6% | 38.61% | 2000-02-18 | 2001-08-17 | 2000-02-23 | 2002-04-12 | -779 | -327.3% | -88.42% | 5 | 9 | -4 | 180% | -80% | 6.173% | 0.1837% | 2000-02-24 | 2000-02-24 | 2002-07-16 | 2002-07-16 | 0 | 0% | 0% |  | 173.4% | -305.4%
1 | 8 | 1 | Organic | Routine | Small | 2095 | 146650 | 2000-12-29 | 1999-11-24 | 2041 | 142870 | 2001-01-31 | 1999-11-24 | 54 | 3780 | 21 | 0 | 2.578% | 2.578% | 4.839% | [31 empty] | 0% | 0% |  |  | 0% | 0% | 0% | 0% | did better than predicted | [6 empty] | 196 | 140 | 56 | 71.43% | 28.57% | 9.356% | 103.7% |  |  |  |  | 39 | 69 | -30 | 176.9% | -76.92% | 1.862% | -55.56% |  |  |  |  | 276 | 157 | 119 | 56.88% | 43.12% | 13.17% | 220.4% |  |  |  |  | 37 | 37 | 0 | 100% | 0% | 1.766% | 0% | 1999-11-24 | 1999-11-24 | 1999-11-24 | 1999-11-24 | 0 |  | 0% | 646 | 620 | 26 | 95.98% | 4.025% | 30.84% | 48.15% | 1999-12-06 | 1999-12-06 | 2000-03-21 | 2000-03-16 | 5 | 4.95% | 23.81% | 901 | 1018 | 2000-04-20 | 2000-03-17 | 2000-12-29 | 2001-01-31 | 32 | 26 | 6 | 81.25% | 18.75% | 1.527% | 11.11% | 2000-04-20 | 2000-03-17 | 2000-04-27 | 2000-03-24 | 34 | 485.7% | 161.9% | 829 | 969 | -140 | 116.9% | -16.89% | 39.57% | -259.3% | 2000-04-28 | 2000-03-17 | 2000-12-29 | 2001-01-31 | -33 | -10.31% | -157.1% | 40 | 23 | 17 | 57.5% | 42.5% | 1.909% | 31.48% | 2000-09-25 | 2000-09-18 | 2000-11-30 | 2001-01-03 | -34 | -31.78% | -161.9% | Included in CM Management | [14 empty] | 100% | -133.3%
1 | 29 | 1 | Hybrid | Routine | Standard | 73103 | 10118000 | 2001-09-01 | 1997-08-01 | 74010 | 10480000 | 2002-02-02 | 1997-08-01 | -907 | -362000 | 154 | 0 | -1.241% | -3.578% | 9.356% | [29 empty] | 180 | 0 | -0% | -0% | 116.9% |  | 0% | 0% | 116.9% | 0% | [7 empty] | 2792 | 2680 | 112 | 95.99% | 4.011% | 3.819% | -12.35% |  |  |  |  | 724 | 495 | 229 | 68.37% | 31.63% | 0.9904% | -25.25% | [29 empty] | 1040 | 978 | 62 | 94.04% | 5.962% | 1.423% | -6.836% | 1997-08-01 | 1997-08-01 | 1998-05-15 | 1998-05-01 | 14 | 5.128% | 9.091% | [6 empty] | 8508 | 8700 | -192 | 102.3% | -2.257% | 11.64% | 21.17% | 1997-08-01 | 1997-08-01 | 1999-08-01 | 1999-08-01 | 0 | 0% | 0% | 3190 | 3680 | -490 | 115.4% | -15.36% | 4.364% | 54.02% | 1998-08-01 | 1998-08-01 | 1999-08-01 | 1999-12-01 | -122 | -25.05% | -79.22% | 15560 | 13004 | 2556 | 83.57% | 16.43% | 21.29% | -281.8% | 1998-10-01 | 1998-10-01 | 2001-05-01 | 2001-12-01 | -214 | -18.5% | -139% | 1214 | 692 | 522 | 57% | 43% | 1.661% | -57.55% | 1998-10-01 | 2001-12-01 | 2001-09-01 | [5 empty] | -308.6% | -209.1%
1 | 4 | 1 | Hybrid | Routine | Small | 2610 | 245000 | 1999-10-29 | 1998-09-18 | 2003 | 199000 | 2000-10-30 | 1998-09-18 | 607 | 46000 | 367 | 2 | 23.26% | 18.78% | 47.48% | [27 empty] | 0 | 0 | 365 | 2 | 0% | 0% | 99.46% | 100% | 0% | 0% | 99.46% | 100% | [7 empty] | 60 | 90.5 | -30.5 | 150.8% | -50.83% | 2.299% | -5.025% |  |  |  |  | 90 | 15.75 | 74.25 | 17.5% | 82.5% | 3.448% | 12.23% | [29 empty] | 315 | 285 | 30 | 90.48% | 9.524% | 12.07% | 4.942% | 1998-09-18 | 1998-09-18 | 1998-11-12 | 1998-11-12 | 0 | 0% | 0% | [6 empty] | 300 | 271 | 29 | 90.33% | 9.667% | 11.49% | 4.778% | 1998-11-18 | 1998-11-22 | 1999-01-06 | 1999-01-31 | -25 | -35.71% | -6.812% | 150 | 102 | 48 | 68% | 32% | 5.747% | 7.908% | 1998-11-18 | 1998-11-22 | 1999-01-06 | 1999-02-28 | -53 | -54.08% | -14.44% | 495 | 327 | 168 | 66.06% | 33.94% | 18.97% | 27.68% | 1998-11-18 | 1999-01-01 | 1999-08-27 | 2000-09-01 | -371 | -60.92% | -101.1% | 30 | 163.5 | -133.5 | 545% | -445% | 1.149% | -21.99% | 1999-09-06 | 1999-10-19 | 2000-09-01 | 2000-09-30 | -29 | -8.357% | -7.902% |  | 30.52% | -130.2%
1 | 12 | 1 | Organic | Routine | Small | 2227 | 162571 | 2001-06-30 |  | 1638 | 119574 | 2001-06-30 | 2000-03-03 | 589 | 42997 | 0 | 0 | 26.45% | 26.45% | 0% | [35 empty] | 0% | 0% | 0% | 0% | [7 empty] | 359 | 168 | 191 | 46.8% | 53.2% | 16.12% | 32.43% |  |  |  |  | 36 | 36 | 0 | 100% | 0% | 1.617% | 0% |  |  |  |  | 24 | 24 | 0 | 100% | 0% | 1.078% | 0% |  |  |  |  | 12 | 12 | 0 | 100% | 0% | 0.5388% | 0% | 2000-03-01 | 2000-03-01 | 2000-03-30 | 2000-03-30 | 0 | 0% |  | 184 | 184 | 0 | 100% | 0% | 8.262% | 0% | 2000-03-01 | 2000-03-01 | 2000-03-30 | 2000-03-30 | 0 | 0% | [7 empty] | 60 | 40 | 20 | 66.67% | 33.33% | 2.694% | 3.396% | 2000-04-01 | 2000-04-01 | 2000-05-01 | 2000-05-01 | 0 | 0% |  | 520 | 453 | 67 | 87.12% | 12.88% | 23.35% | 11.38% | 2000-05-01 | 2000-05-01 | 2000-09-30 | 2000-09-20 | 10 | 7.042% |  | 120 | 154 | -34 | 128.3% | -28.33% | 5.388% | -5.772% | 2000-10-01 | 2000-11-01 | 2000-12-30 | 2001-02-10 | -42 | -41.58% |  | 32 | 26 | 6 | 81.25% | 18.75% | 1.437% | 1.019% | 2001-06-15 | 2001-06-15 | 2001-06-20 | 2001-06-20 | 0 | 0% |  |  | 42.44% | 0%
1 | 15 | 1 | Hybrid | Urgent | Small | 735 | 76500 | 2001-07-27 | 2001-05-08 | 735 | 76500 | 2001-07-27 | 2001-05-08 | 0 | 0 | 0 | 0 | 0% | 0% | 0% | [35 empty] | 0% | 0% | 0% | 0% | [7 empty] | 4 | 4 | 0 | 100% | 0% | 0.5442% | [41 empty] | 4 | 4 | 0 | 100% | 0% | 0.5442% |  | 2001-05-08 | 2001-05-08 | 2001-05-08 | 2001-05-08 | 0 | [8 empty] | 8 | 8 | 0 | 100% | 0% | 1.088% |  | 2001-05-08 | 2001-05-08 | 2001-05-17 | 2001-05-17 | 0 | 0% |  | 4 | 4 | 0 | 100% | 0% | 0.5442% |  | 2001-05-08 | 2001-05-08 | 2001-05-17 | 2001-05-17 | 0 | 0% |  | 0 | 0 | 0 |  |  |  |  | 2001-06-14 | 2001-07-15 | 2001-05-21 | 2001-07-02 | -42 | 323.1% |  | 4 | 4 | 0 | 100% | 0% | 0.5442% |  | 2001-07-31 | 2001-07-27 | 2001-07-31 | 2001-07-27 | 4 |  |  |  | 0% | 0%
1 | 41 | 1 | Organic | Urgent | Small | 886 |  | 2002-01-17 |  | 442 |  | 2002-09-30 | 2001-08-30 | 444 |  | 256 | 0 | 50.11% |  | 64.65% | 58 |  |  | 0 | 13.06% |  |  |  | 0.065463 | [10 empty] | 286 |  | 252 | 0 | 64.41% |  | 98.44% |  |  |  | 30 | 0 | 0% |  | 11.72% |  | 77.48% | 0% | 110.2% | 0% | Note: A 286 hour reduction of scope ocurred at the very end of the project. There was no rebaseline because there was no remaining work to be planned. Project Management, Configuration Management, and Quality Assurance were tracked together. Total plann | [53 empty] | 64 |  |  | 0% | 100% | 7.223% | 14.41% | 2001-08-30 | 2001-08-30 | 2001-09-07 | 2001-09-14 | -7 | -46.67% | -2.734% | [13 empty] | 2001-08-30 | 2001-08-30 | [14 empty] | 2001-09-19 | 2001-10-31 | -42 | -0.1129% | -16.41% | 216 |  |  |  |  | 24.38% |  | 2001-09-10 | 2001-09-10 | 2002-01-15 | 2002-06-17 | -153 | -54.64% | -59.77% | 366 |  |  | 0% | 100% | 41.31% | 82.43% | 2001-11-05 | 2001-12-10 | 2002-01-17 | 2002-09-30 | -256 | -87.07% | -100% |  | 96.85% | -178.9%
1 | 18 | 1 | Organic | Urgent | Small | 538 |  | 2001-09-21 |  | 538 |  | 2001-09-21 | 2001-05-07 | 0 |  | 0 |  | 0% |  | 0% | [35 empty] | 0% | 0% | 0% | 0% | The final actual cost and schedule for this project are missing. The SAT for the next to last month show the project within 2% of cost and schedule, so am assuming the project completed on cost and schedule. Project Management, Configuration Management | [53 empty] | 64 |  |  | 0% | 100% | 11.9% |  | 2001-05-07 | 2001-05-07 | 2001-07-31 | 2001-08-10 | -10 | -10.53% | [14 empty] | 2001-05-07 | 2001-05-07 | [19 empty] | 216 |  |  |  |  | 40.15% |  | 2001-05-21 | 2001-05-21 | 2001-08-31 | 2001-08-28 | 3 | 3.03% |  | 122 |  |  | 0% | 100% | 22.68% |  | 2001-08-31 | 2001-08-31 | 2001-09-21 | 2001-09-21 | 0 | 0% |  |  | 0% | 0%
1 | 32 | 1 | Organic | Routine | Standard | 8978 | 589010 | 2000-10-15 |  | 11370 | 739910 | 2002-04-23 | 1998-08-01 | -2392 | -150900 | 555 | 0 | -26.64% | -25.62% | 40.78% | 2062 | 134030 | 308 | 0 | -86.2% | -88.82% | 55.5% |  | 0.22967 | 0.22755 | 0.2263 | [16 empty] | 330 | 21450 | 270 | 0 | -13.8% | -14.21% | 48.65% |  | -100% | -103% | 104.1% | 0% | [7 empty] | 252 | 511 | -259 | 202.8% | -102.8% | 2.807% | 10.83% |  |  |  |  | 170 | 67 | 103 | 39.41% | 60.59% | 1.894% | -4.306% |  |  |  |  | n/a | n/a | [9 empty] | n/a | n/a | [5 empty] | n/a | n/a | n/a | n/a |  |  |  | 1228 | 1134 | 94 | 92.35% | 7.655% | 13.68% | -3.93% | 1998-09-01 | 1998-09-01 | 1999-06-15 | 1999-06-15 | 0 | 0% | 0% | [6 empty] | 1212 | 1727 | -515 | 142.5% | -42.49% | 13.5% | 21.53% | 1999-01-01 | 1999-01-01 | 2000-02-28 | 2000-03-10 | -11 | -2.535% | -1.982% | 2384 | 3168 | -784 | 132.9% | -32.89% | 26.55% | 32.78% | 1999-08-01 | 1999-08-01 | 2000-05-31 | 2000-10-31 | -153 | -33.48% | -27.57% | 672 | 1544 | -872 | 229.8% | -129.8% | 7.485% | 36.45% | 2000-06-01 | 2000-11-01 | 2000-08-10 | 2001-06-01 | -295 | -139.2% | -53.15% | 32 | 60 | -28 | 187.5% | -87.5% | 0.3564% | 1.171% | 2000-10-28 | 2000-10-31 | 2002-04-23 | 2002-04-26 | -3 | -0.5535% | -0.5405% |  | 94.52% | -83.24%
1 | 1 | 1 | Hybrid | Routine | Small | 2313 | 178101 | 2000-02-28 |  | 4198 | 426906 | 2000-05-31 | 1999-11-22 | -1885 | -248805 | 93 | 1 | -81.5% | -139.7% | 48.69% | 465 | 35000 | 120 | 1 | -24.67% | -14.07% |  | 100% | 0.20104 | 0.19652 | 0.62827 | 1420 | 213000 | 120 |  | -75.33% | -85.61% | [18 empty] | -100% | -99.68% | 0% | 100% | [7 empty] | 331 | 504 | -173 | 152.3% | -52.27% | 14.31% | 9.178% | [15 empty] | 120 | 120 | 0 | 100% | 0% | 5.188% | -0% | [18 empty] | 281 | 289 | -8 | 102.8% | -2.847% | 12.15% | 0.4244% | 1999-11-11 | 1999-11-11 | 2001-02-28 | 2001-05-31 | -92 | -16.23% | -98.92% | [6 empty] | 600 | 600 | 0 | 100% | 0% | 25.94% | -0% | 2000-02-18 | 2000-02-18 | 2000-02-18 | 2000-02-18 | 0 |  | 0% | 681 | 681 | 0 | 100% | 0% | 29.44% | -0% | 2000-09-15 | 2000-09-15 | 2001-01-16 | 2001-01-16 | 0 | 0% | 0% | 180 | 1884 | -1704 | 1047% | -946.7% | 7.782% | 90.4% | 2001-01-16 | 2001-01-16 | 2001-04-16 | 2001-04-16 | 0 | 0% | 0% | 120 | 120 | 0 | 100% | 0% | 5.188% | -0% | 2001-04-16 | 2001-04-16 | 2001-05-28 | 2001-05-28 | 0 | 0% | 0% |  | 100% | -98.92%
2 | 19 | 1 |  |  |  | 35314 | 2335751.5628 | 37165 |  | 34713 | 2296000 | 2001-10-01 |  | 601 | 39751.5628 | 0 |  | 1.702% | 1.702% | 0% | [35 empty] | 0% | 0% | 0% | 0% | [131 empty] | 0% | 0%
2 | 6 | 1 |  |  |  | 17428 | 1235993 | 2000-12-01 |  | 10614 | 752745 | 2000-12-01 |  | 6814 | 483248 | 0 |  | 39.1% | 39.1% | 0% | [35 empty] | 0% | 0% | 0% | 0% | [131 empty] | 0% | 0%
2 | 3 | 1 |  |  |  | 11535 | 818159 | 2000-07-01 |  | 11138 | 790000 | 2000-07-01 |  | 397 | 28159 | 0 |  | 3.442% | 3.442% | 0% | [35 empty] | 0% | 0% | 0% | 0% | [131 empty] | 0% | 0%
2 | 2 | 1 |  |  |  | 7783 | 551970 | 2000-06-01 |  | 7145 | 506723 | 2000-06-01 |  | 638 | 45247 | 0 |  | 8.197% | 8.197% | 0% | [35 empty] | 0% | 0% | 0% | 0% | [131 empty] | 0% | 0%
6 | 35 | 1 |  |  |  | 13378 | 829436 | 2002-03-15 |  | 19443 | 1205466 | 2002-05-15 | 1999-05-01 | -6065 | -376030 | 61 |  | -45.34% | -45.34% | 5.495% | [35 empty] | 0% | 0% | 0% | 0% | [131 empty] | 0% | 0%
6 | 33 | 1 |  |  |  | 18278 | 1133236 | 2002-06-01 |  | 11942 | 740404 | 2002-05-01 | 2001-06-01 | 6336 | 392832 | -31 |  | 34.66% | 34.66% | -9.281% | [35 empty] | 0% | 0% | 0% | 0% | [131 empty] | 0% | 0%
6 | 34 | 1 |  |  |  | 671 | 45809.17 | 2001-12-02 |  | 368 | 25123.36 | 2002-05-12 | 2001-09-02 | 303 | 20685.81 | 161 | 0 | 45.16% | 45.16% | 63.89% | na | na |  | 0 | [7 empty] | 0 | 0 | 0 | 0 | 0% | 0% | 0% |  | 0 | 0 | 0 | 0 | 0% | 0% | 0% |  | 0 | 0 | 0 | 0 | 0% | 0% | 0% |  | 0% | 0% | 0% | 0% | also showed data for documentation and mgmt reserve -- not clear if that was a subset of execution categories or not | [6 empty] | 0 | 8 | -8 |  |  | 0% | -2.64% |  |  |  |  | 0 | 5 | -5 |  |  | 0% | -1.65% |  |  |  |  | 0 | 4 | -4 |  |  | 0% | -1.32% |  |  |  |  | 0 | 0 | 0 |  |  |  |  | NA | NA | NA | NA |  |  |  | 40 | 10 | 30 | 25% | 75% | 5.961% | 9.901% | 2001-09-02 | 2001-09-02 | 2001-09-07 | 2001-09-06 | 1 | 25% | 0.6211% | [6 empty] | 30 | 28 | 2 | 93.33% | 6.667% | 4.471% | 0.6601% | 2001-09-10 | 2001-09-10 | 2001-09-14 | 2001-09-18 | -4 | -50% | -2.484% | 30 | 54 | -24 | 180% | -80% | 4.471% | -7.921% | 2001-09-17 | 2001-09-24 | 2001-09-21 | 2001-10-05 | -14 | -127.3% | -8.696% | 340 | 150 | 190 | 44.12% | 55.88% | 50.67% | 62.71% | 2001-09-24 | 2001-10-08 | 2001-11-19 | 2001-12-10 | -21 | -33.33% | -13.04% | 0 | 8 | -8 |  |  | 0% | -2.64% | 2001-11-29 | 2002-05-05 | 2001-12-02 | 2002-05-12 | -161 | -2300% | -100% |  | 57.1% | -123.6%
6 | 16 | 1 |  |  |  | 8000 | 560000 | 2001-07-31 |  | 8931 | 625170 | 2001-08-09 | 2000-12-11 | -931 | -65170 | 9 |  | -11.64% | -11.64% | 3.734% | [19 empty] | 150 | 10500 |  |  | -16.11% | -16.11% | 0% | [9 empty] | -16.11% | -16.11% | 0% | 0% | [7 empty] | 1061 | 763 | 298 | 71.91% | 28.09% | 13.26% | -32.01% |  |  |  |  | 457 | 452 | 5 | 98.91% | 1.094% | 5.713% | -0.5371% | [29 empty] | 2367 | 2910 | -543 | 122.9% | -22.94% | 29.59% | 58.32% | [14 empty] | 26 | -26 |  |  | 0% | 2.793% | [7 empty] | 1190 | 638 | 552 | 53.61% | 46.39% | 14.88% | -59.29% | 2001-01-16 |  | 2001-04-02 |  |  |  |  | 1701 | 3224 | -1523 | 189.5% | -89.54% | 21.26% | 163.6% | 2001-04-11 |  | 2001-07-12 |  |  |  |  | 1225 | 918 | 307 | 74.94% | 25.06% | 15.31% | -32.98% |  |  | 2001-07-31 | 2001-08-09 | -9 | -0.02425% | -100% |  | 99.89% | -100%
6 | 42 | 1 |  |  |  | 6495 | 519600 | 2002-08-31 |  | 6665 | 533200 | 2002-09-30 | 2001-08-20 | -170 | -13600 | 30 |  | -2.617% | -2.617% | 7.389% | [35 empty] | 0% | 0% | 0% | 0% | [7 empty] | 2201 | 952 | 1249 | 43.25% | 56.75% | 33.89% | -734.7% |  |  |  |  | 366 | 356 | 10 | 97.27% | 2.732% | 5.635% | -5.882% | [49 empty] | 221 | 142 | 79 | 64.25% | 35.75% | 3.403% | -46.47% | [7 empty] | 1263 | 1468 |  | 116.2% | -16.23% | 19.45% | 120.6% | [7 empty] | 2444 | 3747 | -1303 | 153.3% | -53.31% | 37.63% | 766.5% | [22 empty] | 100% | 0%
5 | 39 | 3 |  |  |  | 1484 |  | 2003-05-16 | 2002-02-25 | 843 |  | 2002-09-20 | 2002-03-18 | 641 |  | -238 |  | 43.19% |  | -128% | [35 empty] | 0% | 0% | 0% | 0% | [131 empty] | 0% | 0%
5 | 30 | 3 |  |  |  | 1632 |  | 2002-08-20 | 2001-06-27 | 1433 |  | 2002-04-09 | 2001-06-27 | 199 |  | -133 |  | 12.19% |  | -46.5% | [35 empty] | 0% | 0% | 0% | 0% |  | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  | 0% | 0% | [15 empty] | 0 | 0 | 0 |  |  | 0% | 0% | [32 empty] | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  | 0% | 0% | [7 empty] | 0 | 0 | 0 |  |  | 0% | 0% | [7 empty] | 16 | 13 | 3 | 81.25% | 18.75% | 0.9804% | 1.508% | [22 empty] | 1.508% | 0%
5 | 13 | 2 |  |  |  | 254590 | 21702886 | 1997-09-30 |  | 274020 | 21778295 | 2001-06-30 | 1993-10-01 | -19430 | -75409 | 1369 | 5 | -7.632% | -0.3475% | 48.39% |  | 997371 | 180 | 2 |  | -1323% | 13.15% | 40% |  | 0.045956 | 0.063627 | [9 empty] | -921962 |  | 3 | -0% | 1223% | 0% | 60% |  |  | 1275 | 3 | -0% | -0% | 93.13% | 60% | 0% | -100% | 106.3% | 160% |  | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  | 0% | -0% | [15 empty] | 0 | 0 | 0 |  |  | 0% | -0% | [32 empty] | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  |  | 0% | -0% | [7 empty] | 0 | 0 | 0 |  |  | 0% | -0% | [7 empty] | 8 | 13 | -5 | 162.5% | -62.5% | 0.003142% | 0.02573% | [22 empty] | 0.02573% | 0%
[18 empty] | % effort var | % cost var | % sched variance | [119 empty] | -170
[15 empty] | avg | 154.9048 |  | -66.07% | -173.1% | 14.97% |  |  |  | avg | -40.98% | -202.4% | 26.25% | 34.67% | 14.84% | 14.47% | 24.53% |  |  |  | avg | -19.46% | -22.03% | 36.89% | #DIV/0! |  |  |  | avg | -35.92% | 106.8% | 43.22% | 57.62% |  |  |  | avg | -6.916% | -9.469% | 73.64% | 58.14% | -19.71% | -17.97% | 41.97% | 26.2% | [8 empty] | avg |  | 2.3387 | -133.9% | 13.29% | 7.643% | [5 empty] | avg |  | 244.4% | -144.4% | 7.229% | -38.46% | [5 empty] | avg |  | 380.2% | -280.2% | 4.225% | 21.67% | [5 empty] | avg |  | 97.57% | 2.433% | 6.185% | 7.09% |  |  |  | avg | -121.3333 | -23.21% | -37.37% |  | avg |  | 284.5% | -184.5% | 8.639% | 19.89% |  |  |  | avg | -183.65 | -27.14% | -103.2% | [7 empty] | avg |  | 2689% | -2589% | 17.39% | 51.15% |  |  |  | avg | -82.5238 | -5.084% | -58.25% |  | avg |  | 2783% | -2683% | 20.5% | 41.39% |  |  |  | avg | -181.2 | -56.13% | -185.6% |  | avg |  | 211.2% | -111.2% | 20.69% | 68.55% |  |  |  | avg | -138.8889 | -57.01% | -79.1% |  | avg |  | 126.6% | -26.56% | 6.002% | 1.095% |  |  |  | avg | -58 | -143% | -33.16% | avg | 104.8% | -233.3%
[15 empty] | std dev | 284.9478 |  | 415.9% | 887.5% | 38.29% |  |  |  | std dev | 39.79% | 497.3% | 25.37% | 40.93% | 9.683% | 9.903% | 26.67% |  |  |  | std dev | 37.27% | 42.4% | 52.16% | #DIV/0! |  |  |  | std dev | 55.36% | 453.4% | 48.7% | 42.39% |  |  |  | std dev | 15.97% | 18.2% | 39.87% | 40.75% | 43.58% | 45.55% | 50.01% | 46.06% | [8 empty] | std dev |  | 7.0468 | 704.7% | 11.15% | 188.5% | [5 empty] | std dev |  | 559.3% | 559.3% | 8.021% | 174.7% | [5 empty] | std dev |  | 780.5% | 780.5% | 5.453% | 65.96% | [5 empty] | std dev |  | 4.214% | 4.214% | 10.86% | 14.18% |  |  |  | std dev | 210.1555 | 32.83% | 52.85% |  | std dev |  | 780.7% | 780.7% | 8.167% | 53.18% |  |  |  | std dev | 389.1378 | 40.86% | 242.1% | [7 empty] | std dev |  | 12119% | 12119% | 18.96% | 151.5% |  |  |  | std dev | 155.8405 | 122.7% | 172.9% |  | std dev |  | 13587% | 13587% | 14.47% | 135.9% |  |  |  | std dev | 265.6222 | 101.6% | 428.7% |  | std dev |  | 327.2% | 327.2% | 20.08% | 196.5% |  |  |  | std dev | 219.2746 | 134% | 93.44% |  | std dev |  | 146.1% | 146.1% | 9.869% | 26.99% |  |  |  | std dev | 142.775 | 485.2% | 49% | std dev | 327.2% | 395.9%
[15 empty] | median | 45.5 |  | 0.8509% | 0.3603% | 8.122% |  |  |  | median | -30.83% | -30.83% | 13.15% | 33.33% | 19.87% | 19.65% | 14.5% |  |  |  | median | -1.251% | -1.251% | 36.89% | #VALUE! |  |  |  | median | -22.48% | -22.48% | 20.2% | 65.71% |  |  |  | median | -0% | 0% | 96.68% | 55% | 0% | 0% | 0% | 0% | [8 empty] | median |  | 0.92371 | 7.629% | 9.825% | 3.238% | [5 empty] | median |  | 100% | 0% | 5.674% | -0.2685% | [5 empty] | median |  | 87.27% | 12.73% | 2.078% | -0% | [5 empty] | median |  | 100% | 0% | 1.152% | 0% |  |  |  | median | 0 | -23.21% | -37.37% |  | median |  | 100% | 0% | 6.31% | 3% |  |  |  | median | 0 | 0% | 0% | [7 empty] | median |  | 96.67% | 3.333% | 11.64% | 15.13% |  |  |  | median | -11 | -10.68% | -6.812% |  | median |  | 114.9% | -14.86% | 21.8% | 24.44% |  |  |  | median | -42 | -25.05% | -83.33% |  | median |  | 118% | -18.03% | 11.62% | 24.83% |  |  |  | median | -42 | -33.33% | -67.7% |  | median |  | 88.31% | 11.69% | 1.661% | -0% |  |  |  | median | -0.5 | 0% | -0.5405% | median | 87.87% | -99.46%
[15 empty] | min | -238 |  | -2689% | -4697% | -128% |  |  |  | min | -100% | -1323% | 10.1% | 0% | 0.6694% | 0.7207% | 6.283% |  |  |  | min | -75.33% | -85.61% | 0% | 0% |  |  |  | min | -100% | -120.5% | 0% | 0% |  |  |  | min | -50.05% | -50.05% | 0% | 0% | -100% | -120.5% | 0% | 0% | [8 empty] | min |  | 0.32 | -3580% | 0% | -734.7% | [5 empty] | min |  | 17.5% | -2300% | 0% | -732.2% | [5 empty] | min |  | 56.88% | -2050% | 0% | -1.32% | [5 empty] | min |  | 92.7% | 0% | 0% | -0% |  |  |  | min | -364 | -46.43% | -74.74% |  | min |  | 0% | -3650% | 0.5442% | -12.5% |  |  |  | min | -1194 | -100% | -746.2% | [7 empty] | min |  | 31.74% | -56850% | 0% | -46.47% |  |  |  | min | -539 | -161.6% | -716.7% |  | min |  | 53.61% | -69300% | 0% | -259.3% |  |  |  | min | -853 | -432.1% | -2100% |  | min |  | 44.12% | -1450% | 0.003142% | -281.8% |  |  |  | min | -823 | -460.7% | -350% |  | min |  | 0% | -445% | 0% | -57.55% |  |  |  | min | -652 | -2300% | -116.7% | min | -308.6% | -2100%
[15 empty] | max | 1369 |  | 50.11% | 45.16% | 99.77% |  |  |  | max | 13.06% | 100% | 55.5% | 100% | 25.95% | 25.95% | 62.83% |  |  |  | max | -0% | 0% | 73.77% | 0% |  |  |  | max | 64.41% | 1223% | 100% | 100% |  |  |  | max | -0% | -0% | 116.9% | 100% | 77.48% | 100% | 116.9% | 160% | [8 empty] | max |  | 36.8 | 68% | 37.3% | 617.9% | [5 empty] | max |  | 2400% | 82.5% | 35.45% | 44.53% | [5 empty] | max |  | 2150% | 43.12% | 15.04% | 220.4% | [5 empty] | max |  | 100% | 7.298% | 22.44% | 28.36% |  |  |  | max | 0 | 0% | 0% |  | max |  | 3750% | 100% | 30.84% | 231% |  |  |  | max | 14 | 25% | 23.81% | [7 empty] | max |  | 56950% | 68.26% | 74.57% | 743.2% |  |  |  | max | 34 | 485.7% | 161.9% |  | max |  | 69400% | 46.39% | 52.74% | 627.1% |  |  |  | max | 10 | 100% | 16.67% |  | max |  | 1550% | 55.88% | 71.6% | 766.5% |  |  |  | max | 46 | 323.1% | 116.7% |  | max |  | 545% | 100% | 41.31% | 82.43% |  |  |  | max | 4 | 16.67% | 16.67% | max | 2114% | 33.33%
[15 empty] | n | 42 |  | 42 | 28 | 42 |  |  |  | n | 7 | 7 | 3 | 5 | 7 | 7 | 4 |  |  |  | n | 4 | 4 | 2 | 0 |  |  |  | n | 10 | 8 | 10 | 6 |  |  |  | n | 15 | 11 | 16 | 10 | 42 | 42 | 42 | 42 | [8 empty] | n |  | 26 | 26 | 29 | 28 | [5 empty] | n |  | 17 | 17 | 18 | 18 | [5 empty] | n |  | 7 | 7 | 11 | 11 | [5 empty] | n |  | 3 | 3 | 4 | 4 |  |  |  | n | 3 | 2 | 2 |  | n |  | 22 | 22 | 22 | 20 |  |  |  | n | 20 | 19 | 17 | [7 empty] | n |  | 22 | 22 | 25 | 24 |  |  |  | n | 21 | 20 | 19 |  | n |  | 26 | 26 | 28 | 27 |  |  |  | n | 25 | 25 | 23 |  | n |  | 27 | 27 | 29 | 27 |  |  |  | n | 27 | 27 | 24 |  | n |  | 19 | 19 | 21 | 19 |  |  |  | n | 24 | 23 | 21 | n | 42 | 42
excluding project on row 27
[15 empty] | avg |  |  | -2.101% | -5.578% | 12.9%
[15 empty] | std dev |  |  | 32.91% | 38.54% | 36.31%
[15 empty] | median |  |  | 1.702% | 0.7207% | 7.389%
[15 empty] | min |  |  | -94.9% | -139.7% | -128%
[15 empty] | max |  |  | 50.11% | 45.16% | 70.83%
Note on H37: Jeannine M. Siviy: this was back calculated
Note on O6: Jeannine M. Siviy:( initial - actual)
Note on Q28: Jeannine M. Siviy: typed in <3 wks
Note on S6: Jeannine M. Siviy: initial - actual)/ initial
Note on S49: Jeannine M. Siviy: initial - actual)/ initial
Note on U6: Jeannine M. Siviy: % of actual duration (because planned duration not available for all projects)
Note on U49: Jeannine M. Siviy: % of actual duration (because planned duration not available for all projects)
Note on V5: Jeannine M. Siviy: missing data implied no contribution to variance if another category is present; if all categories missing, then data is not available also note… review raw data -- things don't always sum up to 100%
Note on V7: Jeannine M. Siviy: implied: no contribution to variance (see 'eternal' contributions)
Note on W7: Jeannine M. Siviy: implied: no contribution to variance (see 'eternal' contributions)
Note on X7: Jeannine M. Siviy: implied: no contribution to variance (see 'eternal' contributions)
Note on Y7: Jeannine M. Siviy: no rebaselines done
Note on Z5: Jeannine M. Siviy: review raw data -- things don't always sum up to 100%
Note on AY25: Jeannine M. Siviy: 8 mos = 8*30??
Note on BP47: Paul.Beard: The project and configuration management tasks hrs were collected under our normal sustainment project
Note on BP48: Paul.Beard: The project and configuration management tasks hrs were collected under our normal sustainment project
Note on BQ43: Jeannine M. Siviy: see comments
Note on BQ47: Paul.Beard: The project and configuration management tasks hrs were collected under our normal sustainment project
Note on BQ48: Paul.Beard: The project and configuration management tasks hrs were collected under our normal sustainment project
Note on ES45: Chandra Emanuel: Includes Code and integration, Documentation and training
Note on ET45: Chandra Emanuel: Includes code and integration, documentation and training
Note on FG45: Chandra Emanuel: Includes procedures, baseline testing rehost, unique testing, regression testing
Note on FH45: Chandra Emanuel: Includes procedures, baseline test rehosting, unique testing and regression testing
Note on FP25: Jeannine M. Siviy: this was typed into original spreadsheet; not sure whether 1/6/01 or 6/31/01 (or something else) is correct
Note on GC16: Jeannine M. Siviy: swapped 2 fields - appears that planned completion date was typed in actual start field and that actual start was typed in planned completion
Note on GC17: Jeannine M. Siviy: swapped 2 fields - appears that planned completion date was typed in actual start field and that actual start was typed in planned completion
Note on GC19: Jeannine M. Siviy: swapped 2 fields - appears that planned completion date was typed in actual start field and that actual start was typed in planned completion
Note on GC20: Jeannine M. Siviy: swapped 2 fields - appears that planned completion date was typed in actual start field and that actual start was typed in planned completion
Note on GC21: Jeannine M. Siviy: swapped 2 fields - appears that planned completion date was typed in actual start field and that actual start was typed in planned completion
Note on GC22: Jeannine M. Siviy: swapped 2 fields - appears that planned completion date was typed in actual start field and that actual start was typed in planned completion
Note on GC23: Jeannine M. Siviy: swapped 2 fields - appears that planned completion date was typed in actual start field and that actual start was typed in planned completion
Note on GC24: Jeannine M. Siviy: swapped 2 fields - appears that planned completion date was typed in actual start field and that actual start was typed in planned completion
Note on GC25: Jeannine M. Siviy: swapped 2 fields - appears that planned completion date was typed in actual start field and that actual start was typed in planned completion
Note on GC26: Jeannine M. Siviy: swapped 2 fields - appears that planned completion date was typed in actual start field and that actual start was typed in planned completion
Note on GC27: Jeannine M. Siviy: swapped 2 fields - appears that planned completion date was typed in actual start field and that actual start was typed in planned completion
Note on GC29: Jeannine M. Siviy: swapped 2 fields - appears that planned completion date was typed in actual start field and that actual start was typed in planned completion
Note on GC30: Jeannine M. Siviy: swapped 2 fields - appears that planned completion date was typed in actual start field and that actual start was typed in planned completion
Note on GC31: Jeannine M. Siviy: swapped 2 fields - appears that planned completion date was typed in actual start field and that actual start was typed in planned completion
Note on GC32: Jeannine M. Siviy: swapped 2 fields - appears that planned completion date was typed in actual start field and that actual start was typed in planned completion
Note on GC35: Jeannine M. Siviy: swapped 2 fields - appears that planned completion date was typed in actual start field and that actual start was typed in planned completion
Note on GD16: Jeannine M. Siviy: swapped 2 fields - appears that planned completion date was typed in actual start field and that actual start was typed in planned completion
Note on GD17: Jeannine M. Siviy: swapped 2 fields - appears that planned completion date was typed in actual start field and that actual start was typed in planned completion
Note on GD19: Jeannine M. Siviy: swapped 2 fields - appears that planned completion date was typed in actual start field and that actual start was typed in planned completion
Note on GD20: Jeannine M. Siviy: swapped 2 fields - appears that planned completion date was typed in actual start field and that actual start was typed in planned completion
Note on GD21: Jeannine M. Siviy: swapped 2 fields - appears that planned completion date was typed in actual start field and that actual start was typed in planned completion
Note on GD22: Jeannine M. Siviy: swapped 2 fields - appears that planned completion date was typed in actual start field and that actual start was typed in planned completion
Note on GD23: Jeannine M. Siviy: swapped 2 fields - appears that planned completion date was typed in actual start field and that actual start was typed in planned completion
Note on GD24: Jeannine M. Siviy: swapped 2 fields - appears that planned completion date was typed in actual start field and that actual start was typed in planned completion
Note on GD25: Jeannine M. Siviy: swapped 2 fields - appears that planned completion date was typed in actual start field and that actual start was typed in planned completion
Note on GD26: Jeannine M. Siviy: swapped 2 fields - appears that planned completion date was typed in actual start field and that actual start was typed in planned completion
Note on GD27: Jeannine M. Siviy: swapped 2 fields - appears that planned completion date was typed in actual start field and that actual start was typed in planned completion
Note on GD29: Jeannine M. Siviy: swapped 2 fields - appears that planned completion date was typed in actual start field and that actual start was typed in planned completion
Note on GD30: Jeannine M. Siviy: swapped 2 fields - appears that planned completion date was typed in actual start field and that actual start was typed in planned completion
Note on GD31: Jeannine M. Siviy: swapped 2 fields - appears that planned completion date was typed in actual start field and that actual start was typed in planned completion
Note on GD32: Jeannine M. Siviy: swapped 2 fields - appears that planned completion date was typed in actual start field and that actual start was typed in planned completion
Note on GD35: Jeannine M. Siviy: swapped 2 fields - appears that planned completion date was typed in actual start field and that actual start was typed in planned completion
blank cell = missing data (crosscheck for any n/a's that were typed in)
pink=calculated on data collection spreadsheet and copied here;
light gray = intended as "no data entry" field in data collection spreadsheet, but some folks typed in information
dark gray= intended as a rollup in data collection spreadsheet, but some folks typed numbers in directly....
blue=calculated here
pink or blue with no data=calculation not available due to missing value or divide by zero (used this to replace both pink and blue cells whose calculations were on "missing" or "div0" data
Notes:
*these are the same charts, with the yscale adjusted.
*need to discuss the "outlier"
*need to replot in time order -- there seems to be a very slight upward trend here, but these aren't in time order
*see next 6 tabs for example control charts (using qi macros) (3 tabs following this are for schedule variance