Analysis 1, Cost Schedule Case

Exploration Exercise, Key

Following are a selection of statistics and charts that may be part of a baseline summary.  This is not intended to be exhaustive.

Bottom line:  There are some statistical differences between different groups, with all groups exhibiting much more variability than is desired.  Practically speaking, the group differences that stand out the most are the project to project differences.  This needs to be understood better.

Data File:  A1C3E2_Explore-ClosedProjectCategories.xls

- See case study, as the data set closely reflects the actual case

Data File: A1C3E1-2_Baseline-Explore-MonthlyData.MTW

Boxplots, as practical (quick) visual indicators of how the groups compare

- These give a view of “median” (not “average”) data and are reflective of “where the eye tends to go” in the distribution

- Cost charts’ y axis rescaled  (outliers not removed; although you may wish to remove them)

One-way ANOVA: %sch var versus org unit

  With this analysis, we see that org unit 5’s mean is statistically different than the other means.  However, the the large standard deviation and the low r-squared contribute (in combination with the median-based boxplots) contribute to a practical interpretation that all the groups are “running in the same pack” in terms of having variability issues that need to be addressed as a top priority.

Source     DF      SS    MS      F      P

org unit    2   15757  7878  21.12  0.000

Error     696  259657   373

Total     698  275414

S = 19.32   R-Sq = 5.72%   R-Sq(adj) = 5.45%

Individual 95% CIs For Mean Based on

Pooled StDev

Level    N    Mean  StDev  ------+---------+---------+---------+---

1      344   -5.02  11.90                        (---*---)

5      189  -15.00  31.69  (-----*-----)

6      166   -3.22  11.62                          (-----*----)

------+---------+---------+---------+---

-15.0     -10.0      -5.0       0.0

Pooled StDev = 19.32

Tukey 95% Simultaneous Confidence Intervals

All Pairwise Comparisons among Levels of org unit

Individual confidence level = 98.05%

org unit = 1 subtracted from:

org

unit   Lower  Center  Upper  -------+---------+---------+---------+--

5     -14.07   -9.98  -5.89     (---*---)

6      -2.47    1.80   6.07                 (---*---)

-------+---------+---------+---------+--

-10         0        10        20

org unit = 5 subtracted from:

org

unit  Lower  Center  Upper  -------+---------+---------+---------+--

6      6.97   11.78  16.59                          (----*----)

-------+---------+---------+---------+--

-10         0        10        20

ANOVA using a different stat package that provides the visual Tukey Kramer test (to parallel one of the graphs that will be shown in the lecture, and to clarify that this data set is a subset of the whole case (i.e., slightly different results in the interest of giving you practice…  )

One-way ANOVA: %sch var versus month id - date

Source            DF      SS   MS     F      P

month id - date    8    3294  412  1.04  0.401

Error            690  272120  394

Total            698  275414

S = 19.86   R-Sq = 1.20%   R-Sq(adj) = 0.05%

Individual 95% CIs For Mean Based on Pooled

StDev

Level       N    Mean  StDev     -+---------+---------+---------+--------

1: Oct 01  83   -4.60  19.21                  (--------*-------)

2: Nov 01  79   -7.30  18.63             (-------*--------)

3: Dec 01  78   -7.63  18.24            (--------*--------)

4: Jan 02  77   -9.26  21.45         (-------*--------)

5: Feb 02  79  -10.87  23.33     (--------*--------)

6: Mar 02  78   -8.78  23.35          (-------*--------)

7: Apr 02  77   -6.26  23.78               (-------*--------)

8: May 02  73   -7.51  16.02            (--------*--------)

9: Jun 02  75   -3.43  10.62                    (--------*--------)

-+---------+---------+---------+--------

-15.0     -10.0      -5.0       0.0

Pooled StDev = 19.86

Tukey 95% Simultaneous Confidence Intervals

All Pairwise Comparisons among Levels of month id - date

Individual confidence level = 99.80%

month id - date = 1: Oct 01 subtracted from:

month id

- date      Lower  Center  Upper  -------+---------+---------+---------+--

2: Nov 01  -12.39   -2.70   6.99       (--------*---------)

3: Dec 01  -12.75   -3.03   6.69      (---------*---------)

4: Jan 02  -14.41   -4.66   5.09     (--------*---------)

5: Feb 02  -15.96   -6.27   3.42   (---------*--------)

6: Mar 02  -13.90   -4.18   5.54     (---------*---------)

7: Apr 02  -11.42   -1.66   8.09        (--------*---------)

8: May 02  -12.80   -2.91   6.98      (---------*---------)

9: Jun 02   -8.65    1.17  10.99          (---------*---------)

-------+---------+---------+---------+--

-10         0        10        20

month id - date = 2: Nov 01 subtracted from:

month id

- date      Lower  Center  Upper  -------+---------+---------+---------+--

3: Dec 01  -10.17   -0.33   9.51         (---------*---------)

4: Jan 02  -11.83   -1.96   7.91       (---------*---------)

5: Feb 02  -13.38   -3.57   6.24      (--------*---------)

6: Mar 02  -11.32   -1.48   8.36        (---------*--------)

7: Apr 02   -8.84    1.03  10.91          (---------*---------)

8: May 02  -10.22   -0.21   9.80         (---------*---------)

9: Jun 02   -6.07    3.87  13.81             (---------*---------)

-------+---------+---------+---------+--

-10         0        10        20

month id - date = 3: Dec 01 subtracted from:

month id

- date      Lower  Center  Upper  -------+---------+---------+---------+--

4: Jan 02  -11.54   -1.63   8.27       (---------*---------)

5: Feb 02  -13.08   -3.24   6.60      (---------*---------)

6: Mar 02  -11.02   -1.15   8.72        (---------*---------)

7: Apr 02   -8.54    1.36  11.27          (---------*---------)

8: May 02   -9.92    0.12  10.16         (---------*---------)

9: Jun 02   -5.77    4.20  14.17             (---------*---------)

-------+---------+---------+---------+--

-10         0        10        20

month id - date = 4: Jan 02 subtracted from:

month id

- date      Lower  Center  Upper  -------+---------+---------+---------+--

5: Feb 02  -11.48   -1.61   8.26        (--------*---------)

6: Mar 02   -9.42    0.48  10.39          (--------*---------)

7: Apr 02   -6.94    3.00  12.93            (---------*---------)

8: May 02   -8.32    1.75  11.82           (---------*---------)

9: Jun 02   -4.17    5.83  15.83               (---------*---------)

-------+---------+---------+---------+--

-10         0        10        20

month id - date = 5: Feb 02 subtracted from:

month id

- date     Lower  Center  Upper  -------+---------+---------+---------+--

6: Mar 02  -7.75    2.09  11.93           (---------*---------)

7: Apr 02  -5.27    4.60  14.48              (---------*--------)

8: May 02  -6.65    3.36  13.37            (---------*---------)

9: Jun 02  -2.50    7.44  17.38                (---------*---------)

-------+---------+---------+---------+--

-10         0        10        20

month id - date = 6: Mar 02 subtracted from:

month id

- date     Lower  Center  Upper  -------+---------+---------+---------+--

7: Apr 02  -7.39    2.51  12.42            (---------*--------)

8: May 02  -8.77    1.27  11.31          (---------*---------)

9: Jun 02  -4.62    5.35  15.32              (---------*---------)

-------+---------+---------+---------+--

-10         0        10        20

month id - date = 7: Apr 02 subtracted from:

month id

- date      Lower  Center  Upper  -------+---------+---------+---------+--

8: May 02  -11.31   -1.24   8.83        (---------*---------)

9: Jun 02   -7.17    2.83  12.84            (---------*---------)

-------+---------+---------+---------+--

-10         0        10        20

month id - date = 8: May 02 subtracted from:

month id

- date     Lower  Center  Upper  -------+---------+---------+---------+--

9: Jun 02  -6.06    4.08  14.21             (---------*---------)

-------+---------+---------+---------+--

-10         0        10        20