Analysis 1, Cost Schedule Case

Exploration Exercise

Instructions, from lecture slides

In your group (15 min )

  - Create your plan for exploring the data.

  - List specific charts and analyses. (Ask for help if you need it.)

Individually (30 min)

  - Create your charts, statistics, and tests.

  - Did you need to adjust your plan along the way?

Return to your group  (30 min)

  - What are your interpretations, conclusions?

    - practical and statistical differences

    - possible root causes for variability

  - What are your assumptions and risks?

Debrief (30 min)

  - Each group reports results (5 min/group)

  - Class discussion

  - Does this case study situation reflect any of your organization’s reality?

    - Record actionable ideas on your “real life project” form

Data Files:

  - A1C3E1-2_Baseline-Explore-MonthlyData.MTW

  - A1C3E2_Explore-ClosedProjectCategories.xls*

*The format of this data lends itself to a spreadsheet, although portions of the data may be imported to minitab.  It is recommended that exploration of the closed projects be done only by groups that are feeling very comfortable with number crunching.

Additional guidance

(information about data files and corresponding analysis tips are on the following pages)

When developing your plan for exploring the data, consider these questions

- What is your strategy? What are your tasks?

- What roadmap questions are relevant?

- What diagrams, statistics, and charts will you create?

- Do you need to manipulate the data to create the desired charts? Or, does the file contain the data in the format that you need?

- Who will create which charts?

- Who will be the group spokesperson?

Notes on hypothesis testing…   In previous cases, you were introduced to basic statistics (p, t, F), regression and analysis of variance.  As often happens in real life, you may find you need other information to complete your analysis in this exercise.

- On the last page of this handout is a “hypothesis testing decision tree” that you may find useful.  Minitab help may also be useful.

- When you are back at your desk, you could also look things up in your favorite statistics book or on online sources such as the Electronic Statistics Textbook and the Engineering Statistics Handbook.  The latter, http://www.itl.nist.gov/div898/handbook.htm,  is particularly readable although it does contain much statistics parlance.

Monthly Data:  A1C3E1-2_Baseline-Explore-MonthlyData.MTW

This data set is a portion of the overall data set used in this case study.

The fieldnames in bold are the primary focus for the exercise.

Consider the following types of analysis to support your exploration.

- Outlier analysis

- Trend charts by org unit, project or month

- Boxplots

- Descriptive statistics and capability analysis

- Hypothesis testing  (see attached for more information on hypothesis testing)

If you have time, consider exploring differences by size (as proxied by BAC).  To do this, you may wish to create a column for size “categories.”

| Fieldname | Additional Explanation | Comments |
| --- | --- | --- |
| month# - date | Date, prefixed by sequential month number (1=october, 2=november, etc) | Prefix allows charting in time sequence |
| date |  |  |
| Org unit | Identifies which organizational unit the project is from |  |
| project id |  |  |
| Size (BAC) | The total staff hours budgeted to accomplish a work package or cost account. |  |
| BCWS | The percentage of a cost account’s Budget at Completion (BAC) that was scheduled to be completed on a particular date. BCWS cannot be calculated until after BAC has been determined and all work packages have been scheduled. | “budgeted cost for work scheduled” |
| BCWP | The amount of the Budget at Completion (BAC) that has been accomplished to date, based on the completion criteria and earned value (EV) method selected for the work package. (When a work package is completed, no matter how long it took to meet the completion criteria, BCWP=BAC.) | “budgeted cost for work performed” |
| ACWP | The actual manhours expended while working on a cost account. | “actual cost of work performed” |
| %sch var | ((BCWP – BCWS) / BCWS) * 100 |  |
| % cost var | ((BCWP – ACWP) / BCWP) * 100 |  |

Data File:  A1C3E2_Explore-ClosedProjectCategories.xls

While the “excel format” may appeal to some, this exploration should be done only groups that are feeling very comfortable with number crunching.

This spreadsheet contains 2 tabs.

- The first shows the closed project data collection spreadsheet (which lists the fields in the second file)

- The second is the recorded of each project for which the data collection spreadsheet was completed:   1 line per project  (it’s a very wide spreadsheet, there are a lot of blank cells)

In the second tab, summary statistics have been calculated on all the data that was available.  Your task is to summarize and evaluate the information.

- Are there any significant sources of variation?  (statistically?   Practically?)

- How would you present the story?

Continuous Data (Comparison)

Categorical Data

(Relationship)

Comparing Mean(s)…

From 2 dists.

From >2 dists.

Comparing Variation(s)…

Against a Target

From 2 dists. …

Against a Target

From 2 dists.

From >2 dists.

2-sample t-Test

ANOVA

2-Test

Normally dist’d.

F-Test

Levene’s Test

Not Normally dist’d.

Normally dist’d.

Bartlett’s Test

Levene’s Test

Not Normally dist’d.

From >2 dists. …

2-Test

Against a Target