## Slide 1
Earned Value Management: Basic Concepts
Dave Zubrow
Notes: © 2002 by Carnegie Mellon University
<number>

## Slide 2
The text and illustrations in this material are licensed by Carnegie Mellon University under a Creative Commons Attribution 4.0 International License. The Creative Commons license does not extend to logos, trade marks, or service marks of Carnegie Mellon University.
References herein to any specific commercial product, process, or service by trade name, trade mark, manufacturer, or otherwise, does not necessarily constitute or imply its endorsement, recommendation, or favoring by Carnegie Mellon University or its Software Engineering Institute.

## Slide 3: Outline
Building the Basic Earned Value Indicators:
  Overview
  Building Data Elements & Indicators
  Summary: The Basics
Notes: © 2002 by Carnegie Mellon University
<number>

## Slide 4: Earned Value: The Concept
Allocate all work across a product-oriented Work Breakdown Structure (WBS)
Clearly define what work needs to be done (completion criteria)
Assign responsibility for the work
Plan the work along a time line
Assign time phased resources to the work
Track actual progress and cost of defined work
Analyze variances between plan and actual performance
Use information provided to manage future direction

## Slide 5: How “Value” is “Earned”
EARNED VALUE:
The PLANNED VALUE
is EARNED by completing work.
PLANNED VALUE:
Project Planning Tasks:
Define work scope & WBS.
Estimate the value of each
work unit.
Develop a time-phased
budget during scheduling.
Value is “earned” by accomplishing
planned work.
Notes: © 2002 by Carnegie Mellon University
<number>
For InstrNotes: Multiple ways of expressing value. Ref to “ways” in 748

## Slide 6: Earned Value Cycle
Building Indicators
EV ANALYSIS
Interpreting Indicators
EV
PERFORMANCE
INDICATORS
Cost of Work
Completed
Completed
Work
Planned
Work
ACTUALS
Plan
Approval
PROJECT PLANNING
PROJECT EXECUTION
BASELINE
PLAN
Notes: © 2002 by Carnegie Mellon University
<number>

## Slide 7: Earned Value Indicators & Analysis
EV Indicator Analysis Areas:
Measures of Current Performance
Performance Forecast adjusted by
Current Performance Factors
EV Data Elements:
Indicator Build
Data
Elements
Cost of Work
Completed
Completed
Work
Planned
Work

## Slide 8: Example: Planned Value (PV)
Planned Value is a time-phased budget of: defined, estimated, and scheduled work.
Synonym for PV: (BCWS)
Budgeted Cost of Work Scheduled
Planned Value (PV)
$10
$15
$10
$25
$20
$20
$100
A
B
C
D
E
F
Total
Work Units (A – F)
Baseline Work:
One Reporting Period
(for this example)
Ref: DoD EV

## Slide 9: Example: Planned Value (PV)
Baseline Plan
Day 4
Day 3
Day 2
Day 1
Day 5
$0
$20
$40
$60
$80
$100
$120
$16
$41
$67
$91
$100
Planned Value
Planned
Value
Completed

## Slide 10: Example: EV Indicator -1
Value Earned:
This Reporting Period
Earned Value measures progress.
“How much of the planned work is completed”
EV = PV x Work Completed
Synonym for EV: (BCWP)
Budgeted Cost of Work Performed
A
B
C
D
E
F
Total
Work Completed
100%
100%
100%
40%
100%
0%
65%
Earned Value (EV)
$10
$15
$10
$10
$20
$ 0
$65
Planned Value (PV)
$10
$15
$10
$25
$20
$20
$100
Work Units (A – F)
Notes: © 2002 by Carnegie Mellon University
<number>

## Slide 11: Example: EV Indicator -2
Day 5
Day 4
Day 3
Day 2
Day 1
$0
$20
$40
$60
$80
$100
$120
Planned
Value
Earned
Value
Work Value
Completed

## Slide 12: Example: CV Indicator -1
Cost Variance measures a project’s cost performance.
CV (represented in $) = EV – AC
CV (represented as a %) = CV  EV
A
B
C
D
E
F
Total
Planned Value (PV)
$10
$15
$10
$25
$20
$20
$100
Work Units (A – F)
Work Completed
100%
100%
100%
40%
100%
0%
65%
Earned Value (EV)
$10
$15
$10
$10
$20
$ 0
$65
Actual Cost (AC)
$9
$22
$8
$30
$22
$0
$91
Cost Variance (CV) as $
Cost Variance (CV as %
$1
10%
$7
47%
$2
20%
$20
200%
$2
10%
$0
0%
$26
40%
Cost Variance
Notes: © 2002 by Carnegie Mellon University
<number>

## Slide 13: Example: CV Indicator -2
Cost
Variance
(EV – AC)
-$26
-40%
$0
$20
$40
$60
$80
$100
$120
Earned Value
(EV)
Planned Value
(PV)
Actual Cost
(AC)
Day 5
Day 4
Day 3
Day 2
Day 1
Work Value
Notes: © 2002 by Carnegie Mellon University
<number>
InstrNotes: Explain Why can’t Earned Value be greater than Planned Value.

## Slide 14: Example: Schedule Variance (SV) Indicator
Schedule Variance measures a project’s schedule performance.
SV (represented in $) = EV – PV
SV (represented as a %) = SV PV
A
B
C
D
E
F
Total
Planned Value (PV)
$10
$15
$10
$25
$20
$20
$100
Work Units (A – F)
Work Completed
100%
100%
100%
40%
100%
0%
65%
Earned Value (EV)
$10
$15
$10
$10
$20
$ 0
$65
Actual Cost (AC)
$9
$22
$8
$30
$22
$0
$91
Cost Variance (CV) as $
Cost Variance (CV) as %
$1
10%
$7
47%
$2
20%
$20
200%
$2
10%
$0
0%
$26
40%
Schedule Variance (SV) as $
Schedule Variance (SV) as %
$0
0%
$0
0%
$0
0%
$15
60%
$0
0%
$35
35%
$20
100%
Schedule Variance
Notes: © 2002 by Carnegie Mellon University
<number>

## Slide 15: Example: Schedule Variance (SV) Indicator
Schedule
Variance
(EV – PV)
-$35
-35%
$0
$20
$40
$60
$80
$100
$120
Day 5
Day 4
Day 3
Day 2
Day 1
Work Value
Earned Value
(EV)
Planned Value
(PV)
Actual Cost
(AC)

## Slide 16: Example: Cost Performance Index (CPIe)
Planned CPIe = 1.00
> 1.00 exceeds planned efficiency
< 1.00 falls short of planned efficiency
EV | AC | CPIe
$65 | $91 | .71
Questions:
“Is the Plan any good?”
“Do assigned resource
capabilities match
the planned efficiency
factors?”
Cost Performance Index (CPIe*) :
A cost efficiency factor: relationship between:
  actual costs expended
  value of the physical work performed
“e” in the acronym “CPIe” indicates, “efficiency”
CPIe = EV AC


=
CPIe for the
Example Project
=
Notes: © 2002 by Carnegie Mellon University
<number>

## Slide 17: Example: Cost Performance Index (CPIe)
CPIe = “What you got for what you spent.”
CPIe at Day 5
.71 29% below plan
Day 5
Day 4
Day 3
Day 2
Day 1
$20
$40
$60
$80
$100
$120
Work Cost
1.00
1.10
.90
1.30
.70
.80
1.20
CPIe
PV
AC
EV
This project spends $1.00 for every $0.71 of planned results.
Planned Cost Efficiency

## Slide 18: Example: Schedule Performance Index (SPI)
Schedule Performance Index (SPI):
Measures accomplished work per the baseline plan.
SPI = EV PV
EV | PV | CPIe
$65 | $100 | .65
=

=
SPI for the
Example Project
Planned SPI = 1.00
> 1.00 exceeds planned schedule performance
< 1.00 falls short of planned schedule performance
.65 = Behind Schedule
Less work has been performed than planned.

Notes: © 2002 by Carnegie Mellon University
<number>

## Slide 19: Example: Schedule Performance Index (SPI)
$20
$40
$60
$80
$100
$120
Work Cost
Day 5
Day 4
Day 3
Day 2
Day 1
1.00
1.10
.90
1.30
.70
.80
1.20
SPI
SPI at Day 5
.65
36% below plan
PV
AC
EV
$0.65 of Schedule is achieved for every Schedule $1.00 planned.
Planned Schedule Efficiency

## Slide 20: Project Status from EV Indicators
-$60
-$40
-$20
$0
$20
$40
$60
$80
$100
$120
Cost
Day 1
Day 2
Day 3
$91 AC
$65 EV
-$26
- 40%
CV
SV
Observations:
  things aren’t great, and,
  appear to be headed south!
CPIe: .71
SPI .65
Project Performance Status @ Day 5:
  40% Over Cost (CV  EV)
  35% Behind Schedule (SV PV)
  $1.00 Spent for every $0.71 of planned results.
  Schedule achieved @ 65% of planned effectiveness.
$100 PV
-$35
- 35%

## Slide 21: Forecasting: Estimate at Completion (EAC)
Typical EAC forecast uses a version of the formula below and combines three elements:
  value of the work remaining
  a Performance Efficiency Factor
  Actual Costs
Value of the Work Remaining*
A Performance Efficiency Factor
(e.g. CPIe ,SPI)
Actual Costs
+
EAC $
=
(divided by)
÷
*Value of Work Remaining = Total Budget – Earned Value
Notes: © 2002 by Carnegie Mellon University
<number>
InstrNotes: What happens with you replan. EAC is project specific/ utilizes project performance to-day

## Slide 22: EAC Example: Cumulative CPIe
Cumulative CPIe Estimate at Completion
Work Remaining
Cumulative CPIe
+ Actual Costs = EAC
Value of the Work Remaining*
$35
Cumulative CPIe
0.71
Actual Costs
$91
+
EAC $
$140
=
(divided by)
÷
$35 = $100 – $ 65
*Value of Work Remaining = Total Budget – Earned Value
$49
=

## Slide 23: EAC Example: Cumulative CPIe
Day 5
Day 4
Day 3
Day 2
Day 1
Day 6
Cost of Work
$0
$20
$40
$60
$80
$100
$120
$140
$160
Day 7
BAC (Budget at Completion)
CV
SV
Baseline Plan
Overrun
Earned Value
(EV)
Planned Value
(PV)
Actual Cost
(AC)
cumCPIe is a “Best Case” EAC
$140
cumCPIe

## Slide 24: EAC Example: Cumulative CPIe x SPI
Cumulative CPIe x SPI = Estimate at Completion
Work Remaining
Cumulative CPIe
+ Actual Costs = EAC
Value of the Work Remaining*
$35
(Cumulative CPIe x SPI)
0.71 x 0.65 = 0.46
Actual Costs
$91
+
EAC $
$167
=
(divided by)
÷
$76
=

## Slide 25: EAC: Cumulative CPIe x SPI
Day 5
Day 4
Day 3
Day 2
Day 1
Day 6
Cost of Work
$0
$20
$40
$60
$80
$100
$120
$140
$160
Day 7
BAC (Budget at Completion)
CV
SV
Baseline Plan
Overrun
Earned Value
(EV)
Planned Value
(PV)
Actual Cost
(AC)
cumCPIe x SPI is a “Most Likely” EAC
$167
$140
cumCPIe
cumCPIe x SPI

## Slide 26: Earned Value – Another Charting Approach
1.18
1.18
1.18
0.82
0.86
0.90
0.94
0.98
1.02
1.06
1.10
1.14
0.82
0.86
0.90
0.94
0.98
1.02
1.06
1.10
1.14
CPI
04/00
07/00
10/00
SPI
Behind Schedule and Overspent
Ahead of Schedule and Overspent
Behind Schedule and Under Spent
Target Area
Ahead of Schedule and Under Spent
0.96
0.94
Notes: © 2002 by Carnegie Mellon University
<number>
This indicator will track the cost Performance Index (CPI) and the Schedule Performance Indes (SPI) in relation to the target values.
Where
Green CPI 1.0 and SPI  1.0
Yellow CPI < 1.0 or SPI  1.0
Red CPI < 0.9 or SPI < 0.9
Target Area
CPI = .95 to 1.08
SPI = .95 to 1.08

## Slide 27: Summary Earned Value – Strengths & Cautions
Integrates the technical & management missions:
  Decisions based on common method – combines technical work units & management metrics.
  Consistent measurement of progress and performance.
Early Warning System for identifying trends.
Questionable EV Indicators result from poor cost & schedule estimates.
EV is an inadequate basis for selecting corrective actions.
Early identification of critical performance trends is compromised by:
  Use of large, lengthy, work units.
  Burying product-building work units under multiple layers of integration or roll-up type work units.
Strengths
Cautions

## Slide 28: Glossary -1
Term | Description | Acronym
Actual Cost Synonym: ( Actual Cost of Work Performed) | The actual cost of tasks that have been completed. | AC Synonym: ( ACWP)
Budget at Completion | The sum of all budgets allocated to a project. | BAC
Cost Performance Indexe | The ratio of budgeted costs to actual costs used to predict the magnitude of a possible cost overrun. | CPIe
Cost Variance | The difference between the planned and actual costs for completed work. | CV
Critical Path | The longest sequential path of activities which are absolutely essential to complete the project. | none
Notes: © 2002 by Carnegie Mellon University
<number>

## Slide 29: Glossary -2
Term | Description | Acronym
Earned Value Synonym: ( Budgeted Cost of Work Performed) | The value of competed work expressed in terms of the budget assigned to that work. | EV Synonym: ( BCWP)
Estimate at Completion | A value representing the projected final costs of the work when completed. | EAC
Planned Value Synonym: ( Budgeted Cost of Work Scheduled) | A time-phased budget of defined and estimated work scheduled to be performed during a given period. | PV Synonym: ( BCWS)
Schedule Performance Index | The planned schedule efficiency factor representing the relationship between the Planned Value and the Earned Value. | SPI
Notes: © 2002 by Carnegie Mellon University
<number>

## Slide 30: Glossary -3
Term | Description | Acronym
Schedule Variance | The difference between the value that was planned for completion and the work actually completed. | SV
To Complete Performance Index | To Complete (the work) Performance Index is the projected performance which must be achieved on all remaining work in order to meet a financial goal set by management. | TCPI
Notes: © 2002 by Carnegie Mellon University
<number>

## Slide 31: References
EIA-748 “Earned Value Management Systems”, Electronic Industries Alliance Standard, EIA-748. May 19, 1998
PMBOK “A Guide to the Project Management Body of Knowledge”, Project Management Institute, Upper Darby, Pennsylvania, 1996 (available on-line at: www.pmi.org)
Flemming, Koppelman Fleming, Quentin, W., Koppelman, Joel M., “Earned Value Project Management, Second Edition”, Project Management Institute, Upper Darby, Pennsylvania, 2000
Verzuh Verzuh, Eric, “The Fast Forward MBA in Project Management”, John Wiley & Sons, New York, New York, 1999
NASA EV NASA Earned Value Management Home Page:
http://evm.nasa.gov/index.html
DoD Department of Defense Earned Value Management Home Page:
http://www.acq.osd.mil/pm
DoD EV The example used for Module VIII is adapted from, “Illustrative Explanation of Earned Value”,
Department of Defense Earned Value Management Home Page, http://www.acq.osd.mil/pm/evbasics.htm
Notes: © 2002 by Carnegie Mellon University
<number>