## Slide 1: Improving Process Performance Using Six Sigma
Module 5: Cost and Schedule – A Case Study in Variability Reduction

## Slide 2
The text and illustrations in this material are licensed by Carnegie Mellon University under a Creative Commons Attribution 4.0 International License. The Creative Commons license does not extend to logos, trade marks, or service marks of Carnegie Mellon University.
References herein to any specific commercial product, process, or service by trade name, trade mark, manufacturer, or otherwise, does not necessarily constitute or imply its endorsement, recommendation, or favoring by Carnegie Mellon University or its Software Engineering Institute.

## Slide 3: Syllabus At A Glance
MONDAY
TUESDAY
WEDNESDAY
THURSDAY
FRIDAY
Core Concepts
Defect Case
Wrap-Up
Core Concepts
Core Concepts
Call Center Case
Call Center Case
Intro
Defect Case
Cost-Schedule Case
Cost-Schedule Case
Notes: Improving Process Performance Using Six Sigma
Module 5: Cost and Schedule – A Case Study in Variability Reduction

## Slide 4: Module 5 Contents – 1
Overview Measurement use Measurement process Define phase Project scope Goals Establishing project | Measure phase Identifying data Obtaining data Sampling considerations Minitab projects 1-sample t-test 1-proportion sample 2-proportion sample 1-way ANOVA sample Determining sample sizes Evaluating data Initial MSE on effort data Minitab projects Gage R&R study Final MSE on effort data Minitab projects Summarizing and baselining
5
9
11
12-17
13
14
17
18-70
19
21
23
26-46
26
35
39
43
47
50
51
54-60
55
61
62-64
66
Notes: Improving Process Performance Using Six Sigma
Module 5: Cost and Schedule – A Case Study in Variability Reduction

## Slide 5: Module 5 Contents – 2
Analyze phase Exploring data Characterizing process & problem Effort variance Updating scope & scale Goal statements Improve phase Identifying & selecting solutions Failure modes & effects analysis Validating solutions | Control phase Estimate at completion Results Case timeline Summary
71-82
72
74
75
81
82
83-98
84
88
95
99-103
100
102
103
104
Notes: Improving Process Performance Using Six Sigma
Module 5: Cost and Schedule – A Case Study in Variability Reduction

## Slide 6: Case Overview – 1
The Organization
This case study is based on work done by Warner Robins Air Logistics Center, which provides combat-ready weapon systems, equipment, services, and support personnel for the U.S. Air Force.
For instructional purposes, the data has been adjusted and the case has been supplemented with techniques and details from other organizations and projects.
The Goal
The organization wants to improve customer satisfaction by reducing field defects and effort & schedule variance.
Notes: Improving Process Performance Using Six Sigma
Module 5: Cost and Schedule – A Case Study in Variability Reduction

## Slide 7: Case Overview – 2
Organizational Context
The organization works on a number of projects with different characteristics.
  Projects vary in size and complexity.
  Some involve development activities and others maintenance.
  Schedules range from less than one month to 18 months and longer.
Notes: Improving Process Performance Using Six Sigma
Module 5: Cost and Schedule – A Case Study in Variability Reduction

## Slide 8: Case Overview – 3
Warner Robins’ support structure for measurement & analysis.
Notes: Roles & responsibilities of QMG, SEPG, SST, POCs
Improving Process Performance Using Six Sigma
Module 5: Cost and Schedule – A Case Study in Variability Reduction

## Slide 9: Case Overview – 4
Our approach to this case included multiple improvements which were identified as we progressed through the DMAIC model phases
Basically, as barriers or challenges arose during the execution of the DMAIC model, we had to initiate improvement actions to enable our primary project to proceed.
Notes: Improving Process Performance Using Six Sigma
Module 5: Cost and Schedule – A Case Study in Variability Reduction

## Slide 10: Measurement in Use
Below is a partial list of work that is already complete at the organization:
    measurement infrastructure for project, product and process metrics
    SPC pilots within selected organizational units
    initial data rollups for management
    initial benefits calculations (ROI and other indicators)
Notes: Improving Process Performance Using Six Sigma
Module 5: Cost and Schedule – A Case Study in Variability Reduction

## Slide 11: Background
What “M&A” type efforts lie ahead to fulfill improvement-related goals?
  ensure compliance to measurement policy
  organizational and project baselines
  model building at the project level
  relating process behavior and performance to product and service quality
  quantitatively manage key processes and subprocesses
Notes: Improving Process Performance Using Six Sigma
Module 5: Cost and Schedule – A Case Study in Variability Reduction

## Slide 12: Site Software Measurement Process
Notes: This case study was written up in the SEI technical report 06TR004.
Improving Process Performance Using Six Sigma
Module 5: Cost and Schedule – A Case Study in Variability Reduction

## Slide 13: Define Guidance Questions
Control
Improve
Analyze
Measure
Identify needed data
Obtain data set
Evaluate data quality
Summarize & baseline data
Explore data
Characterize process & problem
Update improvement project scope & scale
Identify possible solutions
Select solution
Implement (pilot as needed)
Evaluate
Define control method
Implement
Document
Define project scope
Establish formal project
Define
What is the current problem to be solved?
What are the goals, improvement targets, & success criteria?
What is the business case, potential savings, or benefit that will be realized when the problem is solved?
Who are the stakeholders? The customers?
What are the relevant processes and who owns them?
Notes: Improving Process Performance Using Six Sigma
Module 5: Cost and Schedule – A Case Study in Variability Reduction

## Slide 14: Defining the Project Scope
What is the current problem to be solved?
We’ll complete a Define-Measure-Analyze iteration to select our project.
First, we’ll select an area of focus from the organization’s strategic goals.
Then, we’ll align technical and project measures to the area of focus.
D
M
A
I
C
Notes: Improving Process Performance Using Six Sigma
Module 5: Cost and Schedule – A Case Study in Variability Reduction

## Slide 15: Organization’s Strategic Goals
Customer Satisfaction – Be honest, responsive, and flexible providing products and/or services that meet or exceed customer requirements.
Employee Satisfaction – Provide and foster a work environment that promotes employee satisfaction.
Common Organization Process – Establish a common organizational process that implements a consistent management discipline across business domains.
Communication – Promote open, multi-directional and timely communication
Business Opportunities – Pursue new business opportunities and partnerships based on value to our customer and to ourselves.
Skills – Develop and maintain the skills base to satisfy requirements of current and future business domains.
D
M
A
I
C
Notes: Much of the CMMI implementation, per se, was done under the umbrella of “common organization process.”
While executing the processes related to measurement & analysis certainly fall under that umbrella, the object of those processes could be any of these strategic goals (whichever ones are deemed to be the priority at any given time – based on strategic imperatives and/or what the data is telling you is the biggest problem spot).
Improving Process Performance Using Six Sigma
Module 5: Cost and Schedule – A Case Study in Variability Reduction

## Slide 16: Customer Satisfaction Goal Structure
D
M
A
I
C
Notes: Improving Process Performance Using Six Sigma
Module 5: Cost and Schedule – A Case Study in Variability Reduction

## Slide 17: Define Guidance Questions
Control
Improve
Analyze
Measure
Identify needed data
Obtain data set
Evaluate data quality
Summarize & baseline data
Explore data
Characterize process & problem
Update improvement project scope & scale
Identify possible solutions
Select solution
Implement (pilot as needed)
Evaluate
Define control method
Implement
Document
Define project scope
Establish formal project
Define
Have stakeholders agreed to the project charter or contract?
What is the project plan, including the resource plan and progress tracking?
How will the project progress be communicated?
Notes: Improving Process Performance Using Six Sigma
Module 5: Cost and Schedule – A Case Study in Variability Reduction

## Slide 18: Establishing the Formal Project
    We selected customer satisfaction as the focus for our project.
    Indicators of customer satisfaction include
      cost & schedule performance
      inspection defects
      field defects
D
M
A
I
C
Notes: Improving Process Performance Using Six Sigma
Module 5: Cost and Schedule – A Case Study in Variability Reduction

## Slide 19: Measure Guidance Questions
Define project scope
Establish formal project
Control
Improve
Analyze
Define
Explore data
Characterize process & problem
Update improvement project scope & scale
Identify possible solutions
Select solution
Implement (pilot as needed)
Evaluate
Define control method
Implement
Document
Measure
Identify needed data
Obtain data set
Evaluate data quality
Summarize & baseline data
What are the process outputs and performance measures?
What are the process inputs?
What info is needed to understand relationships between inputs and outputs? Among inputs?
What information is needed to monitor the progress of this improvement project?
Notes: Improving Process Performance Using Six Sigma
Module 5: Cost and Schedule – A Case Study in Variability Reduction

## Slide 20: Identifying Needed Data
  Questions to address
  What are the customers saying?
  How is our product performing in the field?
  What does inspection data look like? Is it in synch with field performance?
  What does cost and schedule performance look like at the end of projects? While projects are in progress?
D
M
A
I
C
Notes: Improving Process Performance Using Six Sigma
Module 5: Cost and Schedule – A Case Study in Variability Reduction

## Slide 21: Measure Guidance Questions
Define project scope
Establish formal project
Control
Improve
Analyze
Define
Explore data
Characterize process & problem
Update improvement project scope & scale
Identify possible solutions
Select solution
Implement (pilot as needed)
Evaluate
Define control method
Implement
Document
Measure
Identify needed data
Obtain data set
Evaluate data quality
Summarize & baseline data
Is the needed measurement infrastructure in place?
Are the data being collected and stored?
Notes: Improving Process Performance Using Six Sigma
Module 5: Cost and Schedule – A Case Study in Variability Reduction

## Slide 22: Obtaining Needed Data
What are the process outputs and performance measures?
What data is available?
Customer Satisfaction
  surveys, after projects are closed
  client emails
    available in organizational manager files
  performance goal: not yet specified
Defects
  inspection data
    manually transferred from forms to database
    defect types, inspection effort, rework also recorded
  field defect data
  performance goal: 0 field defects
Cost and Schedule
  Monthly cost and schedule variance
    relative to most recent estimate
  Final project cost and schedule performance
    Available in project manager files
  Text explanation for variance
  Performance goal: +/- 20% variance
D
M
A
I
C
Notes: Improving Process Performance Using Six Sigma
Module 5: Cost and Schedule – A Case Study in Variability Reduction

## Slide 23: Cost/Schedule Measurement System
Monthly effort, schedule (earned value based)
  variance: (most recent estimate – current actual)
    compared to variance specification (+/- 20%)
    text entry for out of specification explanations
  data manually transferred from project files to monthly report
  cost in terms of effort hours
  schedule performance derived from effort hours
Completed project data:
  variance: (original plan – final actual)
    categorized by internal and external causes
    categorized by life-cycle phase
  cost in terms of effort + purchase costs
  schedule in terms of calendar days
  each replan recorded
Positive variance implies under -budget or schedule
Negative variance implies over- budget or schedule
D
M
A
I
C
Notes: Improving Process Performance Using Six Sigma
Module 5: Cost and Schedule – A Case Study in Variability Reduction

## Slide 24: Sampling Considerations – 1
From our earlier discussions on hypothesis testing, we learned that sample size can have a dramatic effect on the p value.
Now we are faced with deciding how big a sample of data will be needed to achieve our goals.
      The answer is in the 4 fraternity brothers:
        alpha (we normally use 5%)
        beta (we normally use 10-20%)
        delta (to be determined case by case)
        sigma (to be determined case by case)
D
M
A
I
C
Notes: Explain that the reason for adding this submodule on sampling is that no matter how much data exists in your organization, you will find yourself having to sample for additional data during your quest to further segment and stratify in pursuit of root causes and relationships in the data.
Improving Process Performance Using Six Sigma
Module 5: Cost and Schedule – A Case Study in Variability Reduction

## Slide 25: Sampling Considerations – 2
Correct decision with probability of 1- alpha | Incorrect decision with probability of alpha
Incorrect decision with probability of beta | Correct decision with probability of 1- beta = (Power)
If the null hypothesis is really…
TRUE
FALSE
and your decision is to…
Accept the null Reject the null
D
M
A
I
C
Notes: Analogy
You are going to the doctor to get tested for cancer.
The Null Hypothesis is that you don’t have cancer, while the Alternative Hypothesis is that you do have cancer.
Alpha is the probability that your doctor will tell you that you have cancer when in fact you do not.
(1-Alpha) is the probability that your doctor correctly tells you that you do not have cancer.
Beta is the probability that your doctor tells you that your are cancer free when in fact you have cancer.
(1-Beta) is the probability that your doctor correctly tells you that you have cancer. This is also called Power.
Ask students to relate this alpha to the p-value within a Hypothesis test.
Improving Process Performance Using Six Sigma
Module 5: Cost and Schedule – A Case Study in Variability Reduction

## Slide 26: Sampling Considerations – 3
The two remaining fraternity brothers are:
Delta: the difference that you want to be able to detect in your hypothesis test (e.g., accuracy).
Sigma: the estimated standard deviation of the population of the data from which you are sampling (remember from ANOVA that variation affects p values and thus higher variation requires higher sample sizes) (e.g., precision).
D
M
A
I
C
Notes: Mention that the Wheeler book talks about news articles on teen smokers.
Improving Process Performance Using Six Sigma
Module 5: Cost and Schedule – A Case Study in Variability Reduction

## Slide 27: Sampling Considerations – 4
Test | When you want to …
1-Sample z | Test if the mean of a variable from a single sample is different from a value you specify
1-Sample t | Test if the mean of a variable from a single sample is different from a value you specify
2-Sample t | Test if the means of the same variable from each of two populations are different
1 Proportion | Test if a population proportion differs from a value you specify
2 Proportions | Determine if the proportions of two populations are different
One-Way ANOVA | Test how changes to power, sample size, and maximum difference affect the other two
Quick reminder of the tests that we may want to perform.
Note: Those in bold are discussed on the following slides

## Slide 28: Sampling Considerations – 5
To demonstrate 1-sample t-test sample sizes, how many code modules do we need to sample to draw a conclusion about the McCabe path complexity of each of the code modules in a given software release?
D
M
A
I
C
Notes: Improving Process Performance Using Six Sigma
Module 5: Cost and Schedule – A Case Study in Variability Reduction

## Slide 29: Sampling Considerations – 6
We want to assess the complexity within different levels of accuracy (e.g., 1…10).
We also will see sample sizes for both 0.8 and 0.9 Power values.
We believe the standard deviation = 2.0
Remember,
Power = 1- Beta
(e.g. Probability of correctly accepting the Alternative Hypothesis)
D
M
A
I
C
Notes: Improving Process Performance Using Six Sigma
Module 5: Cost and Schedule – A Case Study in Variability Reduction

## Slide 30: Sampling Considerations – 7
We will test whether the set of modules in the release equal or do not equal a given McCabe path complexity. We want alpha of 5%.
D
M
A
I
C
Notes: Improving Process Performance Using Six Sigma
Module 5: Cost and Schedule – A Case Study in Variability Reduction

## Slide 31: Sampling Considerations – 8
D
M
A
I
C
The session window shows the sample size needed for each scenario of accuracy and Power (e.g. “1-Beta”).
So, if we want to conclude the average McCabe path complexity for a release within a complexity value of 2 (and using power of 0.9), we would need to randomly sample 13 code modules to do the 1- sample t-test.
Notes: If students have trouble identifying with the complexity notion, explain that this sampling could be to determine any other attribute of the code modules without having to measure all modules.
Make double sure the students know what “difference” is in context of the scenario.
How accurate do you need to be?
Improving Process Performance Using Six Sigma
Module 5: Cost and Schedule – A Case Study in Variability Reduction

## Slide 32: Sampling Considerations – 9
D
M
A
I
C
Notes: The graph displays one power curve for each sample size. The different power curves represent every combination of power and difference the test can detect based on the various sample of sizes (3, 4, 6, 7, 10, 13, 34, 44). The symbol on each power curve represents the test's power for detecting the specified differences. The curves representing larger sample sizes yield higher power for any given difference when the other assumptions are held constant.
Improving Process Performance Using Six Sigma
Module 5: Cost and Schedule – A Case Study in Variability Reduction

## Slide 33: Sampling Considerations – 10
To demonstrate 2-sample t-test sample sizes, how many code modules do we need to sample from each of two software releases to draw a conclusion about their relative McCabe path complexity?
D
M
A
I
C
Notes: Instructors must ensure they preface each scenario by fully explaining the callout that describes the scenario.
Need to preface the entire sampling section to inform students that most data collection will be of new sampling because historically collected data will rarely be sufficient for analysis and modeling.
Improving Process Performance Using Six Sigma
Module 5: Cost and Schedule – A Case Study in Variability Reduction

## Slide 34: Sampling Considerations – 11
We want to see required sample sizes under scenarios of accuracy of 1..10 complexity value and powers of 0.8 and 0.9.
D
M
A
I
C
Notes: Improving Process Performance Using Six Sigma
Module 5: Cost and Schedule – A Case Study in Variability Reduction

## Slide 35: Sampling Considerations – 12
D
M
A
I
C
So, to compare two different software releases for McCabe complexity values (given we want to discern differences of complexity value of 3 and with power at 0.9, we need to randomly sample 11 code modules from each release.
Notes: Need to have 11 samples from each release.
Improving Process Performance Using Six Sigma
Module 5: Cost and Schedule – A Case Study in Variability Reduction

## Slide 36: Sampling Considerations – 13
D
M
A
I
C
Notes: The graph displays one power curve for each sample size. The various power curves represent every combination of power and difference the test can detect based on the sample of sizes listed. The symbol on each power curve represents the test's power for detecting the specified differences.
Improving Process Performance Using Six Sigma
Module 5: Cost and Schedule – A Case Study in Variability Reduction

## Slide 37: Sampling Considerations – 14
To demonstrate 1-proportion sample sizes, we want to sample our major findings from inspections and conduct root cause analysis to determine the proportion of architecture issues we are experiencing overall.
D
M
A
I
C
Notes: Improving Process Performance Using Six Sigma
Module 5: Cost and Schedule – A Case Study in Variability Reduction

## Slide 38: Sampling Considerations – 15
Expert opinion claims that 60% of major inspection findings will be root caused to architecture issues. We want to identify the number of findings to be randomly selected for root cause analysis, given that we want to discern different possible proportions of 40%, 45%, 50%, 55%, 65% and 70% (along with powers of 0.8 and 0.9).
D
M
A
I
C
Notes: Improving Process Performance Using Six Sigma
Module 5: Cost and Schedule – A Case Study in Variability Reduction

## Slide 39: Sampling Considerations – 16
We have learned that if we use power = 0.9 and want to know whether the proportion is really 40% instead of 60%, we will need to randomly sample at least 64 of the major software inspection findings for conducting root cause analysis.
D
M
A
I
C
Notes: Improving Process Performance Using Six Sigma
Module 5: Cost and Schedule – A Case Study in Variability Reduction

## Slide 40: Sampling Considerations – 17
D
M
A
I
C
Notes: The graph displays one power curve for each sample size. The various power curves represent every combination of power and alternative proportion values based on the sample of sizes listed . The symbol on each power curve represents the test's power for detecting the specified alternate proportions.
Improving Process Performance Using Six Sigma
Module 5: Cost and Schedule – A Case Study in Variability Reduction

## Slide 41: Sampling Considerations – 18
To demonstrate 2-proportion sample sizes, we want to sample our major findings from inspections for two different software releases and conduct root cause analysis to determine whether the two releases have different proportions of architecture issues.
D
M
A
I
C
Notes: Improving Process Performance Using Six Sigma
Module 5: Cost and Schedule – A Case Study in Variability Reduction

## Slide 42: Sampling Considerations – 19
We believe the first release has 50% architecture root causes and we want to discern if the second release has a different proportion of architecture root causes of 35%, 40%, 45%, 55%, 60%, 65%, and 70%, (along with powers of 0.8 and 0.9).
D
M
A
I
C
Notes: Improving Process Performance Using Six Sigma
Module 5: Cost and Schedule – A Case Study in Variability Reduction

## Slide 43: Sampling Considerations – 20
We have learned that if we use power = 0.9 and want to know whether the second release is different from the first release by at least 10%, we will need to randomly sample at least 519 of the major software inspection findings from each release to conduct root cause analysis.
D
M
A
I
C
Notes: Improving Process Performance Using Six Sigma
Module 5: Cost and Schedule – A Case Study in Variability Reduction

## Slide 44: Sampling Considerations – 21
D
M
A
I
C
Notes: The graph displays one power curve for each sample size. The various power curves represent every combination of power and proportion 1 values based on the sample of size sizes listed. The symbol on each power curve represents the test's power for detecting the specified proportion 1 values.
Improving Process Performance Using Six Sigma
Module 5: Cost and Schedule – A Case Study in Variability Reduction

## Slide 45: Sampling Considerations – 22
To demonstrate 1-way ANOVA sample sizes, we now want to sample code modules within each programming language to discern if there are differences of McCabe path complexity by programming language.
D
M
A
I
C
Notes: Read the callouts to ensure the students understand the scenario being analyzed.
Improving Process Performance Using Six Sigma
Module 5: Cost and Schedule – A Case Study in Variability Reduction

## Slide 46: Sampling Considerations – 23
We have 5 different programming languages involved: Ada, C++, Fortran, Cobol, and Assembly.
We want to discern differences of complexity values among the programming languages of 5, 10, 15, or 20; we will use power of 0.8 or 0.9.
D
M
A
I
C
Notes: Improving Process Performance Using Six Sigma
Module 5: Cost and Schedule – A Case Study in Variability Reduction

## Slide 47: Sampling Considerations – 24
To discern differences of complexity value of at least 5 among the programming languages (and using power of 0.9), we will need to randomly sample at least 21 code modules of each language.
D
M
A
I
C
Notes: Improving Process Performance Using Six Sigma
Module 5: Cost and Schedule – A Case Study in Variability Reduction

## Slide 48: Sampling Considerations – 25
D
M
A
I
C
Notes: The graph displays one power curve for each sample size. The various power curves represent every combination of power and the maximum difference in means the test detects based on the listed sample sizes. The symbol on each power curve represents the test's power for detecting a maximum difference of 5.
Improving Process Performance Using Six Sigma
Module 5: Cost and Schedule – A Case Study in Variability Reduction

## Slide 49: Exercise: Determining Sample Sizes – 1
Break into groups and determine the needed sample sizes for the following four scenarios:
    Scenario #1: Want to find out if two projects have different proportions of requirements issues, given that one project has approximately 65% requirements issues, and we want to discern if the second project is different by 15% in either direction. Use alpha = 5% and power = 0.8.
    Scenario #2: Want to sample two projects to determine if one project has different average individual daily interruptions or not, given alpha = 5%, power = 0.9, standard deviation of average daily individual interruptions = 3 and we want to discern if the two projects are different by at least 5 average daily individual interruptions.
D
M
A
I
C
Notes: Scenario #1: This is a 2-Proportions t-test; We will need to sample 170 issues.
Scenario #2: This is a 2 sample t-test; We will need 9 days of interruption counts for each project.
Improving Process Performance Using Six Sigma
Module 5: Cost and Schedule – A Case Study in Variability Reduction

## Slide 50: Exercise: Determining Sample Sizes – 2
    Scenario #3: We want to conduct a comparison to determine if there are different McCabe complexity values between New code, Modified code, and Reused “as is” code. Use alpha = 5%, power = 0.9, standard deviation = 4, and we want to discern differences of complexity values of at least 5.
    Scenario #4: We want to sample completed projects for average years of experience of individual software developers to determine if the average years of experience is greater than 15. Use alpha = 5%, power = 0.9, standard deviation of years of experience = 4, and we want to discern differences of at least 3 years experience.
D
M
A
I
C
Notes: Scenario #3: This is an ANOVA situation; We will need 18 code units each of New, Modified, Reused.
Scenario #4: This is a 1 sample t-test; We will need 17 completed projects in our sample. Remember, of at least 3 years means that we will use the Options button and under Alternative Hypothesis, we should use Greater Than. If the student uses Not Equal for Alternative Hypothesis, you will get a sample size of 21.
Improving Process Performance Using Six Sigma
Module 5: Cost and Schedule – A Case Study in Variability Reduction

## Slide 51: Measure Guidance Questions
Define project scope
Establish formal project
Control
Improve
Analyze
Define
Explore data
Characterize process & problem
Update improvement project scope & scale
Identify possible solutions
Select solution
Implement (pilot as needed)
Evaluate
Define control method
Implement
Document
Measure
Identify needed data
Obtain data set
Evaluate data quality
Summarize & baseline data
Does the measurement system yield accurate, precise, and reproducible data?
Are urgently needed improvements revealed?
Has the risk of proceeding in the absence of 100% valid data been articulated?
Notes: Improving Process Performance Using Six Sigma
Module 5: Cost and Schedule – A Case Study in Variability Reduction

## Slide 52: Cost & Schedule Data Issues
Does the measurement system yield accurate, precise, and reproducible data?
Cost / Schedule Data: MSE
Accuracy
  rebaselining biases the data, promotes perception that performance is better than it actually is
Repeatability
  different estimating methods across life cycle, across projects
  Unclear definition of “project”
  Poor records about project replans
Completeness
  which project types are “in” and which are “out”?
  sparse data – some parts of organization better represented
  completed project data missing from organization data
D
M
A
I
C
Notes: Improving Process Performance Using Six Sigma
Module 5: Cost and Schedule – A Case Study in Variability Reduction

## Slide 53: Initial MSE on Effort Data – 1
We suspected large measurement error within the project effort data reported.
We identified 10 random projects to measure actual completed effort.
We identified 3 different measurement analysts to participate in our MSE.
D
M
A
I
C
Notes: Improving Process Performance Using Six Sigma
Module 5: Cost and Schedule – A Case Study in Variability Reduction

## Slide 54: Initial MSE on Effort Data – 2
We asked each of the analysts to identify and report the actual effort data for each of the projects.
We also asked them to repeat this exercise the following month without tracking the projects identity from the previous month.
We felt the instability of the databases, as well as the human requests for clarification from project staff, were injecting error in the reported effort numbers
D
M
A
I
C
Notes: Improving Process Performance Using Six Sigma
Module 5: Cost and Schedule – A Case Study in Variability Reduction

## Slide 55: Initial MSE on Effort Data – 3
We decided this would be analyzed as variables data.
We decided we would use a Crossed Gauge R&R analysis because each analyst would measure each of the 10 projects.
The following slides depict the Minitab screen shots of this demonstration.
▼Minitab – GaugeRRStudyInitial.mpj
D
M
A
I
C
Notes: Improving Process Performance Using Six Sigma
Module 5: Cost and Schedule – A Case Study in Variability Reduction

## Slide 56: Initial MSE on Effort Data – 4
▼Minitab – GaugeRRStudyInitial.mpj
The dataset has three columns:
C1 = Project Id 1-10
C2 = Analyst A, B, or C
C3 = Measurement of reported actual effort hours
D
M
A
I
C
Notes: Improving Process Performance Using Six Sigma
Module 5: Cost and Schedule – A Case Study in Variability Reduction

## Slide 57: Initial MSE on Effort Data – 5
▼Minitab – GaugeRRStudyInitial.mpj
We have a crossed design (all projects measured by all analysts).
D
M
A
I
C
Notes: Improving Process Performance Using Six Sigma
Module 5: Cost and Schedule – A Case Study in Variability Reduction

## Slide 58: Initial MSE on Effort Data – 6
For us,
Part number = Project Operators = Analysts
D
M
A
I
C
Notes: Improving Process Performance Using Six Sigma
Module 5: Cost and Schedule – A Case Study in Variability Reduction

## Slide 59: Initial MSE on Effort Data – 7
For p values < 0.05, the factor is significant and causes notable variation.
D
M
A
I
C
Notes: Improving Process Performance Using Six Sigma
Module 5: Cost and Schedule – A Case Study in Variability Reduction

## Slide 60: Initial MSE on Effort Data – 8
Total Gage R&R is 14.57% of total Variation. This is greater than 10%, indicating that the measurement system error is marginal.
D
M
A
I
C
Notes: Improving Process Performance Using Six Sigma
Module 5: Cost and Schedule – A Case Study in Variability Reduction

## Slide 61: Initial MSE on Effort Data – 9
The number of distinct categories discernable by the measurement system must be at least 5 according to AIAG. Here, the “3” indicates an unacceptable system.
D
M
A
I
C
Notes: Improving Process Performance Using Six Sigma
Module 5: Cost and Schedule – A Case Study in Variability Reduction

## Slide 62: Evaluating and Improving Data Quality
Are urgently needed improvements revealed?
At this point, we find immediate improvement opportunities with our measurement system of effort data.
Define standard definitions of what effort to include and how to store and retrieve effort data from the various sources.
Automate collection of completed project cost and schedule.
D
M
A
I
C
Notes: Improving Process Performance Using Six Sigma
Module 5: Cost and Schedule – A Case Study in Variability Reduction

## Slide 63: Final MSE on Effort Data – 1
We implemented the measurement system improvements and then re-conducted our MSE.
We analyzed this dataset in the same manner as before with the 3 different analysts.
The following slides depict the Minitab screen shots of this demonstration.
▼Minitab – GageRRStudyFinal.mpj
D
M
A
I
C
Notes: Improving Process Performance Using Six Sigma
Module 5: Cost and Schedule – A Case Study in Variability Reduction

## Slide 64: Final MSE on Effort Data – 2
All p values still < 0.05 and thus cause notable variation.
D
M
A
I
C
Notes: Improving Process Performance Using Six Sigma
Module 5: Cost and Schedule – A Case Study in Variability Reduction

## Slide 65: Final MSE on Effort Data – 3
The total Gage R&R, based on our measurement system improvements, is now only 3.75% of total variation.
D
M
A
I
C
Notes: Improving Process Performance Using Six Sigma
Module 5: Cost and Schedule – A Case Study in Variability Reduction

## Slide 66: Final MSE on Effort Data – 4
The number of distinct categories = 7.0, which is well above the AIAG standard of 5.0. We have an acceptable measurement system.
D
M
A
I
C
Notes: Improving Process Performance Using Six Sigma
Module 5: Cost and Schedule – A Case Study in Variability Reduction

## Slide 67: Measure Guidance Questions
Define project scope
Establish formal project
Control
Improve
Analyze
Define
Explore data
Characterize process & problem
Update improvement project scope & scale
Identify possible solutions
Select solution
Implement (pilot as needed)
Evaluate
Define control method
Implement
Document
Measure
Identify needed data
Obtain data set
Evaluate data quality
Summarize & baseline data
What does the data look like upon initial assessment? Is it what we expected?
What is the overall performance of the process?
Do we have measures for all significant factors, as best we know them?
Are there data to be added to the process map?
Are any urgently needed improvements revealed?
What assumptions have been made about the process and data?
Notes: Improving Process Performance Using Six Sigma
Module 5: Cost and Schedule – A Case Study in Variability Reduction

## Slide 68: Summarizing and Baselining the Data
What does the data look like upon initial assessment? Is it what we expected?
We expect project data to be in good shape, and we anticipate that our CMMI task is to build models to monitor what is pretty good performance.
Question:
  What does cost and schedule performance look like at the end of projects? While projects are in progress?
D
M
A
I
C
Notes: Improving Process Performance Using Six Sigma
Module 5: Cost and Schedule – A Case Study in Variability Reduction

## Slide 69: How Do Projects Typically End?
Cost/Schedule Performance Baseline, Outliers Removed
Reminder: This is the total cumulative variance.
  (initial plan – final actual)
  customer-driven changes are included
Some extreme values still present
  there are no valid reasons to remove or segment the data
Large % of data outside specification
  process not capable
D
M
A
I
C
Notes: Improving Process Performance Using Six Sigma
Module 5: Cost and Schedule – A Case Study in Variability Reduction

## Slide 70: What is Month to Month Performance?
Cost/Schedule Performance Baseline, Outliers Removed
In-process effort/cost data
  All life-cycle phases, all projects, Oct – June
Reminder: variance = most recent estimate – current actual
Similar to completed projects’ data.
  averages running close to target
  more data than expected outside of spec
  high variability
  Is monthly performance consistent with final performance?
D
M
A
I
C
Notes: Is monthly performance consistent with final performance?
Averages are running about the same, but monthly data has slightly lower standard deviation and lower % outside spec.
This is most likely due to a couple things: the difference in operational definitions (the monthly data incorporates the effect of rebaselining), and also a difference in sample size).
Improving Process Performance Using Six Sigma
Module 5: Cost and Schedule – A Case Study in Variability Reduction

## Slide 71: Initial Baseline Summary
Both monthly and final project cost/schedule data are consistently out of spec.
Many measurement infrastructure improvements were identified:
  improved operational definitions
  improved automation, to improve quality and minimize quantity of missing data
  addition of completed project data into central repository
  group data by life cycle phase or project % complete for reporting
D
M
A
I
C
Notes: Improving Process Performance Using Six Sigma
Module 5: Cost and Schedule – A Case Study in Variability Reduction

## Slide 72: Where Do We Go From Here?
Further explore cost and schedule variability
  note issues of small sample size
  anticipate establishing variance reduction goals
  anticipate establishing cost-schedule models
    not defect models, as thought for CMMI implementation
Actively monitor defect data
  Keep vigil over unhealthy trade-offs with quality
Improve measurement infrastructure, including collecting more data
Re-evaluate driver for cost/schedule focus
  customers are satisfied
  may need to align focus to internal business management
D
M
A
I
C
Notes: Improving Process Performance Using Six Sigma
Module 5: Cost and Schedule – A Case Study in Variability Reduction

## Slide 73: Analyze Guidance Questions
Define project scope
Establish formal project
Control
Improve
Measure
Define
Identify needed data
Obtain data set
Evaluate data quality
Summarize & baseline data
Identify possible solutions
Select solution
Implement (pilot as needed)
Evaluate
Define control method
Implement
Document
Analyze
Explore data
Characterize process & problem
Update improvement project scope & scale
What do the data look like?
What is driving the variation?
What is the new baseline?
What are associated risks and assumptions associated with revised data set and baseline?
Notes: Improving Process Performance Using Six Sigma
Module 5: Cost and Schedule – A Case Study in Variability Reduction

## Slide 74: Exploring the Data
What do the data look like? What is driving the variation?
  In Measure, we baselined the data and discovered unexpected large variability in cost & schedule performance. Now we need to determine the cause of this variability.
First, we’ll conduct an initial exploratory analysis to
    confirm or refute several possible drivers of variation
    identify specific improvement opportunities
D
M
A
I
C
Notes: Improving Process Performance Using Six Sigma
Module 5: Cost and Schedule – A Case Study in Variability Reduction

## Slide 75: Analyze Guidance Questions
Define project scope
Establish formal project
Control
Improve
Measure
Define
Identify needed data
Obtain data set
Evaluate data quality
Summarize & baseline data
Identify possible solutions
Select solution
Implement (pilot as needed)
Evaluate
Define control method
Implement
Document
Analyze
Explore data
Characterize process & problem
Update improvement project scope & scale
Are there any hypotheses that need to be tested?
What causal factors are driving or limiting the capability of this process?
What process map updates are needed?
Are there any immediate issues to address? Any urgent and obvious needs for problem containment?
Notes: Improving Process Performance Using Six Sigma
Module 5: Cost and Schedule – A Case Study in Variability Reduction

## Slide 76: Characterizing the Process and the Problem
What causal factors are driving or limiting the capability of this process?
To find out how to reduce organization costs and reduce effort variance, we need
  further analysis to refine the quantitative goal statement
  to complete root cause analysis and process improvement until the target goal is reached
D
M
A
I
C
Notes: Improving Process Performance Using Six Sigma
Module 5: Cost and Schedule – A Case Study in Variability Reduction

## Slide 77: Causal Analysis of Effort Variance
We’ll follow this basic plan for our causal analysis:
  brainstorm about causes
  establish cause codes taxonomy to classify reasons for variation
  access additional data from the archives
  perform further data exploration and comparative analysis
  identify a transfer function (prediction equation) for effort variance as a function of several cause factors
D
M
A
I
C
Notes: Improving Process Performance Using Six Sigma
Module 5: Cost and Schedule – A Case Study in Variability Reduction

## Slide 78: Exercise: Effort Variance
Your intern is taking care of routine data analysis so you can shift your attention to the complexities of root cause analysis.
Your task is to explore and prioritize root causes of project effort variances.
Using your toolbox of techniques taught earlier this week, your group will:
  explore and analyze the dataset
  document performance baselines of all factors
  be able to predict future project effort variances
  identify process improvement actions to reduce effort variance
▼Minitab – Case3Exercise3.mpj
D
M
A
I
C
Notes: Improving Process Performance Using Six Sigma
Module 5: Cost and Schedule – A Case Study in Variability Reduction

## Slide 79: Exercise: Instructions – Data Dictionary
▼Minitab – Case3Exercise3.mpj
Case3Exercise3.mtw
D
M
A
I
C
Variable Name | Comment on what it is
ProjectID | Assigned
EffortVarPercentage | Outcome we are interested in
StaffTurnoverPercentage | Annualized staff turnover rate on each team
TechnologyDifficulty | Result of checklist tallies on difficulty of the technology used in that team
ForecastingExperience | Average yrs experience of forecasters on each team
DevelopmentEnvironment | Modernity of the development environment
DevStaffExperienceYrs | Average yrs experience of all team members
SoftwareSizeKSLOC | Basline total size of configuration items in that team
DaystoCompleteReqts | Duration of Requirements activities (calendar time)
WeekOfYearToBegin | Workweek on which the effort began
ProgrammingLanguage | Categories
TypeOfReuse | Categories

## Slide 80: Exercise: Instructions
As individuals,
  Think of your approach to first graphically and then statistically explore this data set for relationships to the Effort Variance.
In your group,
  Agree and document a data exploration plan on the flippad.
  Agree on what graphical charts to generate.
  Agree on what comparative tests to perform.
  Agree on how to develop a transfer function to predict effort variance.
In your group,
  Create and discuss all charts including all performance baselines.
  Perform all statistical analysis and document which factors are significant along with the transfer function.
Debrief
  Each group reports results (5 min/group).
  Class discussion.
  Does this case study situation reflect any of your organization’s reality?
    Record actionable ideas on your “at-home project” form.
▼Minitab – Case3Exercise3.mpj
Case3Exercise3.mtw
15 min.
30 min.
30 min.
20 min.
D
M
A
I
C
Notes: Have the students turn in their attach plan after 5 minutes.
Remind the students that we need to see the best Regression and best ANOVA.
Improving Process Performance Using Six Sigma
Module 5: Cost and Schedule – A Case Study in Variability Reduction

## Slide 81: Exercise: Debrief
What graphical charts of the data did you use?
What were the current performance baselines?
What factors were identified as significant in predicting effort variance?
What transfer function did your group identify to predict future project effort variance?
What problems or questions did your group encounter?
  Did you have any problem creating or interpreting charts?
D
M
A
I
C
Notes: During the debrief, don’t forget to make the following points:
There is no one best regression model.
If models of similar Adjusted R2 values exist, the models with fewer number of factors are more simple and preferred.
All of these models should be retained as it is uncertain which factors will be measurable for a given situation in which a prediction is required.
Improving Process Performance Using Six Sigma
Module 5: Cost and Schedule – A Case Study in Variability Reduction

## Slide 82: Analyze Guidance Questions
Define project scope
Establish formal project
Control
Improve
Measure
Define
Identify needed data
Obtain data set
Evaluate data quality
Summarize & baseline data
Identify possible solutions
Select solution
Implement (pilot as needed)
Evaluate
Define control method
Implement
Document
Analyze
Explore data
Characterize process & problem
Update improvement project scope & scale
Should the improvement goal be updated?
Is additional data exploration, data decomposition, and/or process decomposition needed? Is additional data needed?
Can I take action? Are there evident improvements and corrections to make?
Have I updated the project tracking and communication mechanisms?
Notes: Improving Process Performance Using Six Sigma
Module 5: Cost and Schedule – A Case Study in Variability Reduction

## Slide 83: Updating the Improvement Project Scope and Scale
Should the improvement goal be updated?
Now we’ll update the project scope & scale by
  establishing a SMART goal statement
  establishing a “management by fact” and populate with information gathered so far
D
M
A
I
C
Notes: Improving Process Performance Using Six Sigma
Module 5: Cost and Schedule – A Case Study in Variability Reduction

## Slide 84: Resultant Goal Statements
Schedule
  Reduce the total variance by decreasing the variance of the top 3 internal causes by 50% in 1 year.
  Reduce the impact of external causes by 50%.
Effort (Cost)
  Reduce effort variance due to the top two controllable factors by 25% within 12 months.
Measurement
  100% of projects reporting timely and accurate information within 1 month.
  100% of projects reporting reasons for variance within 6 months.
  The remainder of this case study will focus on schedule goals.
D
M
A
I
C
Notes: Consider asking students to take 5 minutes and evaluate goal statements for SMART-ness
Improving Process Performance Using Six Sigma
Module 5: Cost and Schedule – A Case Study in Variability Reduction

## Slide 85: Improve Guidance Questions
Define project scope
Establish formal project
Control
Analyze
Measure
Define
Identify needed data
Obtain data set
Evaluate data quality
Summarize & baseline data
Explore data
Characterize process & problem
Update improvement project scope & scale
Define control method
Implement
Document
Improve
Identify possible solutions
Select solution
Implement (pilot as needed)
Evaluate
What type of improvement is needed?
What are solution alternatives to address urgent issues and root causes of identified problems?
What are the process factors to be adjusted?
What is the viability of each potential solution?
What is the projected impact or effect of each viable solution?
Notes: Improving Process Performance Using Six Sigma
Module 5: Cost and Schedule – A Case Study in Variability Reduction

## Slide 86: Identifying Possible Solutions
Now we can create & launch our improvement plan, including additional related measurement infrastructure enhancements.
D
M
A
I
C
Notes: Improving Process Performance Using Six Sigma
Module 5: Cost and Schedule – A Case Study in Variability Reduction

## Slide 87: Identifying And Selecting Possible Solutions
What are solution alternatives to address urgent issues and root causes of identified problems?
Some improvement candidates for schedule variance included:
  develop tips for implementing Microsoft Project
  enhance interface between project and EV data systems to automate data transfer
  teach “Successful Techniques in Project Management” on site
  identify course in model-based estimating
  require a peer review of the project schedule before baselining
D
M
A
I
C
Notes: Improving Process Performance Using Six Sigma
Module 5: Cost and Schedule – A Case Study in Variability Reduction

## Slide 88: Improve Guidance Questions
Define project scope
Establish formal project
Control
Analyze
Measure
Define
Identify needed data
Obtain data set
Evaluate data quality
Summarize & baseline data
Explore data
Characterize process & problem
Update improvement project scope & scale
Define control method
Implement
Document
Improve
Identify possible solutions
Select solution
Implement (pilot as needed)
Evaluate
What are the relative impacts and benefits?
What are relevant technical and logistical factors?
What are potential risks, issues, and unintended consequences?
Notes: Improving Process Performance Using Six Sigma
Module 5: Cost and Schedule – A Case Study in Variability Reduction

## Slide 89: Improve Guidance Questions
Define project scope
Establish formal project
Control
Analyze
Measure
Define
Identify needed data
Obtain data set
Evaluate data quality
Summarize & baseline data
Explore data
Characterize process & problem
Update improvement project scope & scale
Define control method
Implement
Document
Improve
Identify possible solutions
Select solution
Implement (pilot as needed)
Evaluate
What is the action plan with roles, responsibilities, timeline and estimated benefit?
Is piloting needed prior to widespread implementation?
Notes: Improving Process Performance Using Six Sigma
Module 5: Cost and Schedule – A Case Study in Variability Reduction

## Slide 90: What is Failure Modes & Effects Analysis (FMEA)?
Description
  A method to identify, analyze and prioritize potential failure modes as part of the evaluation of a proposed solution
  DFMEA=FMEA for Design; PFMEA=FMEA for Process
Usage
  Determine failure modes’ effects on system, product and process performance
  Risk prioritization and mitigation
  Evaluate and prioritize effectiveness of failure prevention methods
  Root Cause Analysis
D
M
A
I
C
Notes: Explain that FMEA is so effective at promoting critical thinking by designer and process owners in anticipating what can go wrong, that many companies are requiring FMEA on all critical product designs and critical business processes. It really should be required on all process improvements before rolling out to the organization!
Improving Process Performance Using Six Sigma
Module 5: Cost and Schedule – A Case Study in Variability Reduction

## Slide 91: FMEA Procedure
  Describe process or product. (Process map or design)
  List key steps or functions.
  Identify potential failure modes for each step or function.
  Describe effects of failure and rate failure severity (1-10).
  List causes of failure and rate cause frequency (1-10).
  Identify how to detect causes and rate likelihood of escape (1-10).
  Calculate risk (Risk Priority Number) = severity x frequency x detection rating.
  Prioritize (especially RPNs > 200) and identify actions to reduce risk.
  Identify mitigation actions
  Re-calculate RPN’s assuming mitigation actions work.
Bold, italicized is for Product Design FMEA rather than Process FMEA.
D
M
A
I
C
Notes: Improving Process Performance Using Six Sigma
Module 5: Cost and Schedule – A Case Study in Variability Reduction

## Slide 92: FEMA (Process) RPN Multipliers
Scale | Frequency of Occurrence | Severity of the Failure | Probability of Detecting the Failure
1 | Failure is unlikely | Unlikely | 100% chance of detection
2 | Failures are few, and time between failures is large | 20% chance | 80% chance
3 | Relatively few failures | 40% chance | 70% chance
4 | Infrequent failures | 60% chance | 60% chance
5 | Occasional failures | 80% chance | 50% chance
6 | Frequent failures | 100% chance | 40% chance
7 | Failures occur often | Customer complaint | 30% chance
8 | Repeated failures | Serious customer complaint | 20% chance
9 | Failures occur more often than not | Requirement non compliance | 10% chance
10 | Failure is almost inevitable | Failure results in loss of life | 0% chance of detection

## Slide 93: Exercise: Risk-Reducing the Solution
Your task is to evaluate a portion of a Software Inspection Process depicted below by conducting a Failure Modes & Effects Analysis (FMEA) to anticipate issues with the proposed solution.
D
M
A
I
C
Work Product
Distributed to
Team
Members
Team
Members
conduct
independent
reviews
Independent
review results
tabulated
Inspection
Meeting Held
Results
addressed by
Author of
Work Product
Notes: Improving Process Performance Using Six Sigma
Module 5: Cost and Schedule – A Case Study in Variability Reduction

## Slide 94: FMEA Exercise Instructions
In your group (FMEA evaluation):
Step 1: Identify at least two failure modes per step
(Remember that a failure mode of a step is a defective output of that step)
Step 2: Identify at least one root cause for each failure mode
Step 3: Identify your severity scores, likelihood of occurrence scores and likelihood of escape scores for all rows in the matrix
Step 4: Calculate RPNs, identify some hypothetical mitigation actions for each row and recalculate RPNs assuming mitigation actions succeed.
Debrief
  Each group reports results (5 min/group)
  Does this case study situation reflect any of your organization’s reality?
    Record actionable ideas on your “at-home project” form
45 min.
20 min.
Hint: Fill out the template by column and debrief by row.
D
M
A
I
C
Notes: Instructors must remember to specifically clarify how to identify a failure mode of a process step. It is the state of deficiency of an output for a process step, e.g., it is a symptom. Also clarify what prevention and mitigation are.
Improving Process Performance Using Six Sigma
Module 5: Cost and Schedule – A Case Study in Variability Reduction

## Slide 95: FMEA Exercise: Debrief
Debrief three (3) rows of the worksheets.
What were your key process steps impacting schedule variance (failure modes)?
What were your key root causes of the process step’s behavior impacting schedule?
What were the Risk Priority Numbers you identified, and which were your top 3 key root causes?
What problems or questions did your group encounter in using FMEA to anticipate issues with the proposed solution?
D
M
A
I
C
Notes: Improving Process Performance Using Six Sigma
Module 5: Cost and Schedule – A Case Study in Variability Reduction

## Slide 96: FMEA Exercise: Debrief
Key points about FMEA:
Populate by column but communicate by row
FMEA can be used for living lessons learned
Test people make the best facilitators of FMEA
FMEA superior to Inspections
D
M
A
I
C

## Slide 97: Improve Guidance Questions
Define project scope
Establish formal project
Control
Analyze
Measure
Define
Identify needed data
Obtain data set
Evaluate data quality
Summarize & baseline data
Explore data
Characterize process & problem
Update improvement project scope & scale
Define control method
Implement
Document
Improve
Identify possible solutions
Select solution
Implement (pilot as needed)
Evaluate
Did the solution yield the desired impact?
Has the goal been achieved?
If piloted, are adjustments needed to the solution prior to widespread rollout? Is additional piloting needed?
How will baselines, dashboards, and other analyses change?
Notes: Improving Process Performance Using Six Sigma
Module 5: Cost and Schedule – A Case Study in Variability Reduction

## Slide 98: Validating Solutions on Projects
Our solutions have been implemented and must now be validated before we deploy.
We will include both a project-level view and an organizational view of cost & schedule variance reduction based on the improvements incorporated.
D
M
A
I
C
Notes: Improving Process Performance Using Six Sigma
Module 5: Cost and Schedule – A Case Study in Variability Reduction

## Slide 99: Project Cost & Schedule Management
What launches project level process improvement?
  Investigations based on dashboard trends (org and project)
  Countermeasure plans based on dashboard trends
  And, real-time project problems
Strategy for project level quantitative management:
  Transform project life cycle analysis into a view that is intuitive for project managers to use
  As “out of control” points occur, conduct simple causal analysis and resolution.
  When possible, calculate project-specific limits
  (future) Evolve methods of early detection and control
D
M
A
I
C
Notes: Improving Process Performance Using Six Sigma
Module 5: Cost and Schedule – A Case Study in Variability Reduction

## Slide 100: Variability Across the Life Cycle
It was hypothesized that there is more cost & schedule variability early in the project than later.
  relative to most current estimate
This was tested in 3 iterations.
project cost index
wider limits for projects in planning phase
narrower limits for projects in execution phase
D
M
A
I
C
Notes: Improving Process Performance Using Six Sigma
Module 5: Cost and Schedule – A Case Study in Variability Reduction

## Slide 101: Within Project Variance – Results
Percentile analysis resulted in 3 groupings:
  < 20% complete (planning)
  20-80% complete (majority of effort; routine execution)
  > 80% complete (converging on completion)
More data anomalies to resolve
  When *exactly* do projects “start” and “stop”?
  Are data from on-hold projects included? (NO)
  Should level of effort data be included? (Yes, but separately)
D
M
A
I
C
Notes: Improving Process Performance Using Six Sigma
Module 5: Cost and Schedule – A Case Study in Variability Reduction

## Slide 102: Control Guidance Questions
Define project scope
Establish formal project
Improve
Analyze
Measure
Define
Identify needed data
Obtain data set
Evaluate data quality
Summarize & baseline data
Explore data
Characterize process & problem
Update improvement project scope & scale
Identify possible solutions
Select solution
Implement (pilot as needed)
Evaluate
Control
Define control method
Implement
Document
Should data be compared to a range? If so, which range?
Does procedural adherence need to be monitored?
Notes: Improving Process Performance Using Six Sigma
Module 5: Cost and Schedule – A Case Study in Variability Reduction

## Slide 103: Estimate at Completion Prediction Model
*
Estimate at
Completion (EAC)
A Project Manager Friendly Indicator
Limits for schedule and cost variance for each grouping projected to a range around the estimate-at-completion values. Response guidance written for each zone.
The smallest green box is a confidence box for projects at the 80% progress point while the next, larger green box is the confidence box for projects at the 20-80% progress point.
The smaller and larger red (the 2 outermost) boxes represent the management specification of 10% and 20% allowable variance, with different scrutiny applied depending where a project falls.
D
M
A
I
C
Notes: Improving Process Performance Using Six Sigma
Module 5: Cost and Schedule – A Case Study in Variability Reduction

## Slide 104: Control Guidance Questions
Define project scope
Establish formal project
Improve
Analyze
Measure
Define
Identify needed data
Obtain data set
Evaluate data quality
Summarize & baseline data
Explore data
Characterize process & problem
Update improvement project scope & scale
Identify possible solutions
Select solution
Implement (pilot as needed)
Evaluate
Control
Define control method
Implement
Document
What updates are needed in the measurement infrastructure?
What process documentation needs to be updated?
What new processes or procedures need to be established?
Who is the process or measurement owner who will be taking responsibility for maintaining the control scheme?
Have we documented improvement projects for verification, sustainment, and organizational learning?
What are the realized benefits?
Is the project documented or archived in the organization asset library?
Have documentation and responsibility been transferred to process or measurement owner?
Notes: Improving Process Performance Using Six Sigma
Module 5: Cost and Schedule – A Case Study in Variability Reduction

## Slide 105: What Happened in the End
Improvements instituted
  measurement infrastructure expansion, automation
  cost and schedule variance cause code taxonomy
  estimating (training, minor process adjustments)
  adoption of “management by fact” format
  homogeneous sampling for cost and schedule data
Monitoring & control mechanisms
  organization: dashboards with charts for cost, schedule, defects, data quality, customer satisfaction
  projects: cost/schedule prediction model
Notes: Improving Process Performance Using Six Sigma
Module 5: Cost and Schedule – A Case Study in Variability Reduction

## Slide 106: Case Timeline
Lest you think this happened overnight:
  Initial baseline: 9/02 – 10/02
  Exploratory analysis, incl first 2 iterations of project level baselines: 9/02 – 12/02
  Measurement POC workshop to review all work to date: 12/02
  Idea for project level for EV model conceived: 12/02
  Management agreement to prototype dashboard: 12/02
  Refinement of dashboard, incl 3rd iteration of project level baselines: 1/03 – 6/03
  Initial root cause analysis & MBFs: 1/03
  Project level QPM and process mapping brainstorming meetings 4/03
Then hit a lull processes were developed and the organization prepared for Class B appraisal.
  Execute, execute, execute (data improvements, low hanging fruit on cost/sched improvements, projects begin using models): 9/03 to 10/04
Notes: The point here is to let people know that these things can take some time and that additional challenges build when the project exceeds 6 calendar months.
Improving Process Performance Using Six Sigma
Module 5: Cost and Schedule – A Case Study in Variability Reduction

## Slide 107: Case Summary
Problems
  Started with customer satisfaction
  Would have pursued defects to satisfy CMMI, but initial baselining showed significant variability in cost & schedule performance
  Aligned cost, schedule improvements to support business opportunities/growth
  Also identified several measurement infrastructure improvements
Solutions
  Indicator templates and improved operational definitions
  Improved customer satisfaction survey
  Procedural adherence
  Cause code taxonomy institutionalized
  Variety of estimating and project management countermeasures
Notes: Improving Process Performance Using Six Sigma
Module 5: Cost and Schedule – A Case Study in Variability Reduction

## Slide 108: Learning Objectives Achieved?
During this case, we:
  Applied DMAIC for project selection
  evaluated a measurement system
  analyzed cost & schedule variance data
  described a discovery process that supports the business and supports CMMI implementation
Now that the case is complete, you should be able to
  explain variation
  analyze, interpret & report data using
    Summarization and baselining tools
    Failure modes and effects analysis
  understand how to examine and improve the quality of your data set
  describe links between your work and CMMI
Notes: Improving Process Performance Using Six Sigma
Module 5: Cost and Schedule – A Case Study in Variability Reduction

## Slide 109
Questions?